United Nations Environment Programme

Half Yearly Progress Report

| Reporting Period: | From: | 1 July 2016 | To: | 31 December 2016 |
| --- | --- | --- | --- | --- |

- PROJECT GENERAL INFORMATION

| Project Title: | Enhancing The Conservation Effectiveness of Seagrass Ecosystems Supporting Globally Significant Populations of Dugongs Across the Indian and Pacific Ocean Basins (Short Title: The Dugong and Seagrass Conservation Project) |
| --- | --- |

| Executing Agency: | The Mohamed bin Zayed Species Conservation Fund (MbZSCF) |
| --- | --- |

| Project Partners: (note by the PC: the list contains the names of implementing Partners only) | Indonesia: Directorate of Conservation and Marine Biodiversity, Directorate General of Marine Spatial Management, Ministry of Marine Affairs and Fisheries, WWF Indonesia, Indonesian Institute of Sciences, Research Centre for Oceanography (RCO-LIPI); Center for Coastal and Marine Resources Studies, Bogor Agricultural University (IPB); Research Center and Development for Fisheries Resources (Puslitbangkan, BALITBANG-MMAF); Research Center and Development for Marine and Coastal Resources (P3SDLP, BALITBANG-MMAF); LAMINA Foundation Madagascar: Blue Ventures, Conservation Centrée sur la Communauté (C3), Madagascar National Parks (COSAP) Sahamalaza, Wildlife Conservation Society (WCS) and Secretary of the State at the Ministry of the Halieutic resources and the Fishery in charge of the Sea (SS in charge of the Sea) Malaysia: Department of Marine Park Malaysia Ministry of Natural Resources and Environment, Department of Fisheries Malaysia, Ministry of Agriculture and Agro-base Industry, Centre for Marine and Coastal Studies, Universiti Sains Malaysia, the MareCet Research Organization and Sarawak Forestry Corporation, Marine Research Foundation, Reef Check Malaysia Mozambique: Blue Ventures, Dugongos.org, Endangered Wildlife Trust (EWT) and the National Environmental Directorate, Ministry of Land, Environment and Rural Development Solomon Islands: World Fish, SICCP and Ministry of Environment, Climate Change, Disaster Management and Meteorology (MECDM) Sri Lanka: Biodiversity Education And Research (BEAR), Department of Wildlife Conservation, Ministry of Sustainable Development and Wildlife, IUCN Sri Lanka, National Aquatic Resources Research and Development Agency (NARA), Ocean Resources Conservation Association (ORCA) and Sri Lanka Turtle Conservation Project (SLTCP) Timor-Leste: Fisheries Directorate, Ministry of Agriculture and Fisheries, Conservation International, Blue Ventures and Biodiversity Directorate, Ministry of Commerce, Industry and Environment Vanuatu: Department of Environment and Conservation, Vanuatu Environmental Science Society (VESS), Vanuatu Fisheries Department, Department of Environmental Protection and Conservation |
| --- | --- |

| Geographical Scope: | Global, multi-country: Indonesia, Madagascar, Malaysia, Mozambique, the Solomon Islands, Sri Lanka, Timor-Leste, Vanuatu |
| --- | --- |

| Participating Countries: | Indonesia, Madagascar, Malaysia, Mozambique, the Solomon Islands, Sri Lanka, Timor-Leste, Vanuatu |
| --- | --- |

| Project actual start date | 01 January 2015 | Project intended completion date | 31 December 2018 | Project expected completion date | 31 December 2018 |
| --- | --- | --- | --- | --- | --- |

2. PROJECT PROGRESS AND RISK MANAGEMENT

2.1	Narrative of project progress during the past semester

This narrative report presents the progress of the Project on two levels, namely: (1) global, presenting the overall achievements and challenges for the global Dugong and Seagrass Conservation Project; and (2) country, giving an overview of country progress in the reporting period. The current report builds on information from 35 (out of 38) national projects, provided by 25 (out of 26) Partners. Madagascar and Vanuatu are the country champions of this reporting period because all Partners from these countries sent well-developed and documented progress reports. There are two project champions in this reporting period and these are (listed alphabetically below): Project MG4 in Madagascar, managed by COSAP Sahamalaza COSAP Sahamalza demonstrated a good progress with their data collection and communities work, updated regularly the Project Coordination Team (PCT) on their progress and promoted both the global Project and MG4 in national and local media, and documented well the progress made and challenges faced during this reporting period; and Project LK7 in Sri Lanka, managed by Sri Lanka Turtle Conservation Project (SLTCP) SLTCP were very active in this reporting period. They carried out a national art completion for school children, featuring marine ecosystems and species, and were monitoring the development of their incentives programmes in Kalpitiya to provide further capacity building to communities and make the link to markets. SLTCP kept a very good communication with the PCT. 2.1.1. Global Project Progress The Project achievements in the reporting period related to: National Projects As previously reported, all 38 project proposals were finalised. Funding agreements were signed for 37 projects and funding was provided to all of these. The cumulative amount disbursed in support of the national projects as of the end of December 2016 comprised 32.67% of the total GEF funds for the national projects.

Second meeting of the Executive Project Steering Committee (EPSC) The second meeting of the Executive Steering Committee of the GEF Dugong and Seagrass Conservation Project took place on 1-2 November 2016 in Kuala Lumpur, Malaysia. The meeting was hosted by the Department of Fisheries Malaysia, Ministry of Agriculture and Agro-Based Industry. The EPSC meeting was attended by 18 participants, among which 10 permanent members – eight Project country representatives (the National Facilitators), the UNEP/ GEF Task Manager and the Programme Manager of the CMS Dugong MoU – the Project Coordination Team (PCT) and representatives of the CMS Dugong Technical Group. The second EPSC meeting was chaired by the National Facilitator of Malaysia. All National Facilitators presented the progress, challenges, lessons learned and next steps for their countries. Improving the scientific rigor of data gathering (research) projects, Partners more proactively sharing their news, capturing women and youth involvement, ensuring sustainability of incentives and needs for better national and cross-region cooperation were the main needs identified for the national and the global Project to be addressed in 2017. The second EPSC meeting provided a good opportunity to demonstrate the conservation efforts towards dugongs and their habitats in Malaysia. The PCT together with the Malaysian Partners conceptualised and carried out a media briefing and a poster session, during which all Project Partners in Malaysia presented their work. Ten media representatives responded the invitation and attended the media briefing. The media briefing was led by Dato’ Haji Ismail bin Abu Hassan, Director General of Fisheries Malaysia and attended by UN Environment/ GEF Task Manager of the Dugong and Seagrass Conservation Project, the Programme Manager of the CMS Dugong MoU and the Project Coordinator. During the media briefing the Programme Manager of the CMS Dugong MoU invited Malaysia to formalise their contribution to dugong and seagrass conservation and DG Fisheries announced that Malaysia is proceeding with arrangements to sign the Dugong MoU at the Third Meeting of the Signatory States to the Dugong MoU, taking place on 13-14 March 2017. More information about the discussions and results from the second EPSC meeting can be found on www.dugongconservation.org (global Project activity 432) After the EPSC meeting, the PCT together with all Malaysian Partners visited one of the Project sites in Malaysia, Johor, where three of the Malaysian Partners work. The trip gave the opportunity to all Partners to demonstrate their work with communities and on dugongs and seagrass. The group visited two islands, included in the Johor Marine Park and met with local communities and Johor state authorities who share management responsibilities with one of our Partners in Malaysia. Project communications The Project website, www.dugongconservaiton.org, officially launched in May 2016, moved into an operation phase during the second half of 2016. The PCT team uploaded project documents, news items, newsletters, and updated project pages. In total, more than 36 news articles were published on the Project website. Social media integration into the site was also executed with multiple Facebook posts and Flickr uploads being incorporated into project pages. According to Google Analytics, since the launch of the website, 3,762 users, including both new and returning users visited the Project website spending on the average about 3 minutes per session. (global Project activity 331) The Dugong and Seagrass Conservation Project maintains a You Tube Channel. By the end of December 2016, the Communications Manager uploaded 7 videos to this channel. Collectively, these videos were viewed nearly 2,500 times for a total of 5,650 minutes. The most viewed video is the Project video, viewed more than 2,180 times in the second half of 2016. The Facebook page of the Project was launched in October 2015. All Project news and short posts are shared and published on the Facebook. In total more than 600 people liked the Project page since its inception. In the second half of the year, 544 people ‘liked’ the Project Facebook page. The top five countries from which the Project Facebook page ‘likes’ originated include Indonesia, Sri Lanka, United Kingdom, Malaysia, and the UAE. Another way to evaluate the impact of the Facebook page is by considering its ‘reach’ or the number of people who received a Facebook post. The most popular post from this time frame told a story of an Indonesian fisherman who released a captured dugong as a result of discussions with our local Project Partners. That post ‘reached’ more than 1,300 people. Other popular stories included two interviews with people working on dugong research, describing their field experience; one of featured people is a CMS DTG member. The Dugong and Seagrass Conservation Project also posts on Instagram, Twitter and Flickr. The Project electronic newsletter is distributed twice a year, covering stories from all Project Partners (who provided content) and upcoming events. One newsletter was distributed in August to a distribution list containing 123 subscribers. At the end of 2016, the same distribution list contained more than 200 email addresses – an increase of almost 75 subscribers. The additional email addresses were gained organically (through voluntary and unsolicited subscriptions), as well as the addition of subscribers by the Communications Manager. The email newsletter distributed in August was effective, with almost 50% of users opening the newsletter. During the second half of 2016, public relations efforts in print and traditional were also successful with excellent coverage in Malaysia and the United Arab Emirates of November’s Executive Project Steering Committee Meeting. Additional coverage of the project was generated by Project Partners in Indonesia and Madagascar. The Project Coordination Team worked with the Dugong Focal Point in Malaysia to ensure local coverage of the Dugong Project and the Executive Project Steering Committee. The public relations effort in Malaysia was very successful. The Dugong Focal Point organized a press event in which the Project Coordinator, UNEP representative and CMS representative participated. Malaysian print news covered the event/project. So, too, did the Malaysian television news channels. The Project also gained coverage of the event in the United Arab Emirates. Three newspapers covered the story including Al Ittihad, Al Khaleej, and Al Bayan – all Arabic language newspapers. (global Project activity 332) CMS Dugong MoU Secretariat’s support to the Project In the second half of 2016, the CMS Dugong MoU Secretariat and the Dugong Technical Group (DTG) continued to support the global Project. Five experts reviewed all national projects progress reports for the first half of 2016 and provided important feedback and recommendations on the way forward for each project. The Project Coordination Team shared the feedback with the Partners and subsequent steps were taken to address them, including putting in contact Partners with DTG members to get technical support. PCT asked all Partners to report on how they have addressed the feedback and recommendations from the CMS DTG in section 3.1 “Monitoring and Evaluation” of their half-yearly progress reports for the second half of 2016. The process of review by DTG members will continue until the end of the Project. (global Project activity 321) Virtual Project Repository In October 2016, the PCT launched the Virtual Project Repository. The Virtual Project Repository is a Dropbox Professional account of the global Project allowing for sharing and storing of progress and supporting documents for each national project and for the global Project. The structure and initial content for all the projects (until first half of 2016) were uploaded by PCT and were already available for all Partners since the launch of the Repository. PCT created written and audio-video guidelines for the Partners on how to use the Repository and provided editing rights to each national project team. Partners are expected to upload all their reports and supporting documents by themselves and have been given the opportunity to upgrade and obtain the Professional version of their national project Dropbox. The second half-yearly progress reporting was the first time when Partners started to use the Repository themselves. The Virtual Project Repository is considered as an important element of the Dugong and Seagrass Conservation Project heritage and the plan for it is to have all the information on a national and global Project level available to the Project countries, CMS Dugong MoU Secretariat, UN Environment and the GEF. (global Project activity 432) Preparation for and start of the mid-term review of the Project PCT briefed all Project Partners on the process through power point presentation and Skype discussions. All Partners supported the preparation for the mid-term review. Three independent consultants were selected to carry out the review of progress on a country and global Project level. Three country clusters were formed and four thematic areas, the Project components, are planned to be addressed by the mid-term review team. The Project mid-term review (MTR) began in December 2016. Challenges In this reporting period, PCT faced two main challenges, related to ensuring the robustness of the Research Project Component and internal communication. All Project Partners had the opportunity to meet the CMS Dugong Technical Group experts during the Project Inception workshop, held in October 2015. Partners were advised that there are seagrass and dugong experts within the CMS DTG, who are ready to help them in their research and other project efforts. However, only one Partner had contacted CMS DTG last year. After the first half-yearly progress for 2016, CMS DTG reviewed the national projects and provided recommendations on their implementation. This related especially to methodologies, tools and techniques adopted by the Partners. The main observation of the DTG experts was that if the Partners had contacted them before embarking on their activities, DTG’s advice could have saved them the Project time and money, and would ensure consistency and comparability of data. PCT tried to push for this collaboration but it was very challenging given the lack of response by most Partners. The second EPSC meeting in Kuala Lumpur provided the opportunity to discuss this issue and PCT is following up on the advice provided during the meeting to ensure the sustainability of Project deliverables. Internal communication has been identified as a challenge because many Partners still miss to share their stories, news and even data. 2.1.2. Country Project Progress In this section, the report on each country contains a table summarising the projects, the main Project Components (Knowledge, Community-based site management or CBM and Incentives, Policy and Awareness) that they contribute to and the Partner, leading the project. NFC projects relate to the Policy Project Component. The report on progress in this section gives the progress “highlights” as drawn from each national project, which formed the basis for reporting on progress by global Project activity later in this report. A reference to the global Project activities that each national project contributes to, is provided between brackets after the related progress reported. The reports of this reporting period as well as supporting documents can be found on on the Virtual Project Repository and can be provided by the Project Coordination Team on request. These will also be available on www.dugongconservation.org Project ID and name Project Partner Project Component D 1 Strengthen and operationalize national policy strategy and action plan for dugongs and seagrass conservation Directorate of Conservation and Marine Biodiversity, Directorate General of Marine Spatial Management, Ministry of Marine Affairs and Fisheries, Projects to be administered by WWF Indonesia Policy ID 2 Improving National Awareness and Research of Dugong and Seagrass in Indonesia Awareness & Knowledge ID 3 Community Based Conservation and Management of Dugong and Seagrass Habitat in Bintan, Alor, Tolitoli and Kotawaringin Barat, Indonesia Incentives INDONESIA All the three proposals have been finalised in Indonesia. As of December 2016, 19% of the total GEF funding available for ID1, ID2 and ID3 was released for the implementation of the projects. The objective of ID1 is to strengthen and operationalize national policy strategy and action plan for dugongs and seagrass conservation. The project has three main deliverables, namely the legalisation of a Dugong and Seagrass National Plan of Action (NPOA), the establishment and operationalisation of a National Dugong Conservation Committee, and the national level coordination among all Project Partners in Indonesia. As reported in the previous report, an initial draft of Dugong and Seagrass National Plan of Action (NPOA) was developed through expert discussions at a national level. The draft NPOA integrated the recommendations from a 2016 Symposium, previously developed by LIPI dugong strategy and action plan in Indonesia, and the strategic and action plan for protected and threatened species prepared by CMB-MMAF. In this period, ID 1 finalised the draft Dugong and Seagrass National Plan of Action (NPOA). The ID1 team undertook initial steps towards the legalisation of the Dugong and Seagrass NPOA – several internal meetings with the Legal Division of Directorate General of Marine Spatial Management were carried out to discuss the steps of the process (global Project activity 413) The National Dugong Conservation Committee (NDCC) initiated in the previous period has not been yet established and legalised by the MMAF, pending on formal confirmation of two organisations - P3SDLP (Research Centre and Development for Marine and Coastal Resources) and PSDI (Directorate of Fish Resources Management). Two preliminary meetings of the NDCC members were carried out in August and September 2016, to discuss the project plan and coordinate the Dugong and Seagrass National Plan of Action. (global Project activity 431) Project ID2 aims to enhance awareness on dugong and seagrass conservation and management, improve the capacity of research and monitoring of dugong and seagrass and provide scientific information to support seagrass and dugong conservation and management. The main deliverables of the project include a set of communications and scientific materials that would enhance the national capacity for dugong and seagrass conservation. These include surveys of the level of awareness on dugong and seagrass, national communications strategy and media campaigns, as part of the communications work. The scientific work is planned to deliver updated data on dugong and seagrass distribution in selected sites, a national standardised methods on dugong and seagrass research and a methodology on assessing carbon sequestration by seagrass ecosystems. In this reporting period, the team of project ID2 advanced substantially with both components of the project work, communications and research. Following the National Symposium on Dugong and Seagrass Habitat reported in the last period and the first field survey in Alor, the team focused on updating and gathering new information on communities, dugongs and seagrass from Bintan, Toli-toli, Kotawaring Barat and Sangihe. The CMS Dugong MoU questionnaire was conducted in the four project sites, followed by field research of dugongs (feeding trails) and seagrass identification. The results from the surveys will be used to identify the baseline situation in the four pilot sites and will feed the design of the incentives, to be introduced in selected sites. The result from each project site can be summarised as follows: Bintan, 21 respondents were interviewed using the CMS Dugong MoU questionnaire. Nine species of seagrasses were identifed. No dugong was sighted, even though several feeding trails were recorded. Instead of dugong, survey team recorded the sigthing of around 25 irrawaddy dolphins. In Tolitoli, 29 respondents were interviewed. Ten species of seagrass were identified. The presence of 4 dugongs were recorded during aerial survey in Ogotua waters. In Kotawaringin Barat, 16 respondents were interviewed. Ten species of seagrass were identified. No dugong was sighted, even though several feeding trails from seagrass survey and sound of dugong from bioacoustic survey were recorded. In Sangihe, 10 respondents were interviewed. Five species of seagrasses were identified. Two dugongs were recorded from aerial survey, while one dugong was recorded and observed during underwater survey in the waters of Likuang Village. The preliminary surveys contributed to the development of maps of dugong and seagrass distribution in the four studied areas and were integrated in technical reports (still draft). WWF Indonesia provided as own contribution additional maps of dugong sighting area, foraging habitat and playing ground from Sangihe. (global Project activity 311) The communications work of the team in this period resulted in the following deliverables: Preliminary assessment of the level of awareness in the four pilot sites – out of the 76 respondents, interviewed during the field surveys, more than 90% said that dugong should live freely in the sea; more than 50% said that dugongs’ presence is important; and between 68-85% of the respondents were already aware that dugongs are protected and catching dugong on purpose is considered as an illegal activity Increasing media presence of the project in Indonesia – the team created a Facebook account of the Project in Indonesia, “Dugong and Seagrass Conservation Project Indonesia”, in October 2016, quickly attracting fans. 6 news articles were published on social media (Please refer to section 4.5 of the Half-yearly report for more details) (global Project activity 422) Project ID3 is the incentives project in Indonesia. ID3 project proposal was finalised by the team, following a series of discussions and a meeting of the Indonesian team with the Project Coordinator, a CMS DTG member, Dr Nicolas Pilcher, and Programme Manager of the CMS Dugong MoU, Dr Donna Kwan, held in October 2016. The Partners and the visiting team reached a common understanding of the term “incentives” and agreed on overall project activities and budget distribution. The proposal was successfully submitted in November 2016 and the Funding Agreement was signed by the Indonesian Partner in December 2016. The main deliverables of ID3 include designing and introducing incentive mechanisms and tools enhancing community-based dugong and seagrass conservation in 3 sites, Toli-toli, Kotawaringin Barat and Alor, and building local capacity for the implementation of the incentives. It will also deliver better integration of seagrass and dugong safeguards in the business activities of tourism developers in Bintan. During the reporting period, the Indonesian team already started some feasibility studies in in the projects sites and carried out consultations with local authorities and stakeholders on the implementation of the project. MADAGASCAR Project ID and name Project Partner Project Component MG 1 Building a model for innovative long-term community-based conservation of seagrass-dependent biodiversity in Madagascar Blue Ventures Community-based management MG 2 Fisher knowledge, awareness and behaviour change for the conservation of dugongs and seagrass using the Mihari network of Locally Managed Marine Areas in Madagascar Blue Ventures Awareness MG 3 Using incentivized Environmental Stewardship to conserve dugongs and seagrass habitat at an identified national hotspot Conservation Centrée sur la Communauté (C3) Incentives MG 4 Integrated approaches to enhance the conservation dugongs and seagrass ecosystems in Sahamalaza areas Madagascar National Parks (COSAP) Incentives MG 5 National Steering Committee for the GEF Dugong and Seagrass Conservation Project Secretary of the State at the Ministry of the Halieutic resources and the Fishery in charge of the Sea (SS in charge of the Sea) Policy MG 6 Dugong and seagrass conservation in North West Madagascar Wildlife Conservation Society (WCS) Knowledge All six proposals in Madagascar were finalised by June 2016. The total amount of the disbursement to projects in Madagascar by December 2016 was 38% of the total GEF funding available for Madagascar under the Dugong and Seagrass Conservation Project. The objective of project MG1 is to build a model for long-term community-based conservation of seagrass-dependent biodiversity in Madagascar. MG1 works in Barren isles Marine Protected Area and several other Locally Managed Marine Areas in Madagascar. Key deliverables of project MG1 are the establishment of at least four permanent “no take” seagrass reserves, the adoption of local marine mammal hunting rules (regulation called “Dina”) together with communities, capacity building of authorities and local communities for dugong and seagrass assessment and monitoring, and awareness raising targeting destructive fisheries. After the training on participatory seagrass mapping in six sites, carried in the first half of 2016, Blue Ventures (BV) continued working with communities to increase their understanding of the role of seagrass and seagrass-dependent species (including green turtles and dugongs) for communities and their livelihoods. The team carried out 22 meetings to share the results from the mapping of seagrass beds and consult with communities on the marine mammal hunting rules. (global Project activity 132) BV reported that recently dugongs have been rarely seen in the Barren Isles. They had to adapt their awareness raising work by taking other seagrass dependent species, such as the sea turtles, to explain the importance of seagrass to communities in the Barren Isles. Vezo fishers (“Vezo” meaning people that have become accustomed to live from sea fishing) have been traditionally hunting and eating turtles for generations, but their fishing methods have intensified through the use of nets, leading to a population decline, despite the laws protecting them. A series of workshops were held, at which authorities reiterated the total ban on hunting, eating and selling sea turtles. BV used the opportunity to tell a story about a fictitious village that experienced negative impacts from the disappearance of turtles, highlighting their role in the ecosystems and their vulnerability. BV also facilitated a debate to identify community rules which locals would be ready to enforce themselves. A positive impact of this strategy could be measured during BV’s field visit, where a Vezo Miray representative of one village told the turtle and seagrass story to the local community. (global Project activity 132) As it was reported in the previous period, seven potential sites were identified to carry out seagrass mapping. In the first half of 2016, weather conditions allowed for mapping seagrass beds along four of the sites only. In this period, the mapping for the other three sites was completed along the islands of Nosy Abohazo, Nosy Manandra and Nosy Marify. The participatory mapping and assessment included community meetings where the objectives and methodology were presented, followed by field (underwater) assessment. Areas with seagrass, located close to the islands, where local communities could establish permanent or temporary reserves, were defined as priority habitat areas. Between all three sites visited, Nosy Abohazo stood out as a potential model area of community-based seagrass monitoring because of the motivation and readiness of local communities to engage. The participatory habitat assessment and mapping contributed to discussing and identifying management measures in each village, including permanent and temporary reserves. All seven sites were included in those discussions and the information obtained will help the team of project MG1 to develop a zoning plan for Barren isles Marine Protected Area, delineating clearly the areas of permanent and temporary reserves and integrating seagrass and coral reefs. The results of the participatory assessment and mapping of seven islands of the Barren isles archipelago were presented during a workshop with Vezo Miray representatives and local authorities. (global Project activities 131 & 132) In addition to the participatory mapping, BV initiated the development of the community-led Monitoring, Control and Surveillance (MCS) programme. Meetings with communities in the two biggest villages helped gain support from local communities for the MCS programme, to determine the structure of the surveillance body (number of agents per village), identify a list of priorities that would be subject to surveillance and the equipment needed. (global Project activity 211) Awareness raising activities comprised a community outreach tour in Maintirano. The team of project MG1 invited the ex-President of the Velondriake fishers association (located in south-west) to present to the fisher communities in the Barren isles Marine Protected Area the work on sustainable community-based marine resources management, as conducted by Blue Ventures. He explained the advantages of implementing temporary and permanent reserves, which at the time were still scary concepts for the fishers in Barren isles MPA. In support of awareness raising and experience exchange, MG1 team organised a community exchange from the Barren Isles to Belo-sur-Mer.(global Project activity 221) Project MG2 aims to stir a behavioural change among local fishing communities for the conservation of dugongs and seagrass through awareness and knowledge raising. The Project is implemented by Blue Ventures in partnership with the MIHARI, a network of Locally Managed Marine Areas in Madagascar. The network has nearly 150 members and meets regularly every year. Key deliverables of MG2 include identification of dugong and seagrass priority sites and raising the awareness of local communities for the importance of their conservation, and capacity building for integrating seagrass management and dugong conservation in the management of Locally Managed Marine Areas (LMMAs). Despite issues with the staff capacity, project MG2 advanced in identifying the priority sites for dugongs and seagrass conservation and awareness raising activities. The identification was made through discussions with NGOs and site visits, during which members of local communities were interviewed. Baseline information on community awareness on dugongs was collected during events, organised by MIHARI, including the MIHARI regional forum in July 2016 in Ambanja, the Dugong Education and Awareness Day, in July 2016 in Nosy Hara, the National Days of Fisheries and Aquaculture in September - October 2016, as well as during the Dugong Festival, held in October 2016 in Nosy Berafia and organised by COSAP Sahamalaza, implementing project MG4. (global Project activities 113 & 221) Potential sites for dugong conservation in three districts, Ambanja, Ambilobe and Analalava, were identified, where MIHARI team will continue education/awareness, participatory mapping training and will provide legal support for the establishment of Dina Nine villages located in the three districts, Ambanja, Ambilobe and Analalava, were visited and 130 local community members were interviewed to assess the baseline situation on awareness and fishing practices, and identify needs for subsequent actions. Five main findings emerged during those activities: Fishers recognize dugongs and seagrass among other species/ habitats and have interesting information about their biology, their traditional use and importance. Fishers are all able to identify dugongs and seagrass hotspots in the area of their village. All fishers the MIHARI team have met have seen dugongs at least once. Communities are aware that the number of dugongs have declined in the last 10 years and seeing them now is unbelievable Despite this, only half of the communities acknowledged that they should change their behaviour when seeing dugongs as they are now rare. (global Project activity 221) The events organised by MIHARI, as reported above were used to identify LMMAs, which are also dugong hotspots. Five criteria related to observations and data on dugongs, sites accessibility and the presence of a supporting partner (an NGO) resulted in selecting the following sites for further conservation actions: Nosy Faly supported by Blue Ventures and Ampasindava supported by Missouri Botanical Garden (both communes located in Ambanja), Ankazomborona, located in Ambilobe, supported by WWF, Analalava, located in Analalava district and commune, supported by Opti-Pousse-Haie and Anjajavy supported by Anjajavy le lodge. MG2 team will support the communities in these areas as well as in Nosy Be to develop their local restrictions and rules on marine and coastal resource use (“Dina”). (global Project activity 113) Project MG3 works in Nosy Hara Marine Park (183,100 ha), Diana region, northern Madagascar and aims at zero dugong mortality and effective protection of seagrass habitats through an incentive-based conservation programme. Key deliverables of project MG3 include the development of illegal fishing database, establishment of two successful livelihoods enterprises, development of a women healthcare clinic, furnishing 4 local schools, training 100 eco guards and raising awareness. The Project is implemented by C3, who work in partnership with local communities and the Local Park Management (CLP) made up of representatives of each of 21 communities across the Park. A total of 21 live dugongs (+3 as compared to the previous period) reported since the project inception from 9 different locations and zero dugong mortalities, with most sightings from the north and west parts of the Park. Two of the sightings included a mother and calf pair and there was also one group of four dugongs spotted. MG3 team started to explore a potential dugong hotspot, engaging with the relevant fishers to get more information on this area. (global Project activity 311) Following the optimization of the Park governance structure, as proposed by C3 (reported in the previous period), C3 and the three regional structures of Nosy Hara Marine Park met monthly to discuss the progress and plan the project activities. (global Project activity 114) The Nosy Hara Marine Park has restrictions for local communities on marine and coastal resource use, “Dina”, and these require to be updated in a participatory manner. In the last reporting period, C3 signed an Agreement with MIHARI (MG2) to get legal advice on the development of the Dina. MIHARI were unable to assist C3 in starting this activity before December 2016. C3, in completion of their responsibilities under the Agreement, shared promotional materials with MIHARI and sent staff and Junior Ecoguards to assist them with outreach events in Nosy Hara Marine Park. Staff trained by C3 also ran a staff training session on dugong ecology and conservation for MIHARI in Antananarivo in November 2016. (global Project activity 121) The forty Conservation Ambassadors (CAs) from all 21 villages continued to be involved in monthly conservation activities including dugong incidental sighting reporting, illegal fisheries reporting, community outreach events, seagrass monitoring, Local Park Management meetings and assistance with C3’s incentives schemes (livelihoods, health and schools programmes). (global Project activity 123) The Junior Ecoguard programme expanded to a further 20 schools in the Diana region and the delivery of toolkits was completed in communities across northern Madagascar. C3 received partial funding towards expanding the programme to 3 new provinces (global Project activity 123) C3’s incentives programme was running well but not without challenges. Monthly fisheries monitoring was conducted at the three primary landing sites across the Park by six trained CAs. Interesting findings of rare or data-deficient species included Tawny nurse sharks, Grey Reef sharks, Honeycomb Stingrays and Grey Spotted Guitarfish. Reporting from the CAs showed that no turtle poaching or harm to other marine megafauna was observed but there were accounts of some illegal fishing gear (e.g spear guns) being used. Annual seagrass monitoring was conducted at four sites as planned: Lalandaka, Vahilava, Ironono and Agnahibe. More marketing materials were produced for the women ecotourism restaurant and tour companies in Diego. Unfortunately, in September disaster struck the poultry farm with disease leaving only 6 chickens. C3 consulted with agricultural specialists and the community about remedial actions and will take action in improving or relocation of the farm. Following the feasibility studies for new livelihoods, a goat farm was planned in Lalandaka (a dugong hotspot) and a duck farm in Andranomavo. In November training was carried out in enterprise management with CLPs an integral part of this process. (global Project activity 213) As part of the incentives to local communities, C3 began a health service programme (a doctor and a midwife visit communities on a monthly basis) and a school programme, improving education conditions for pupils in three schools. Monthly visits of a general practitioner and midwife began in June under formal collaboration with the Ministry of Health. Construction of a new well to provide drinking water for the community in Ampasindava was completed in August 2016. (global Project activity 213). A promotional film on C3’s work in Nosy Hara Marine Park was completed and will be disseminated in from January 2017. (global Project activity 121) C3 teamed up with the famed clothes company of the Indian Ocean islands, 'Baobab clothing', to produce fundraising dugong t-shirts and informative posters for their shops across Madagascar, with a proportion of profits going to C3's dugong conservation work. (global Project activity 221) Four major outreach events took place at Lalandaka village (a dugong hotspot), Diego city (World Environment Day), Ambodivahibe protected area (festival) and Mangoaka village (regional reforestation event). Outreach materials designed and distributed include dugong information boards, posters, t-shirts and factual postcards. (global Project activity 422) Project MG4’s objective is to improve the protection of endangered dugongs and the seagrass ecosystems in the northwestern coastlines through community-based monitoring, capacity building and applied conservation strategy MG4 works in Sahamalaza Marine and Costal UNESCO Biosphere Reserve (153,200 ha of which 26,035 ha is Marine and Costal National Park), and is managed by an association of local communities, Park and other local authorities, and NGOs, called COSAP Sahamalaza. Key deliverables of project MG4 are development of Dugong and Seagrass Community Conservation Groups in 14 villages, update of the management plan of Sahamalaza to integrate a monitoring plan on dugongs and seagrass, development of two livelihoods enterprises and development of Dina for regulating fishing in all, twenty governance structures on the territory of the park. Since the start of the project, ten Dugong and Seagrass Community Conservation Groups (+2 as compared to the previous reporting period) were established. The Conservation Groups were initiated in Mahadera and Ambalabao fishing villages, following workshops on collecting baseline information on dugongs and on the preparation of the local convention on regulating fishing and protection of emblematic species. The governance structures of Mahadera and Ambalabao were respectively named “Fitaramazava” and “VOI Ambalabao”. In September 2016, the two new conservation community-based structures adopted their own local convention or Dina. (global Project activity 114) MG4 team continued to conduct surveys in Nosy Valiha and in several sites located along the eastern and western sides of Sahamalaza Peninsula for consolidating the information on dugongs and seagrass. A student from the University of Mahajanga was involved in the collection of additional data using the CMS Dugong MoU Questionnaire. The team created a database of the historical sightings of dugongs in Sahamalaza area from the 1980s to the 2010s. Additionally, maps of survey sites during 2016 were developed. (global Project activities 311) The community members in the previously identified dugong hotspots, located in Ambatolava (East of Berafia island), Ankasetra (West of Valiha island) and Ambatobe (in Sahamalaza bay) reported to the team of project MG4 the results of their monitoring activities. A total of four sightings of mother-calf pair were reported between June and October 2016 in the waters of Berafia. (global Project activities 311 & 313) The twenty existing community-based structures in COSAP participated in the protected area patrolling. During the period, 960 person/ day of patrolling were realized. (global Project activity 313) COSAP Sahamalaza worked actively on awareness raising of local communities on dugongs and seagrass. They participated in the Lemur Festival, one of the annual outreach events organized in Sahamalaza Area for raising awareness of the environment and conservation. MG4 team took advantage of this event to raise the public understanding on dugongs and seagrass. The global Project factsheet was translated and exhibited during a poster session. Apart the administrative authorities, most of the visitors were pupils. They asked many questions related to dugong such as the size, lifespan, reproduction, number of calf. (global Project activity 221) MG4 team organised the first ever Dugong Festival in Madagascar, reaching out a large audiences and engaging them in thinking about conservation of dugongs and seagrass in Sahamalaza. The moto of the Festival was “Hasondrotrontsika miaraka ny fiarovana trozogno ndraiky ahi-dramasina agnatin’ny hôban’ny Sahamalaza“- Together, we enhance the conservation of dugong and seagrass in the coastal zone of Sahamalaza.” The festival was a success, with more than 1,000 people attending, including high officials and authorities from Sofia and Diana Regions, NGOs, local private partners, migrant fishermen and local community. Following the Dugong Festival, MG4 team undertook three expeditions to promote the regional conservation effort on dugong and seagrass under the GEF project and to mobilise support among the local authorities of the coastal regions of Diana (Ambanja and Antsiranana) and Sofia (Antsohihy). (global Project activity 221) The communications activities included the development and distribution/ display of banners, traditional piece of textile and T-shirt to convey the message on the protection of dugongs. Media, including the national radio and television stations as well as the GEF Project website and Facebook were used to support communications activities of MG4. (global Project activity 221) Project MG5 is the National Facilitating Committee in Madagascar. MG5 is led by a government institution, the Secretary of the State at the Ministry of the Halieutic resources and the Fishery in charge of the Sea. Key deliverables of MG5 include the establishment of the National Facilitating committee and the development of a National Strategy including legal framework for the conservation of dugongs and their seagrass ecosystems. Although MG5 proposal had been finalised in the first half of 2016, a Funding Agreement between the MbZ Fund and the Secretary of State in charge of the Sea was still not signed because of administrative and regulatory obstacles on the side of the Partner. Funding was not provided to this project but costs made by the team on the attendance of the Executive Project Steering Committee were covered by the Project Coordination Team. The Secretary of State in charge of the Sea organised two meetings with all Partners in Madagascar – one in July 2016, to kick-off the National Facilitating Committee and one in October 2016 to coordinate on the preparation for the mid-term review and for the Executive Project Steering Committee. (global Project activity 432) Project MG 6 aims to improve the conservation status of dugongs and seagrasses through reduction of knowledge barriers on dugong populations and habitats, and trialing of community-led conservation initiatives in Northwest Madagascar. The project is implemented by WCS covering two MPAs – Ankivonjy (139,409 hectares), located in District Ambanja, Region Diana and Ankarea (135,556 hectares), located in District Ambilobe, Region Diana. Key deliverables of the project are maps of dugong habitats, dugong acoustic detections and presence/absence information in 12 sites, CMS Dugong MoU Questionnaire applied in 100 local villages, dugong and seagrass monitoring integrated in the management plans of two Marine Protected Areas and three piloting conservation actions reducing threats to dugongs and seagrass. During the reporting period, the project continued monitoring activities in the northern section of the study area and prepared for starting monitoring activities in the southern section in 2017. Activities included finalizing the seagrass mapping, completion of the additional community interview surveys and re-deployment of acoustic loggers in the northern section of the study area. (global Project activity 311) Fine scale seagrass mapping through field observations in the northern part of the project study area was undertaken in September 2016 in order to ground truth the remote sensing data on seagrass beds distribution and to organize the deployment of acoustic loggers. The seagrass maps in the southern region of the study area were finalised in October 2016. Maps will be used to organize both community interviews and deployment of acoustic loggers in the areas. The project also collaborated with researchers from Stockholm University who are investigating carbon sequestration and storage in the seagrass beds in Nosy Be, around the deployment area of acoustic loggers. A Master’s student from the Fisheries and Marine Studies Institute in Toliara was taken on to participate in the seagrass project under the supervision of WCS staff. The student joined the WCS’ team for three weeks in November 2016 to assess carbon storage in seagrass beds through observation of sediments and seagrass productivity. The team focused on disturbed seagrass areas where there is a loss of mangroves as well as considerable fishery activities, and undisturbed seagrass areas, which are defined as a clean ecosystem without anthropogenic perturbation. For each area, samplings were done close to mangroves, on seagrass beds, and on sandy substrate. Following the 126 community interviews in 42 villages carried out in first half of 2016, MG6 team continued the community interviews to gather information on local knowledge and impacts of human activities on dugongs and other marine mammals in this region. Two interviewers from Ambanja were hired to conduct additional community interview surveys in the northern study area. Interviews were held in 12 villages in the bays of Ambaro and Ankify over a two-week period. Collected data are currently being checked and analyzed. As previously reported, WCS deployed six acoustic loggers in the northern study area but three of them were lost. WCS team discussed on the solutions with technical advisors and the Project Coordination Team. As suggested, the project hired two local community fishermen to perform daily monitoring of acoustic loggers and inform WCS staff immediately if a logger is missing. Training of the two monitoring fishermen was held in August 2016 with the redeployment of the four remaining recorders at Nosy Komba area in Ankify Bay. It has been decided not to redeploy loggers in Ambaro Bay due to low water visibility and greater risks of loss in that location. All technical measures were taken to ensure successful deployment and retrieval of recorders. In September 2016, WCS staff raised awareness of community members on the existence and objectives of those recorders. The team broadcast a message on local radio and visited villages in Ankify Bay. A targeted awareness raising visit was made to Ambiky, where the logger monitoring fishermen thought it possible that there could be issues with the local community. During this period, the monitoring fishermen reported the loss of one logger in late September 2016 and the case was reported still under investigation. The team retrieved three loggers in December 2016 and redeploy them again to record until April 2017. After their retrieval, they will be moved down to the southern study area. (global Project activity 311) Project ID and name Project Partner Project Component MY 1 Operationalizing the Malaysian National Plan of Action for Dugong in Pulau Sibu and Pulau Tinggi, Johor, Peninsular Malaysia Department of Marine Park Malaysia (DMP), Ministry of Natural Resources and Environment Community-based management MY 2 Establishment of the National Working Committee for conserving dugongs and their habitats through involvement of various stakeholders Department of Fisheries Malaysia (DFM), Ministry of Agriculture and Agro-base Industry Policy MY 3 Community understanding and management of dugong and seagrass resources in Johor Center for Marine and Coastal Studies, Universiti Sains Malaysia (USM) Awareness MY 4 A two-pronged approach for overcoming knowledge barriers on the ecology and status of dugongs in Johor, Malaysia – towards critical habitat protection The MareCet Research Organization MareCet Knowledge MY 5 Overcoming the knowledge gaps and involvement of local community to establish a marine protected area (MPA) for the conservation of dugong and seagrass in Bay of Brunei, Lawas, Sarawak, East Malaysia Protected Area & Biodiversity Conservation Division (PABC) Sarawak Forestry Corporation Community-based management MALAYSIA There are five projects in Malaysia, managed by five Partners. The elaboration of all five proposals were finalised by December 2015. Funding Agreements for all projects were signed and was provided to all Partners for their work. The total amount of cash released the projects in Malaysia as of the end of this reporting period comprised 40% of the GEF funds available for Malaysia. The total co-funding generated by all Partners in Malaysia In October 2017, the Project Coordination Team visited Malaysia to carry out the second meeting of the Executive Project Steering Committee. The opportunity was used to promote the work of the Malaysian Partners and meet with them to discuss their progress, challenges and the upcoming mid-term review. Following the EPSC meeting, in November 2016, the Project Coordination Team, all Malaysian Partners and representatives of the CMS Dugong MoU Secretariat (including a DTG member and the Coordinator of the Programme) visited the Malaysian Project sites in Johor Marine Park. Three out of five Project Partners in Malaysia operate in this site, covering the islands of Sibu and Tinggi. The trip was organised by the National Facilitator in Malaysia with support from all Partners. The field visit was a very good opportunity to get an insight into Project activities in Malaysia as well as the challenges that implementing Partners experience on the ground. Project Partners, including the MY5 Partner, working in Lawas, demonstrated their work. This helped experience exchange and team building among the Partners. As a result of the meeting and the field trip, several issues were identified, such as the need for better coordination among the Partners and better dialogue between institutions working in Johor to enable further the work on dugong and seagrass conservation in the area. A particular issue in Johor is the overlap of jurisdiction and interest between federal and state government over the same project area. Both government agencies have similar objectives, which will require some of the current project work to be modified, mostly affecting projects MY1 and MY4. (global Project activity 431) Project MY1 aims to operationalise the National Dugong Plan of Action (NPOA) at Pulau Sibu and Tinggi, Johor. The project is implemented by DMPM in partnership with Reef Check Malaysia. (14,440 ha). Key deliverables of the project include the establishment of a Dugong Sanctuary and elaboration of a management plan for it. Project MY1 started almost a year behind schedule (in August 2016) due to the legal issue on the contract facing one of the implementing partner, Department of Marine Park Malaysia, which is a government agency. However, the issue was resolved in the previous reporting period by appointing third party NGO partner, Reef Check Malaysia and the project received a jump start with having a full time staff based on the project site (Pulau Sibu). Stocktaking process was immediately kicked off and some baseline data were collected and preliminary understanding of the community’s attitude. (global Project activity 131) MY1 reported on an issue of redundancy between federal and state government as both agencies have similar interest, objective and activities on the same project area which is in preparing the Management Plan of the Dugong Sanctuary. Meetings between both agencies were organised to resolve this issue but more information on the result from these meetings will be presented in the next reporting period. (global Project activity 115) Meanwhile the Department of Marine Park took initiative to fund a research study conducted by University Malaya to compile information from previous research study on the local communities demographic and marine resources surrounding Pulau Sibu and Pulau Tinggi, Johor. The results were partially contributing to a baseline information of project MY1. (global Project activity 131) Despite the slow start, the project is believed to be able to catch up with the proposed timeline. However, pending to the meeting outcome between federal and state government discussion, it may be necessary to amend the proposed activities for this project to fit into the big picture Project MY2 is the National Facilitating Committee-type of project in Malaysia. The project aims to review and improve the implementation on National Plan of Action for Conservation and Management of Dugong (NPOA of Dugong). Similarly to project MY1 and for the same legal reasons, project MY2 started almost a year late. The Department of Fisheries Malaysia (DFM), a government agency, appointed an NGO partner, the Marine Research Foundation, to facilitate the signing of the Funding Agreement. The Funding Agreement was signed in this period and first cash was immediately released to the Partner. As reported previously, despite that the Funding Agreement had not been signed, DFM set up the National Facilitating Committee in the first half of the year and organised an Expert group meeting to discuss the action plan for the execution of the Dugong Sanctuary in Johor As written in section 2.1.1 of the progress report, the second Executive Project Steering Committee meeting this year took place in Kuala Lumpur, Malaysia. The team of project MY2 and the National Facilitator were fully involved in the preparation for the event. Several meetings around the EPSC meeting were planned and successfully organised by the MY2 team, including: A coordinating meeting of the Malaysian Partners with the Project Coordination Team, carried out before the second EPSC meeting; (global Project activity 431) The second EPSC meeting, which was chaired by the National Facilitator of Malaysia A media event during the second EPSC meeting, which was led by the Director General of the DFM and attended by the UN Environment Project Task Manager, the Programme Coordinator of the CMS Dugong MoU and the Project Coordinator. (global Project activity 422) During the media event all Malaysia Partners were able to demonstrate their work and talk to media representatives – they presented their communications and marketing materials, and posters. A field trip to Johor, attended by all Malaysian Partners. DFP carried successfully two more coordinating meetings with the Malaysian Partners in the reporting period. MY3’s objective is to assist local communities in understanding the ecological and economic importance of conserving dugongs and seagrass resources and improve local capacity to manage these resources more effectively bearing in mind social, cultural and economic needs. Universisty Sains Malaysia (USM) implements the project, covering Pulau Tinggi Marine Park (76,565 ha), located in Southeast Johor. Project MY3 will deliver awareness raising among local communities and community-based management solutions for seagrass and dugong conservation, including tourism guidelines on the protection of dugongs and seagrass. In this reporting period, USM undertook several trips to Johor to carry out their education programme with the local communities and obtain information from tourism developers in the area on their interest in conservation management activities in the area. The English language education programme, which was previously initiated, continued in the second half of 2016, targeting the local people of Kg. Tanjung Balang. The programme was run for four days over two-hour slot. USM reported that between 8 and 10 people came every day, among each school children, mothers, boatmen and a few fishermen. The program was an interpretation of the dugong storybook while learning English. As flashcards and role-playing were used to interpret the storybook, participants were also asked to read passages in a book telling a story of a dugong and interpret their meaning. USM also included house visits to fishermen families to compensate for the low level of interest/ coverage of fishermen. (global Project activity 121) To assess the interest and readiness of local community members and resort managers to get involved in conservation management activities as developed by project MY3, USM visited Pulau Sibu and Pulau Tinggi. Seven villages and resorts were reach out and three stakeholders demonstrated their interest in dugong and seagrass conservation - Rimba resort, Sea Gypsy resort and Coconut Village resort. (global Project activity 122) The draft Guidelines for Good Practices for dugongs and seagrasses in Tinggi and Sibu Island, Johor, developed in the previous reporting period were updated to integrate the comments and feedback by the CMS DTG. USM shared the document with the remaining Project partners in Malaysia, some of which also commented on the document. The draft guidelines will be presented to the Fisheries Department in January 2017. (global Project activity 322) So far, the team of project MY3 developed thematic awareness raising materials, such as T-shirts, posters and A4 size stickers. The materials were distributed among local community members and hotel managers during field visits of MY3 team to their project site. MY3 developed a project video showing moments of their interactions with the communities To support communications activities, MY3 team launched a project Facebook page named “Community Management of Dugong and Seagrass in Malaysia”. (global Project activity 121) In November 2016, a part-time project officer, a PhD student at University Sains Malaysia, conducting research on community involvement in alternative livelihoods such as tourism, was hired to assist with project activities and administration. MY4 aims to overcome knowledge barriers that hinder the understanding of dugong and seagrass conservation needs in Johor, Malaysia, so as to enable the comprehensive development of tangible and effective conservation and management plans, including the extension of current MPA boundaries to include seagrass meadows being critical habitat for the dugong. MareCet leads MY4, working in Pulau Tinggi Marine Park. The key deliverables of MY4 are data on dugong and seagrass distribution and their status in the project site. In this period, MareCet finalised data collection activities and participated actively in the launch of the Dugong Sanctuary in Johor. Survey work included aerial surveys and two seagrass mapping surveys on seagrass diversity and abundancy around the Sibu Archipelago, and occurrences of dugong feeding trails. The data of these are compiled and will be processed in 2017. 271 interviews with local communities (152 of which were with fishers) were conducted to collect information on community members’ perceptions and opinions of dugong and seagrass conservation plans for the Johor east coast islands and adjacent waters. More interviews with fishermen are scheduled for March 2017, after which all the data will be analysed. (global Project activities 131) A Dugong Sanctuary was launched by the Johor State Authorities in August 2016. Although the establishment of the Dugong Sanctuary was planned to be carried out under projects MY1 and MY4 and that MareCet supported the local government, it was not a result of project MY4. MareCet reported that the Sanctuary was a result of the interest in and support of Johor State Authorities for conservation as well as the efforts of MY4 to establish it dating from before the Dugong and Seagrass Conservation Project. The official launch of the Dugong Sanctuary took place during the annual island expedition of the Sultan of Johor. During this Expedition, MareCet were invited to present their work on dugong conservation, including the work on project MY4. (global Project activity 111) The work on the Dugong Sanctuary under project MY4 included providing support for development of the management framework of the Dugong Sanctuary, including a delineation of a dugong and seagrass conservation area and drafting of a management plan for said area. The team of MY4 started carrying out consultative sessions with local communities. (global Project activity 133) MY5 aims to establish a Marine Protected Area (MPA) for the conservation of dugong and seagrass in bay of Brunei, Lawas, Sarawak East Malaysia. This project is implemented by the biodiversity research team of the Sarawak Forestry Corporation (SFC). The main deliverables of MY5 include awareness raising and capacity building to enhance dugongs’ conservation, data collection and gazettement of the marine protected area. Currently the area is not under any protection regime. In the previous reporting period, MY5 team focused their work on raising awareness of local stakeholders under their Nature ‘n U programme (93 secondary school students from Lawas). Following the first drone survey in May 2016, more drone surveys were successfully conducted in June, July and August. Eight dugong sighting were recorded in this period. (global Project activity 131) MOZAMBIQUE There are six projects managed by four Partners in Mozambique. All projects in Mozambique work in different sites of the Bazaruto Archipelago National Park (143,000 ha). The total amount of cash provided for the implementation of the projects in Mozambique as of the end of December 2016 was 24% of the available total GEF funding for the country. Project ID and name Project Partner Project Component MZ 1 Development of community-based activities to improved local engagement in marine management in the Bazaruto archipelago Blue Ventures Incentives MZ 2 The distribution of dugongs in the coastal waters of Mozambique Dugongos.org Knowledge MZ 3 Developing an education and awareness campaign to conserve dugongs in the Bazaruto Archipelago and Mozambique Dugongos.org Awareness MZ 4 The Bazaruto Dugong Emergency Protection Project Endangered Wildlife Trust (EWT) Incentives MZ 5 Participatory Research of Additional Methods to reduce the Impact of the beach seine fisheries on seagrass beds at Vilanculos and Inhassoro National Environmental Directorate (NED), Ministry of Land, Environment and Rural Development Knowledge MZ 6 National Steering Committee for the GEF Dugong and Seagrass Conservation Project Policy Project MZ1 aims to develop community-based activities to improve local engagement in marine management. The project lead, Blue Ventures (BV) works in close collaboration with the lead of MZ4, EWT, sharing experience and lessons learned from the establishment of community-based conservation programmes in Madagascar, and providing expert support. MZ1 supports the incentives work in Mozambique addressing the issues of unmet family planning needs leading to population growth and the lack of local economically viable alternatives to fishing, both leading to pressure on the marine ecosystems and dependent biodiversity, including dugongs. During this reporting period, BV and EWT continued to deepen understanding of their Mozambique programmes, communities and situations through the needs assessments completed for health, regular meetings and conversations to share information, and visits from Blue Ventures’ Health-Environment Partnerships (PHE) Manager and Medical Director to Bazaruto island. (global Project activities 211 & 213) The community health needs assessment was completed. Surveys and focus groups were used to assess: community strengths and problem-solving histories; health-related knowledge, attitudes and practices; existing access to health information and services; major health problems; typical preventative and care-seeking behaviour; unmet family planning needs; desired access to health information and services; women’s roles in the community. This community needs assessment indicated that there are high levels of unmet family planning needs on Bazaruto island due to lack of access to information, lack of access to contraceptives, and lack of partner support / approval. (global Project activity 211) An environmental impact assessment was also conducted to explore the possibility of seaweed aquaculture. It was found that seaweed aquaculture is not feasible in Bazaruto due to potential negative impacts on seagrass habitats. Therefore, oyster aquaculture was being investigated but this has been put on hold whilst EWT reviews their strategy. As of November 2016, the Population-Health-Environment (PHE) programme in Bazaruto is put on hold because of staff problems on the side of EWT (see below the report on project MZ4) Project MZ2 is designed to determine the presence and/or absence of dugongs and their relative numbers in areas outside Bazaruto Archipelago. This project is implemented by Dugongos and key deliverables of MZ2 include data on dugong presence, distribution and status, and good practices guidelines. Project MZ2 started relatively late, in this reporting period but quickly advanced by setting up the implementation team and preparing for fieldwork. The team of project MZ2 acquired necessary permits and equipment for their survey work, including a Canon G16 camera with an underwater housing, sampling equipment (e.g. quadrats, containers, etc.), six acoustic loggers and eighteen batteries. Dugongos carried out several coordination meetings with local communities and other environmental NGOs to make them aware of the upcoming activities under project MZ2 and ensure collaboration. (global Project activity 112) The team of project MZ2 compiled existing information on seagrasses of Central Mozambique coast and satellite imagery in preparation for fieldwork (seagrass sampling and mapping validation). (global Project activity 131) A baseline with past and current information on dugongs’ distribution and abundance in Mozambique coast is being collated. Further, reports, conservation plans and legal framework were compiled to serve as basis for analysis and development of a good practices guideline for dugongs and seagrasses conservation in Mozambique. (global Project activity 131) Using the CMS Dugong Questionnaire, 160 questionnaire surveys were carried out in South of the Bazaruto archipelago (Massinga district) and North of the Bazaruto Archipelago (Govuro, Machanga, Buzi, Beira and Dondo). The results of these will be presented in the next reporting period. (global Project activity 131) For analysing the status of the dugongs across Mozambique waters, a research is being conducted by a Mozambican PhD student at Nelson Mandela Metropolitan University in Port Elizabeth, who is a team member of project MZ2. Under her research, the PhD student will assess dugongs’ abundance and distribution, study the genetic population structure and variability, and analyse impacts to the species and its habitats in Mozambique coast. (global Project activity 131) Project MZ3 is also managed by Dugongos.org and aims to mitigate anthropogenic impacts on dugongs turtles and seagrass, through public awareness, education and social marketing A progress report was expected but not submitted by Dugongos for the previous and current reporting period. EWT’s project MZ4, aims to effectively contribute towards the improvement of the conservation status of Dugongs in and around the Bazaruto Archipelago by mitigating human-induced threats and applying a long-term approach to responsible fisheries. EWT works with the communities of Inhambane Province, districts of Vilankulo and Inhassoro. The key deliverables of project MZ4 include the development and application of several livelihoods alternatives for local communities to encourage them manage the marine resources sustainably and to protect dugongs and seagrass. This project has made a very good progress. However, there are several challenges to the project, which impact its overall implementation and require from EWT to put the project on hold for a few months until the challenges are addressed. More details on progress and challenges are provided below. Since the last report, MZ4 team carried out a number of community focus groups in order to understand better the relationships/interactions of community members with their natural resources, specifically with the marine environment. What stood out, over and above the numerous challenges that communities face due to lack of access to basic services, was that the ocean was the most important commodity available to the communities. Community members expressed their attitude and perception for the ocean, demonstrating emotional and practical links (showing their respect for the ocean, and the need that they have for the ocean to feed them). (global Project activities 112 & 131) While project MZ4 and/ or a conservation organisation cannot address the lack of basic needs that the community members on Bazaruto Island lack, EWT’s efforts were towards improving the management of the marine resources on which the communities so heavily rely. EWT began working with the fishers to understand further the current fisheries management system. At the moment, the fishers agree amongst themselves on a few months a year when the seine netting fishery is closed. However, this closure is not based on any robust data and there are often arguments between fishers as to when the optimum closure should occur. EWT reported that local fishers were enthusiastic to get involved in monitoring their catch and to improve their practices and gear, preventing depletion of the resources, as well as access to markets. (global Project activity 131) MZ4 team collaborated with the fishers who expressed interest to improve the status of their fishery and co-developed and piloted a smart phone application with which the fishers could begin to record their fishery data and discuss the patterns that emerged. The application allows for identifying the most commonly caught fish and monitoring changes; it displays the information in a visual way suitable to facilitate a discussion on sustainable and non-sustainable fish catch. During the development of this application, the EWT Project Coordinator, accompanied by the president of the Bazaruto Fishers Association, attended a workshop in Cape Town, with fishers and NGOs from a number of countries where small-scale fishing is important (including representatives from Madagascar, Tanzania, Trinidad and Tobago and Seychelles). This was extremely beneficial for the fishers as it provided network opportunities and a platform for discussions on fisheries management at the small-scale level and the tools available for this. (global Project activity 123) EWT reported that the piloting of the application already had a very positive outcome and can be used as a management incentive in much the same way that alternative livelihoods are used as incentives for change While project MZ4 has demonstrated some success, it has also experienced a number of challenges in its implementation. These range from logistics and accommodation difficulties and lack of staff capacity to challenges in communication and misguided expectations with the fishers at times as well as the park management. EWT Project Coordinator resigned in the end of the reporting period and thus a significant challenge in the project implementation is faced. From next year, African Parks will be taking over the management of the Bazaruto Archipelago National Park. In the light of this change in management and the resignation of the EWT Project Coordinator, EWT decided to put the project on hold for a few months in order to assess needs and discuss how EWT can most effectively play a role within the new management system. The information gathered over this past year will be used by all stakeholders to inform decisions made into 2017. The goal of MZ5 is to identify management measures to stop degrading fishing practices and over-exploitation of marine resources. MZ5 is implemented by the National Directorate of the Environment (NED), Ministry of Land, Environment and Rural Development (MLERD). The main deliverables of project MZ5 include the development of a management plan together with 18 fishing communities in Vilanculos to prevent the degradation of seagrass beds and loss of biodiversity, including dugongs. During the reporting period, a joint technical team of experts of the NED (Division of Coastal Management), Provincial Directorate of Land, Environment and Rural Development of Inhambane (Department of Environmental Management), District Services of Infrastructure and Planning (Inhassoro and Vilankulo), Provincial Directorate of Sea, inland waters and fisheries (Vilankulo and Inhassoro delegations), University of Eduardo Mondlane (Department of Biological Sciences-DCB)/Museum of Natural History-MHN), had a field trip to the districts of Vilankulo and Inhassoro. The field trip aimed to gather data and contribute to creating and strengthening the foundations of governance structures for the community-based conservation and monitoring of dugongs and seagrass ecosystems. A questionnaire was used to gather information about the current state of conservation of seagrass and dugongs, as well as about fishing practices and their impact on the seagrass and dugongs, and tourism. The results of the field work helped obtain information on types of fishing gear and vessels, fishing areas and type of fish, trends in levels of income, periods of fishing closure, value chain of fish, management of fishing activity, knowledge of dugongs and other species, alternatives economic activities and tourism. Interviews and focus groups were conducted in Vilankulo and Inhassoro districts. This work indicated that there are high levels of knowledge about the conservation of dugongs and seagrass. It also indicated that the fishing closure seasons differ between the two districts - 15 January - 15 April in Vilankulo and 01 July - 30 September in Inhassoro. (global Project activities 112 & 131) Alongside the district institutions, the technical team also met different Fisheries Communities Consuls (CCP) and Association and Trading Association in Vilankulo and Inhassoro In parallel to the compilation of data and information on the ground, MZ5 team recorded photographic images and footage of short videos on the mission that will later be the subject of analysis and publication in the medias. MZ6 is the National Facilitation Committee of Mozambique, coordinated by NED. The main purpose of the MZ6 is to build an informed and effective National Facilitating Committee (NFC) to provide country-level oversight of project activities in order to ensure that dugong and seagrass conservation considerations are integrated within relevant national-level environmental policy, planning and regulatory frameworks. Project MZ6 will deliver a legal analysis identifying gaps and recommendations to integrate dugongs and seagrass safeguards in sectoral and marine resources-relevant legislation. During the reporting period, the NED held two meetings with the Project Partners in Mozambique (in August and October 2016). The objectives of the meetings were the official launching of the national projects in Mozambique, familiarisation of the Partners with all projects to ensure the coordination and collaboration between Partners and preparation for the first meeting of the National Facilitation Committee. (global Project activity 431) The first meeting of the National Facilitating Committee took place on 17 October 2016. All Partners and many institutions attended the first meeting including National Directorate of environment, Department of the Environmental Management, Division of Marine and Coastal Environment, National conservation areas Administration, Museum of Natural history, National Fisheries Research Institute, National Board of fisheries, National Institute of Fisheries and Aquaculture Development, Ministry of Transport and Communication, National Institute of the Marine and World Wildlife Fund-Mozambique. (global Project activity 432) THE SOLOMON ISLANDS Project ID and name Project Partner Project Component SB 2 National-level awareness raising campaign to champion dugong and seagrass conservation SICCP Awareness SB 3 Mapping critical seagrass fisheries habitats in Lau Lagoon, Solomon Islands WorldFish Knowledge SB 4 Towards better management and protection of dugongs and seagrass habitats in Solomon Islands SICCP Incentives SB 5 Strengthening provincial and national capacity for project implementation in the Solomon Islands (combined with SB1) WorldFish Policy There are four projects in the Solomon Islands, implemented by two Partners. All projects are operational. By the end of this reporting period, 18% of the GEF funds available for the Solomon Islands under the Dugong and Seagrass Conservation Project were disbursed. SB2 aims to deliver a national-level awareness raising campaign to champion dugong and seagrass conservation. Project SB2 is implemented by SICCP and is expected to mainly deliver awareness raising on the importance of dugongs and seagrass on a national and local level (in selected sites reaching out at least 10 local communities) and to mobilise support for the conservation efforts of all Project Partners in the Solomon Islands toward the protection of the dugong and its habitat. In this period, SICCP has a trip to Roviana, where they met with Roviana Conservation Foundation and participated in the Roviana Lagoon Festival, held in Munda, Western Province, for 3 days. The theme of the festival was “People, Culture, and Environment”. To help raise profile for the project, SICCP sponsored prizes for two water-based activities a) underwater breath-holding competition and b) the underwater swim (swim as far as you can on a lungful of air). Both activities had female and male prizes for Junior and Adult categories. SICCP also gave a public talk during an evening session, providing general information on seagrass and dugongs. SICCP and Roviana Conservation Foundation had a stall and distributed thematic communication materials, including the global GEF Dugong and Seagrass Conservation Project factsheet. The information materials covered the importance of dugongs, seagrass and turtles. Information on the benefits of community-based resource management was also made available to the public. The talk also introduced Seagrass-Watch as a useful citizen science tool for monitoring seagrass status and invited the public to participate in Seagrass-Watch monitoring activities that the SICCP office in Munda and Roviana Conservation Foundation will be running in 2017 (global Project activity 121) The objective of project SB3 is to overcome existing knowledge barriers regarding the distribution, status and ecology of seagrass ecosystems in the Lau Lagoon, Malaita Province. WorldFish Solomon Islands implements the project. Project SB3 will deliver participatory maps on seagrass and dependent biodiversity, information on dugong sightings and a compilation of local communities’ stories on dugongs and seagrass. Following the visit to the Lau Lagoon in the previous reporting period, in July-August, WorldFish conducted a participatory mapping of critical seagrass fisheries habitats. Team members consisted of WorldFish staff and a representative from the Ministry of Environment, Climate Change, Disaster Management and Meteorology (MECDM). The aims of the trip were to conduct participatory mapping activities workshops with five communities in the Lau Lagoon on seagrass and their perceptions and valuation of seagrass, to collect indigenous stories from locals on seagrass and dugong folklore, to carry out the CMS dugong survey and to confirm dugong sittings. (global Project activity 132 & 131) During the participatory mapping workshop, information on dugongs and seagrass was solicited through Focus Group Discussion (FGD), Pebble Distribution Method (PDM). In addition the team administered a quantitative questionnaire with men and women. In the FGD people were asked to identify and features of importance on a detailed map of the lagoon. During the workshops the team also gave a presentation on dugong and seagrass ecology and conservation. This generated much interest and questions, on how to protect key marine resources and species and on the role of the government and customary authorities. WorldFish provided the data from the participatory mapping to MECD to be digitalised, after which a first draft of the map will be obtained and shared with communities for their review and feedback before finalisation. In September, WorldFish attended a stakeholders meeting convened by the Ministry of Fisheries and Marine Resources (MFMR) to discuss the development of the inshore fisheries regulations. Following on from the second NFC meeting in July last year, recommendations suggested at that time were relayed to MFMR. (global Project activity 412) In November, staffs from WorldFish were invited by the Secretariat of the Pacific Community (SPC) to give a talk on Community Based Resource Management to more than 200 youths undergoing internship training with the Youth at Work Program of SPC in Honiara. This was seen as an opportunity for an awareness session with the interns and so this incorporated an awareness talk on dugongs and seagrass. (global Project activity 111) Also in November, WorldFish held a three-day community-based resource management training in Auki, Malaita for 32 youth representing from 10 local communities. While this work is not captured directly under the SB3 project, staff took the opportunity to share information on dugongs and seagrass. (global Project activity 111) Project SB4 is the community-based management and incentive project in the Solomon Islands. The objective of SB4 is to improve the management and protection of dugong populations and seagrass ecosystems throughout Solomon Islands. SICCP leads the project in collaboration with other conservation and community organisations. SB4 works in, Vavanga LMMA (1,641 ha), located on Kolombangara Island, Marovo Lagoon and Tetepare Marine Protected Area (1,516 ha), located on Tetepare Island. The key deliverables of project SB4 are collection of data on dugongs and seagrass that would feed good management practices and integrated community-based management plans in at least three sites. In this reporting period, SICCP involved actively local community members is data collection. A four-day survey of the seagrass habitats around Tetepare Island was conducted in August by a team of six local women. This was the first time that seagrass surveys was conducted around Tetepare Island in 2016. The survey also contributed to a long-term monitoring program that SICCP has been helping Tetepare Descendants Association to implement for the past 3 years. A total of 16 sites within both the marine protected area and open access areas were surveyed using a modified Seagrass-Watch protocol. Giant clam surveys were also conducted within the marine protected area by the same team of women. In December, a similar survey was carried out by sane team of women. This time they were aided by Dr. Katy Soapi of the University of the South Pacific (USP), a Solomon Islander with cultural ties to Tetepare Island. During her visit to Munda, Dr Soapi had discussions with SICCP’s Marine Scientist on the feasibility of introducing a Master of Science program that will be based on the seagrass monitoring work at Tetepare. If successful this program will commence in the second half of 2017 and run for 12 months. The program will only be open to Solomon Islanders. (global Project activity 132) In September, the SICCP’s Project Coordinator visited Chubikopi and Akara-Takuti sites in the Marovo Lagoon. The assessment of these two sites identified them as a priority seagrass area for SB4. During the trip, three local sites were confirmed for seagrass monitoring at Chubikopi. The SICCP team visited Chubikopi again in October to follow up on the training workshop, held in Honiara (see below for reference). (global Project activity 113) A workshop was held in Honiara in September as an introductory for the participants from the community in the Marovo Lagoon. This workshop introduced the project to the SICCP’s local partners in Marovo and Tetepare and was used to conduct a training on survey and monitoring to enable and prepare individuals for the series of seagrass monitoring and surveying. (global Project activities 112 & 123) As a follow-up to the April surveys, a second round of resource surveys was conducted within the Locally Managed Area (LMA) at West Parara. These included seagrass, shellfish and coral reef surveys at surveys sites within the proposed LMA of West Parara. Formal endorsement of the LMA by the broader community and tribe is expected to occur within the second half of 2017. However, resident community members have already demarcated a coastal stretch of water that is closed to certain harvest activities such as gill-netting and spear-fishing. This area includes mangrove and seagrass habitats and is a well-known feeding ground for dugongs and turtles. It is also a popular location for harvesting shellfish species. The first formal LMA committee meeting will take place in March 2017. (global Project activity 131 & 114) A follow up visit to Ropa and West Parara was carried out in November to map the seagrass beds. The extent of available seagrass habitat was mapped at the LMA sites at both Ropa and West Parara by SICCP, KIBCA and local community representatives. The process was carried out using a hand-held GPS and involved walking and paddling a canoe along the edges of the seagrass area. The information is stored on a computer and will be used to monitor any changes in seagrass cover (i.e. shape and size of meadows) over time. (global Project activity 132) Project SB5 is the National Facilitating Committee of the Solomon Project. WorldFish, leading SB5, is the lead on the NFC in the Solomon Islands. SB5 is expected to deliver a national coordination on the dugong and seagrass conservation and a National Dugong and Seagrass Conservation Strategy Four key activities were carried out by the National Facilitating Committee in the reporting period, including two meetings of the NFC. (global Project activity 431) The SB5 team called an Extraordinary meeting of the NFC for the development of the National Dugong and Seagrass Strategy. WorldFish convened this meeting to provide and get feedback from the NFC on an outline of the Strategy. (global Project activity 413) In October, a three day workshop was held in Auki, Malaita Province. The workshop was an inception workshop for two WorldFish projects that are being implemented in Malaita Province, funded by the Asian Development Bank (ADB) and SwedBio. During this workshop, WorldFish highlighted their work on the GEF Dugong and Seagrass Project in Lau Lagoon. These projects focus on community-based resource management, which includes threatened species. The information provided by WorldFish on their dugong conservation work, under projects SB3 and SB5, attracted the attention of the participants and spread the dugong conservation message to a new area outside Lau Lagoon - Langalanga Lagoon near Auki. (global Project activity 121) Project ID and name Project Partner Project Component LK 1 A Community Based Approach for Conserving the Globally Threatened Dugong dugon in Sri Lanka BEAR Awareness LK 2 Improving communication and collaboration amongst all relevant stakeholders in Sri Lanka to enhance seagrass and dugong conservation DWC Community-based management LK 4 Development of a multiple-community-based marine resource management plan in the Gulf of Mannar IUCN Sri Lanka Community-based management LK 5 Ensuring seagrass ecosystem values are incorporated into coastal area planning in Sri Lanka NARA Knowledge LK 6 Increasing knowledge on sea grass habitats and dugong distribution at selected sites in North Western Sri Lanka ORCA Knowledge LK 7 Providing incentives to local communities in return for wise stewardship of coastal habitats SLTCP Incentives LK 8 National Steering Committee for the GEF Dugong and Seagrass Conservation Project IUCN & DWC Policy SRI LANKA There are seven projects in Sri Lanka, managed by six Partners. Funding agreements were signed and ongoing funding was provided for all the projects. The total amount disbursed to projects in Sri Lanka by the end of December 2016 was 46% of the available GEF funds for the country under the Dugong and Seagrass Conservation Project. All projects in Sri Lanka work in two main sites – Kalpitiya and the Gulf of Mannar and Palk Bay, including several protected areas, such as Bar reef Sanctuary, Northwestern coast (30,670 ha), Ankalai Sanctuary, Northern Coast (4,839 ha), Adamsbridge National Park, Northern coast (18,990 ha), Delf Island National Park, Northern coast (1,846 ha), Parithive Sanctuary, Northern coast (97 ha). Project LK1 will conserve the dugong and their seagrass habitats through education and awareness raising in the Gulf of Mannar and Palk Bay. The project is led by BEAR and will deliver high awareness & social marketing programs effected in the community groups (with over 5000 school children and over 10 fisher and other social communities), collation of local information on dugongs and seagrass beds, and enhanced understanding and formulation of guidelines for best fishery/interaction practices. In 2016, LK1 team carried out pre awareness surveys in 12 sites located between Silavathurai (Northwest) to Poonaryn in Jaffna (North), including fishing villages, military bases and other government bodies affiliated. As a result from the pre-awareness survey, LK1 team got anecdotal information that at least one dugong is landed each month in certain fishing villages around the north and north-western parts of the country. LK1 observed that some of the fishers use illegal fishing gear (certain types of nets). The rate and magnitude of the bycatch is alarming, so is the rate of the destruction of the seagrass beds. (global Project activity 111) The Partner implementing LK1, BEAR, commissioned the development of a film about dugongs, seagrass and communities. Underwater footage was also made. As per the discussions of the Project Coordination Team with BEAR, the footage was finalised and the team worked on translation of the movie in Tamil. LK1 team also reported that they developed awareness material for school children and the fisher communities. Following legal requirements, the team sent a letter for the approval from the Ministry of Education to conduct the awareness programme in schools in the northwester and northern part of Sri Lanka in 2017. (global Project activity 121) LK1 team reported that during the last six months of 2016, four dugong deaths were reported, necropsy were carried out and the cause of death was due to blast fishing, which was evident by the extensive internal bleeding. (global Project activity 131) Project LK2, managed by DWC, targets to strengthened legal and administrative capability for wildlife resource management and conservation in Sri Lanka with participation from a wide range of stakeholders including local communities. LK2 will establish and equip a marine conservation centre in Jaffna District and develop a national communications network for dugongs and seagrass. As it was reported in the previous period, a Marine Conservation Unit to handle all dugong and seagrass conservation activities was formally established within the DWC and the required manpower was hired. A Marine Sector Conservation Plan was developed but not shared with PCT yet. (global Project activity 114) A mobile base application for the communication network was developed and the equipment’s for the network was purchased. Institutions which are the part of the communication network had been identified and their capacity for the application was built. (global Project activity 331) In the second half of 2016, DWC carried out four visits to project sites, one in each of Puttalam, Jaffna, Killinochchi and Mannar districts. These visits aimed to assess and raise the level of awareness of local communities of dugong and seagrass importance. The awareness raising activities were convened and organised by the Marine Conservation Unit. The visits were also important to acquire substantial data on past dugong fisheries, dugong sighting and seasonality/ frequency of sightings around the offshore islets, and the current trend of dugong hunting. (e.g. in some islets at least one dugong is killed each month.) (global Project activities 112 & 131) Marine mammal’s observation guidelines were reviewed but not yet approved by the Cabinet of the Parliament. DWC scheduled a workshop to validate the guidelines in the first quarter of the year 2017. An update on this will follow in the next reporting period. (global Project activity 322) Project LK4 is managed by IUCN Sri Lanka for the preparation of a multiple community-based management plan for the conservation of dugongs and seagrass meadows. The project works in 4 districts in Kalpitiya - Puttalam, Mannar, Kilinochchi and Jaffna – where several protected areas are located.LK4 will declare 10,000 ha of a dugong and seagrass MPA. In this period, IUCN team focused their efforts on working with communities for dugong and seagrass conservation. Forming Community Conservation Groups was the main focus in the activities conducted during the last 6 months from July to December 2016. The focus was on three communities covering strategically important locations in Kandakuliya on the Kalpitiya Peninsula, Arippu located on the mainland along the Gulf of Mannar coast and Vidataltivu in the Palk Bay. Two of the groups, Kandakuliya and Vidataltivu, were selected due to their cohesiveness within their respective communities and because they had already formed their tourism associations. The group members in the Arippu group are engaged in fishing only and had no previous association for any community oriented activities. The total number of individuals in the three groups is 48. (global Project activity 114) Most of the members in all three groups are engaged in fishing or related activities as their main source of income. The group in Kandakuliya are divers for sea cucumber and conch shells but have begun tourism related activities within the last decade due to overexploitation of sea cucumber and chanks. Presently they are engaged in whale and dolphin watching and taking visitors to the coral reefs of the Bar Reef Marine Sanctuary. They still collect sea cucumber and chanks occasionally. The group in Vidataltivu has also begun tourism related activities and have been involved in taking tourists to the coral reefs at Maldiva Bank in the Palk Bay and bird watching in the wetlands of Vankalai Sanctuary. Several meetings were held at the three locations to inform the communities about the Dugong and Seagrass Conservation Project and discuss community-based conservation aspects of marine ecosystems and species. Current issues and constraints were also discussed, especially the problem of widespread blast fishing and the use of bottom trawling in the Palk Bay by fishermen from Tamil Nadu and also some fishers from Mannar. (global Project activity 112) The next steps for this Community Conservation Groups was to register them formally with the Department of Wildlife Conservation. The aim of the registration is to give recognition of communities to engage in conservation activities, including experience sharing with other neighbouring communities. This is believed to contribute to expanding the knowledge base on sustainable resource use and the protection of dugongs and seagrass ecosystem. (global Project activity 114) Fishermen in Mannar and Puttalam Districts are mainly Christians and therefore their activities are strictly governed by the catholic priests. The catholic priests are closely linked to the governance aspects at the community levels in both districts. In August 2016, IUCN met catholic priest of seven villages (Silavathurai, Arippu, Vankalai, Talaimannar, Mannar, Vidataltivu and Pesalai) On the request of the Vicar General of the Mannar diocese, an awareness programme was conducted to all the parish priests in the Mannar District at the Bishop’s House on 17th October 2016. (global Project activities 114 & 111) NARA’s project LK5 aim to improve decision-making and coastal area planning in Sri Lanka through improved knowledge on the distribution and abundance of seagrass habitats in Palk Bay, Gulf of Mannar and Kalpitiya. The project work is implemented in the Districts of Puttalam, Mannar and Jaffna. Key deliverables of LK5 include the development of a database on seagrass distribution and status, identification of hotspots and threats to dugongs and seagrass. In this period, NARA carried ground truthing studies to update and validate the seagrass distribution maps of LK study areas in Mannar, Palk Bay and Palk straight. For the purpose, NARA acquired satellite images for the areas with clear (non-turbid) and shallow water and used GIS and field surveys for mapping deep and turbid areas. (global Project activity 311) LK5 team identified the area of Veditativu as an important seagrass area, where dugongs’ preferred species were found (Halophila, Halodule and Cymodocea) and will continue research activities there. (global Project activity 113) Seagrass ecological studies in Veditativu (80km2) and Mannar South Bar (110km2) were conducted in the reporting period. Seagrass samples were collected by using randomly placed 25cmx25cm quadrates for biomass studies and by placing 50cmx50cm quadrate for estimating percentage cover. The location of 8 Km away from the shore Veditativu reef is located and corals found to be dead due to bleaching. Halophila ovalis and Cymodocea rotundata were observed in low dense and patchy distribution around the deeper areas around the coral reefs. Caulerpa taxifolia was observed distributed around the reef area over the seagrasses which is recorded as invasive in some reports. The other area studied was the South Bar Mannar in which some dugong deaths were recorded in 2016 end. NARA studied the seagrass beds there using random quadrate method to collect seagrass samples, as there was no continuous seagrass patches observed, as reported by the Partner. LK5 team reported that detrimental fishing, using dynamite was normally practiced by local fishermen and according to them the area should be marked as a sensitive area to be protected. During the fieldwork, NARA identified seaweeds/ macro algae species, such as Caulerpa racemose, Caulerpa sertularioides/ Caulerpha taxifolia, Halimida spp, distributed around the coral reef. From the seagrass species, NARA observed densely grown area of Cymodacea serrulata with 100% coverage and parches (from 2’x4’ to 40’x50’) of Halophila ovalis and Syringodium isoetifolium. Slimy filamentous green algae was dominant in the area close to the shore (more than 60 km2; belt of no 10 in the map). This area beyond 3 Km away from the shore limited to conduct “Madel” fishery which has no seagrasses found in the bottom. (global Project activity 311) It has been recorded that, there is a major decrease in all marine species and a decline in fish biomass in areas where C. taxifolia has become a serious problem. In LK5 team studies, they have observed similar phenomena, but need further studies to confirm the preliminary observations. LK5 team also collated information on impact of fishing gears on seagrass destruction and seagrass associated fisheries. During the baseline survey two main sites were observed with high number of bottom and submerged gill net operations in the Mannar district namely, Vankalei and Urumalei. Fishermen in these two sites mainly target crabs (Blue swimming crab (Portunuspelagicus)) and other benthic and demersal fish species (such as rays, guitar fish, Mullet, Asian Seabass Snappers). Also, fishermen operate seasonal gears, which target specific fish species groups abundant within the area Three main types of fishing gears are used by fishermen in the two districts, which are operated on seagrass beds - gillnets, trammel nets, fyke nets and squid jig. The gillnets were further grouped in three types based on their material. (global Project activity 311) NARA assessed the impact of fishing gear on seagrass by observing the entangled amount of seagrasses with each gears, while clearing gears (nets) and categorized to five criteria’s as very high, high, medium, low and none. Multi-monofilament and monofilament gillnets were identified as the most detrimental. NARA also reported that blast fishing is a common practice in their survey area. (global Project activity 311) Other factors considered and measured during the ecological surveys included water quality (salinity, turbidity and Ph). The details on these are presented in NARA’s half-yearly progress report. NARA interviewed forty fishermen within the Mannar area to compile information on dugong sighting. Two fishermen stated that they had not seen dugongs for more than 10 years. Project LK6 is led by ORCA to close the knowledge gaps that presently prevent effective management, conservation and policy initiatives on seagrass and dugong in the Bay of Bengal/ Palk Bay area. Project LK6 will deliver In this reporting period, ORCA focused on community-based monitoring of the coastal fishing areas and collection of data on captures, beaching and observation of dugongs. 42 days of field surveys were carried out in 31 coastal locations, conducting over 95 personal interviews with community members. Information of dugong records were provided by 35 individuals. (global Project activity 311) The new data collected included about 13 additional capture and sighting records from fishermen during 2016, including two records of dead dugongs getting washed ashore on the southern coast of the Mannar Island. The autopsies on both (carried out by the Department of Wildlife Conservation) indicated that they were probably killed by dynamite fishing. Illegal blast fishing activities are prevalent in the area and specially practiced by fishing camps in South bar and the area. ORCA noted that though blast fishing primarily targets finfish, interviewed fishermen indicated that dugongs were also targeted, when they had been detected, especially when they were with calves - the calf tend to stay at the surface longer and is tracked till a hunt is organized. Three such kills were documented in 2016, close to Arippu reef, near Silavathura reef and near Iranathivu island. (global Project activity 311) ORCA further reported that two records of dugong carcasses being washed ashore in November and December 2016, both on the southern shores of Mannar and less than 10 km apart from each other. One carcass was badly decomposed, while the other was in a fresh state with bleeding seen from nostrils and ears which may indicate damage from a dynamite blast. Blast fishing is rampant in the area of the Vankale reef. Vankale reef area also contain significant areas of small leaved seagrasses as well as a significant number of dugong records over the past years. The area is also subject to very high fishing pressure as well as illegal fishing practices. The deeper channel areas of the Mannar Islands in Adam's bridge around Island 2 and 5 area also contain several sighting records of dugongs. (global Project activity 311) During the reporting period, ORCA acquired new equipment for their work - an additional scanning sonar (Panoptix) with accessories for boat mounts and protective carry bag for the units manufactured locally and a sonar image software to facilitate replay of sonar images for later analysis. The side-scan sonar system that ORCA was using in field surveys proved very useful in identification of bathymetry and general seafloor substrate types, which helped them significantly in identification and mapping seagrass areas. However, the effectiveness of the units traces suffered a setback in making positive identification of possible dugong targets, as when a probable target was detected and the boat was stopped to investigate the sonar, imaging was immediately lost. The new equipment will be tested with the opening up of the diving season in January 2017. Project LK7, managed by SLTCP aims to reduce impacts of destructive fishing practices on seagrass habitats and provide income-generation opportunities to local communities in return for their commitments to wise habitat and natural resource use in Puttlam area. The SLTCP team works with communities from six fishing villages along Puttalam lagoon, Anawasala, Kandakkuliya, Sotthupitiya, Palliwasathurei, Thirikkapallama and Serakkuliya. LK7 main deliverable is the development of incentive and livelihoods models for communities to participate in the conservation of dugongs and their habitats. All incentive programmes introduced by SLTCP continued to develop (global Project activities 213 & 214). As reported in the previous period, the incentives to communities were provided further to assessing needs, raising awareness about marine conservation issues related to seagrass and dependent biodiversity and setting in a participatory manner conservation objectives to reduce the negative impact of fishing practices. All incentives/ alternative livelihoods were introduced to communities upon signing of a Memorandum of Understanding. The Memorandum stipulates that communities should not use illegal fishing gear and practices. SLTCP monitored the development of the alternative livelihoods models through monthly visits. To date, SLTCP used the GEF funds for project LK7 to provide the following support to local communities to encourage support for seagrass protection and dependent biodiversity: Batik materials and thematic designs to one batik group in Kandakuliya; 37 sewing machines were provided to communities in 3 locations in Puttlam lagoon (total of 27 machines in 2015 to Sotthupitiya (7), Serakkuliya (10) and Thirikkapallama (10) and total of 10 new sewing machines to the communities in Thirikkapallama in the first half of 2016); legally accepted, harmless fishing nets in substitute of illegal gear to 10 beneficiaries at Sotthupitiya and 25 beneficiaries in Serakkuliya (in 2016); A seabass aquaculture site initiated at Thirikkapallama (600 fingerlings purchased), benefiting 18 families; 5 seabass facilities in Sotthupitiya A crab culture programme introduced in Palliwasathurei Ornamental fish culture – 2 stock tanks in Sotthupitiya salt packet production - 5000kg of salt, 1 wooden table and 5 sealer machines benefiting 10 fishers’ communities in Anawasala facilities in two primary schools – an audio- visual systems for two pre-schools at Sotthupitiya and Kandakuliya, and a water tank to one rural school in Kandakulia In this period, the batik group in Kandakuliya was provided with designs of dugongs and seagrass to be applied on in their products, in order to encourage conservation and awareness. SLTCP provided a toolkit of dye and batik materials to 9 members to initiate the production. The groups of women, who got the sewing machines, were provided produced 238 cotton bags. SLTCP purchased the fabric and paid the sewing cost. The Partner used the cotton bags in the award ceremony of the ‘Werale Asiriya’ art competition (see below for reference). The sewing group in Serakkuliya to sell their products. Monetary support to construct fish rearing tanks given to two sites – four tanks were purchased in Soththupitiya and and three in Serakkuliya. After completion of construction of tanks, SLTCP provided Platy (ornamental) fish varieties to the tanks at Serakkuliya. Grown fishes were purchased by the organisation. The Platy varieties purchased from the local communities were included in an annual exhibition of ornamental fish aquaria, “Min Visithuru”, held in Colombo in August 2017, winning first and second places for SLTCP. SLTCP were very active on communications and awareness raising. The partner carried 19 awareness lectures and 19 film shows dedicated to dugong and seagrass conservation, targeting mainly fishing communities and schools. (global Project activity 111) SLTCP conducted an annual art competition ‘Werale asiriya’ on marine and coastal environment for school students and an award giving ceremony was held on 3rd September. Over 500 guests participated in the event, attended also by Hon. Minister of Megapolis and Western Development. Best artworks were displayed to the public during a prize giving ceremony. (global Project activity 111) In addition, SLTCP participated in a school educational exhibition organized by and held at Defense school, Colombo in September, 2016, where they presented their work, including on LK7 project. Several educational materials were produced to support the communications efforts of the LK7 team, including leaflets on mangroves, coral reefs and turtles, and fiberglass model of a dugong. (global Project activity 111) LK8 is the National Facilitating Committee of Sri Lanka. The Project is administered by IUCN Sri Lanka on behalf of the Department of Wildlife Conservation (implementing LK 2). The National Facilitator of Sri Lanka continued to be very active and kept a very good contact with PCT and the rest of the Project Partners in Sri Lanka. In this period, the National Facilitating Committee of Sri Lanka met 3 times to discuss project progress and constrains and to identify a strategic approach to achieve project objectives. (global Project activity 432) Following the assessment of training needs of the Partners in Sri Lanka (as reported in the previous period), the National Facilitator organised training sessions for the Partners and reported this activity as completed. (global Project activity 431) TIMOR-LESTE Project ID and name Project Partner Project Component TL1 Identification of priority sites for conservation of dugongs and seagrasses in Timor-Leste CI in coordination with Fisheries Directorate, Ministry of Agriculture, Forestry and Fisheries (MAF) Knowledge TL2 Incentivising community engagement in dugong and seagrass conservation in Timor-Leste through volunteer ecotourism Blue Ventures Incentives TL 3 Mainstreaming dugongs and their seagrass habitats into national coastal zone planning and decision-making CI in-coordination with the MCIE and MAF Policy TL 4 National-level awareness raising campaign to champion dugong and seagrass conservation. National Directorate for Biodiversity Protection and Restoration, Ministry of Commerce, Industry and Environment (MCIE) Awareness TL5 Timor-Leste National Facilitating Committee Policy There are five projects managed by three Partners in Timor-Leste. All are operational. The cumulative disbursement to the projects in Timor-Leste, as of the end of 2016 was 43% of the GEF funds available for the country under the Dugong and Seagrass Conservation Project. As evident from the title of TL1, the project will gather information for the identification of priority sites for conservation of dugongs and seagrasses in Timor-Leste. The project is implemented by Conservation international (CI). Project TL1 will deliver a draft community-based management plan for at least one priority area, integrating dugongs and seagrass and will compile the necessary data. As previously reported, CI worked on identifying three communities to work with on integrating dugong and seagrass conservation and monitoring in their management plans. Two potential sites for dugong and its seagrass habitat conservation were identified in Com (Lautem) and Vila (Atauro Island) and local communities there were approached to discuss the project. TL1 team conducted a training (20 attendees) for the Community Conservation members from Nino Konis Santana National Park on seagrass mapping and monitoring. Both classroom theory and onsite practical trainings were provided. (global Project activities 112 & 132) Community work in this period included also awareness raising and an environmental education campaign on seagrass, turtles and cetaceans in the community and through schools in Dili, Atauro Island, and Oecussi. (global Project activity 111) As reported in the previous report, CI adapted the CMS Dugong MoU bycatch questionnaire, adjusting it to the situation in Timor-Leste and to include questions related to turtles and cetaceans. The questionnaire was translated into the national language of Tetun and provided to a survey team. The survey team comprised Blue Ventures, Ministry of Agriculture and Fisheries and students from UNITAL (a private university in Timor-Leste, which has an environment program). Seven UNITAL students were selected to support the survey work based on their home municipality. Selecting students from the TL1 project sites, who speak the local languages, will facilitate the interviews of community members. Added to Atauro Island and Lautem district, the seven municipalities would give 9 out of 11 potential coastal municipalities to be surveyed. (global Project activity 311) In preparation for seagrass mapping and monitoring work, CI staff translated in Tetun training materials from Seagrass-Watch. 15 people, including Project Partners in Timor-Leste and stakeholders were trained on seagrass mapping and monitoring. The training included theory and practical activities. Mapping of the seagrass beds began with Atauro Island, the east end of the Timor island, and some of the surrounds of Dili. (global Project activity 311) TL1 carried informal Dugong surveys with communities, which indicated the presence of a group of five dugongs on the south side of the island. CI reported that no dugong has ever been seen on the eastern tip of the island, with communities not recognising a picture of a dugong. All communities state that dugongs are protected under the traditional law and are not hunted by Timorese. This informal survey was followed up by the formal Dugong and Seagrass questionnaire being implemented up to end of December 2016. (global Project activity 112) Project TL2 is managed by BV and aims to to develop a replicable model for marine conservation ecotourism to incentivise local engagement in dugong and seagrass conservation in Timor-Leste. The project is the first incentives-based project in Timor-Leste. As previously reported, BV identified Atauro as their base for ecotourism activities in Timor-Leste and Barry’s Place in Beloi as the provider of accommodation and food. Project TL2 demonstrated a good progress in this period and the BV team reported that they would continue to examine multiple places to replicate their model. Behau village on mainland Timor-Leste was identified as a potential satellite/secondary site and work to investigate the local interest in and feasibility of ecotourism opportunities in this community is planned commence in early 2017. Using Barry’s Place as a base for ecotourists during the initial phases of the project, TL2 team made significant progress towards preparing and supporting local families to set-up homestays in the community of Beloi. Following the recruitment of a Community Conservation Coordinator in September 2016, BV identified eight families in the village willing to host ecotourists in their homes for two weeks out of each six week expedition (starting in January 2017). BV reported that all families were currently preparing their homes to receive guests and started establishing a homestay association as a cooperative of the host families. In addition, families received training in hospitality and food preparation from the Ministry of Tourism, Arts and Culture. Representatives from the homestay association will travel to Raja Ampat, Indonesia, in early 2017 to learn from a successful association using a similar model to host dive tourists in the region. (global Project activities 214 & 212) The ecotourism volunteering expeditions continued to attract ecotourists from across the world. In the reporting period, there were four expeditions with a total of 39 volunteers, all but three of whom spent more than 25 nights in country. In total, Blue Ventures ecotourists contributed approximately 1,320 bed nights in the second half of 2016. Ecotourists are asked to voluntarily confirm their spending at the end of their expedition with most respondents spending between USD100 - 200 whilst they are in the local community, typically on items such as souvenirs, guided activities and food and drink. (global Project activity 212) The ecotourism model already contributed funding to maintenance and monitoring of the Adara Locally Managed Marine Area (LMMA) through park fees (to date 51 divers at USD1.50 a dive). This payment system has strengthened local support for the LMMA within Adara and is strengthening broader interest in conservation among other communities on Atauro Island. (global Project activity 223) Progress to identify partner communities for co-management activities has been slow in 2016. This activity has been delayed by community leaders whose support is key to commencing discussions on co-management, and who recently reached the end of their five-year mandate in office; elections originally planned for September took place at the end of October. (global Project activity 113) Despite the challenges, BV team carried out stakeholder meetings, which resulted in identifying two villages, Akrema and Uaro-ana, in the north of Atauro as the first potential sites for the community-based nature resource management activities. Following these meetings, BV and ecotourists started the mapping of nearshore seagrass habitats in three locations on the eastern coast of Atauro (adjacent to Beloi, Akrema and Uaro-ana). The team used Seagrass-Watch methodologies in their seagrass mapping work. (global Project activities 112, 113 & 131) In late September, BV held a stall at Beloi market focused on gathering local knowledge of seagrass resources, local fisher interactions with seagrass resources and to gather expressions of interest for training in ecological monitoring methodologies, in order to become community based monitors (CBM). (global Project activities 112 & 221) Following on this, four training sessions were carried out and 18 members of the Atauro community from Beloi, Biqueli and Vila-Maumeta Sucos attended the training sessions for seagrass mapping and monitoring. The sections of Seagrass-Watch, translated by CI in Tetun, were provided to BV and used during the training. The community-based monitors will commence community surveys and participated in seagrass mapping in early 2017. (global Project activity 123) CI’s project. TL3, aims to strengthen and operationalize a national inter-ministerial mechanism to ensure a coordinated approach to national level coastal zone planning and decision-making which effectively addresses dugong and seagrass conservation. Project TL3 will deliver guidelines on management of seagrass and policy recommendation Project TL3 progressed in this period. CI team carried out a desktop review of existing policies and planning documents to see the level of integration of seagrass and dugong safeguards. Based on this research, the team found out that there was no existing legislation or planning guidelines for dugong and seagrass in place in Timor-Leste. CI team reached out to neighbouring country contacts, and to date Australia is the only country in the region with this level of legislation; Indonesia has localised project based guidelines and planning requirements related to dugong conservation which are not yet adopted at national level. According to CI’s desk review, the UAE to be the only other country with the same level of legislation in place as Australia. (global Project activity 411) CI’s Marine team and the local authority from Varoana, Vila (Atauro Island) and Com discussed and decided to put their seagrass area designated into their Suco Regulation (Local Regulation) (global Project activity 113) CI also initiated the work on good practices guidelines for dugongs and seagrass ecosystems conservation by reaching out to some CMS DTG technical experts to build on knowledge of dugong and seagrass needs. (global Project activity 322) Project TL4’s objective is to develop social marketing and innovative environmental education campaigns for dugongs and seagrass at a national-scale and across coastal communities. The project is managed by the National Directorate for Biodiversity Protection and Restoration (NDBPR). A report was submitted but no progress was reported by the Partner. TL5 is the National Facilitating Committee project in Timor-Leste. The project, managed by National Directorate for Biodiversity Protection and Restoration (NDBPR). In this period, the National Facilitator of Timor-Leste coordinated with all project Partners and carried out one meeting of the National Facilitating Committee. In addition, NDBPR and the National Facilitator organised two events in this period, as follows: Municipal workshop on Climate Change and Biodiversity issues, including dugong and seagrass conservation, in the Autonomic Region of Oecusse, Timor-Leste. The workshop was attended by local authorities, students, civil society and the community. Some community members reported that they had seen dugongs while they were fishing and traditionally dugong is protected by the community. Sustainable Ocean Initiative National Workshop, in Dili, organised by the Secretariat of the UNCBD and CSIRO Australia, together with the Ministry of Commerce, Industry and Environment. This was a capacity building workshop for Timorese national stakeholders, which was facilitated and coordinated by the National Facilitator as Timor-Leste’s National Focal Point for UN Convention on Biological Diversity (CBD). The workshop was financially supported by the Government of the Republic of Korea, contributed by the Ministry of Commerce, Industry and Environment, the Government of Timor-Leste. The workshop was an important opportunity for interactive discussions among different sectors and stakeholders in Timor-Leste on marine resource priorities, stakeholders’ value and perception of marine resources, drivers of change to marine environment and management response, and how to use this information in a marine spatial planning process in Timor-Leste. During this workshop important EBSA’s (Ecologically or Biologically Marine Significant Areas) were identified taking into account seagrass and dugong distribution. The National Facilitator actively promoted the project at several events, including: Timor-Leste’s Public Service Expo, held on 11 – 13 July 2016 National workshop on Blue Economy Assessment and Preparation of the National State of the Ocean and Coast Report. The National Facilitator gave a presentation on the Impact of Climate Change on Marine Biodiversity. Dugong and seagrass conservation was one of the issues discussed during the workshop. National Seminar on Terrestrial and Marine Survey Project of Atauro Island, organized by Conservation International with the Ministry of Agriculture and Fisheries in Dili. The rapid assessment carried by CI in 2016 identified 652 marine species from 52 families, including seagrass species. Marine species in Atauro Island per site is one of the highest species found to date. Conference of Parties (COP 13) of Biological Diversity in Cancun, Mexico, 4 – 17 December 2016. During the meeting, the National Facilitator was invited to share national experience of National Capacity building on the Sustainable Ocean Initiative during an EBSA (Ecologically or Biologically Marine Significant Areas) side-event. The outcome of the COP13 was the Cancun Declaration to mainstream biodiversity into various sectors such as Agriculture, Forestry, Fisheries and Tourism. Conference of Parties (COP22) on UNFCCC in Marrakech, Morocco with other delegates from Timor-Leste. One of the sectoral issues discussed in COP22 was “Biodiversity and Climate Change” was how climate change is affecting the coral reefs and marine biodiversity due to unsustainable industrial activities, infrastructure and population growth. In response to this issue one of the outcomes from this meeting was the implementation of the Paris Agreement by the Parties. (global Project activity 432) VANUATU Project ID and name Project Partner Project Component VU 1 To develop recommendations for a National Plan for conservation of dugongs and their seagrass habitats, identify areas important for dugongs and seagrasses conservation in Vanuatu and to raise awareness about dugongs and seagrasses in these area VESS Policy & Awareness VU 2 National Steering Committee for the GEF Dugong and Seagrass Conservation Project VESS Policy The two projects in Vanuatu, under the lead of VESS and with support from Department of Environmental Protection and Conservation (DEPC), Vanuatu and Vanuatu Fisheries Department (VFD), progressed well in this reporting period. Until 31 December 2016, 35% of the GEF funding available for Vanuatu under the Dugong and Seagrass Conservation Project were released for implementation of the two projects. Project VU1 has multiple objectives related to filling in knowledge gaps on dugongs and seagrass in Vanuatu, to develop and enforce a national plan for conservation of dugongs and their habitats and to raise awareness. 455 surveys were conducted to the end of December 2016. The survey team visited 25 islands within Vanuatu and each of the six provinces. The aim of the project was to complete a minimum of 250 questionnaires. Although VESS accomplish successfully this activity, they reported that there are still at least two places with known significant dugong populations that have not yet been visited. The majority of the data is yet to be entered onto the database (all the data to be uploaded by the end of February 2017). (global Project activity 311) While carrying out the questionnaires, VESS used the opportunity to distribute booklets about dugongs and seagrass and posters, one on dugongs and one on seagrass. These books and posters (in English and Bislama) were developed and printed by VESS with funding from a Critical Ecosystem Partnership Fund (CEPF) small grant. As of the development of this report, 1,986 posters and 776 booklets have been distributed. Downloadable versions of these materials are also available on the VESS website. (global Project activity 121) VU2 is the National Facilitating Committee project in Vanuatu. A meeting of the NFC was convened in October 2016. This was the fourth time, when the NFC met. (global Project activity 432) VESS continued promoting the two projects in Vanuatu through different media channels, such as the VESS Facebook page (https://www.facebook.com/vanuatuconservation) and VESS website http://www.vanuatuconservation.org. (global Project activity 121) The Dugong and Seagrass Conservation Project in Vanuatu was featured in a magazine article in Scuba Diver Australasia in August this year. (global Project activity 121)

2.2	Project implementation progress

| Outputs | Expected completion date | Implementation status as of end of reporting period expressed in % | Comments if variance. Describe any problems in delivering outputs |
| --- | --- | --- | --- |
| Output 1.1: (describe) Governance structures for community involvement in conservation and monitoring of dugong and seagrass ecosystems established or strengthened in target areas |  |  |  |
| Activity 1.1.1: (describe) National and local awareness surveys; awareness/ education campaigns | Q3 2018 | 45% |  |
| Activity 1.1.2: Community meetings/ workshops | Q3 2018 | 60% |  |
| Activity 1.1.3: Selection of sites for community-based stewardship | Q4 2015 | 85% | Some projects started later than expected. |
| Activity 1.1.4: Local (e.g. community/ government/ co-management, Fishing Association) structures established & functioning | Q2 2016 | 50% | Some projects started later than expected. |
| Activity 1.1.5: Consultative committees/ management councils, Dugong Protection Forum (MZ) | Q3 2018 | 20% |  |
| Output 1.2 Capacity developed for community-based stewardship (conservation and monitoring of dugongs & seagrass) |  |  |  |
| Activity 1.2.1.: Awareness/ education campaigns (media, social media) | Q3 2018 | 55% |  |
| Activity 1.2.2.: Training in dugong and seagrass community-based management (CBM) | Q3 2018 | 60% |  |
| Activity 1.2.3.: Training in dugong and seagrass monitoring | Q3 2018 | 40% |  |
| Output 1.3: Integrated community management plans (conservation and monitoring of dugong and seagrass ecosystems) developed and piloted |  |  |  |
| Activity 1.3.1: Baseline information gathering & consultations | Q1 2016 | 70% | A lot of information from all projects has been compiled. However, PCT expects more information to be reported in the next reporting period. |
| Activity 1.3.2: Participatory mapping, zonation | Q3 2018 | 30% |  |
| Activity 1.3.3: Pilot site management plan preparation | Q1 2016 | 30% | Data have been compiled and under processing – this information will feed the management plans. |
| Output 2.1: Management and incentive mechanisms and tools for sustainable fisheries – pilots and capacity building (local community and government) |  |  |  |
| Activity 2.1.1: Tools developed and tested at pilot sites | Q3 2018 | 40% |  |
| Activity 2.1.2: Pilots established; seed funding provided – community business plans | Q3 2018 | 50% |  |
| Activity 2.1.3: Alternative income-generation models developed and tested with communities (from Coastal Communities Toolbox & others) | Q3 2018 | 65% |  |
| Activity 2.1.4: Communities trained in use of tools/ new income-generating skills | Q3 2018 | 65% |  |
| Output 2.2: Awareness raising and social marketing programmes contributing to more sustainable practices (subsistence and small-scale artisanal fishers) in target areas |  |  |  |
| Activity 2.2.1: Awareness raised; social marketing pilot initiatives providing alternative finance | Q3 2018 | 45% |  |
| Activity 2.2.2: Economic valuation of ecosystem goods and services | Q3 2018 | 5% |  |
| Activity 2.2.3: Investigation of long-term sustainable finance mechanisms | Q3 2018 | 10% |  |
| Output 3.1: Critical knowledge gaps (dugongs and seagrass ecosystems) identified and surveys initiated/ completed |  |  |  |
| Activity 3.1.1: Research/ survey methodologies developed & tested (ecological: status, distribution, threats; socio-economic: behaviour/economics of fishers & fisheries; ecosystem services valuation) | Q3 2018 | 85% |  |
| Activity 3.1.2: Training in R&M methods, collaborative/ participatory surveys | Q3 2018 | 20% |  |
| Activity 3.1.3: Monitoring & evaluation systems established (e.g. “COSAP” model, MG) | Q3 2018 | 45% |  |
| Output 3.2: Good practice guidelines for dugongs and seagrass ecosystems conservation developed from project experience |  |  |  |
| Activity 3.2.1: Evaluation of project research (scientific and socio-economic), experience and use of models | Q3 2018 | 40% |  |
| Activity 3.2.2: Guidelines developed, consulted on (Project Partners, communities, technical experts) | Q3 2018 | 35% |  |
| Output 3.3: Conservation-relevant information and guidance (dugongs and seagrass ecosystems) collated and disseminated |  |  |  |
| Activity 3.3.1: Information and guidance (dugongs and seagrass ecosystems) collated and disseminated; best practice and experience shared | Q3 2018 | 35% |  |
| Activity 3.3.2: Preparation and implementation of a Project Communication strategy and materials and national communications strategies | Q3 2018 | 65% |  |
| Output 4.1: Policy, planning and regulatory gaps reviewed (conservation of dugongs and seagrass ecosystems) and recommendations developed |  |  |  |
| Activity 4.1.1: National legislative, policy and regulatory review of gaps/ barriers | Q3 2018 | 35% |  |
| Activity 4.1.2: National workshops and consultation on legal, policy, regulatory gaps and recommendations | Q3 2018 | 20% |  |
| Activity 4.1.3: Draft National Strategies/ action plans (dugong and seagrass conservation) developed | Q3 2018 | 25% |  |
| Output 4.2: Advocacy programmes and advocacy capacity for improved conservation management of dugongs and their seagrass ecosystems developed and implemented |  |  |  |
| Activity 4.2.1: National and local (community) advocacy networks established and capacity developed | Q3 2018 | 25% |  |
| Activity 4.2.2: Advocacy programmes and campaigns | Q3 2018 | 35% |  |
| Output 4.3: Capacity for national and regional networking and contribution to global policy for effective dugong and seagrass conservation in Indian and Pacific Ocean basins |  |  |  |
| Activity 4.3.1: Initiation and implementation of national programmes and component projects | Q3 2018 | 65% |  |
| Activity 4.3.2: Functioning regional programme and networks (information, advocacy/ policy) | Q3 2018 | 60% |  |

2.3	Action plan to address any project shortcomings.

This Section should be completed if project progress was rated MS, MU, U or HU during the previous Project Implementation Review (PIR) or by the Mid-term Review/Evaluation.

| Problem(s) identified in previous PIR | Action(s) taken | By whom | When |
| --- | --- | --- | --- |
| N.A. |  |  |  |

2.4	Risk management

If internal or external risks were rated as Substantial or High during the previous Project Implementation Review (PIR) or during the Mid-term Review, please indicate what risk mitigation measures were implemented during the period and with what results:

| Risk Statement | Action taken | By who | Date | Result |
| --- | --- | --- | --- | --- |
| N.A. |  |  |  |  |

3.	MONITORING AND EVALUATION

3.1. Please describe activities for monitoring and evaluation carried out during the reporting period

As mentioned in section 2.1 of the report, all national projects half-yearly progress reports for the period January-July 2016 were provided to the CMS DTG for their review and feedback. Five experts reviewed the reports. The feedback was shared with the respective Partners to follow up on it. Partners were then requested to provide information on how they addressed DTG’s recommendations in their half-yearly progress reports. This process of internal monitoring is important for the sustainability of the global Project results and is planned to continue until the end of the global Project. PCT and all Project Partners prepared for the mid-term review of the Project. The review began in December 2016 and will run until March 2017.

4.	INVENTORY OF STAFF, CONTRACTS, MEETINGS AND OUTPUTS

4.1	Staffing details of Executing Partner (Applies to personnel, experts, consultants paid by the project budget

| Functional Title | Nationality | Budget Line (1101, 1102, 1201,1301, etc) |
| --- | --- | --- |
| Project Coordinator | Bulgarian | 1101, 1102 |
| Project Associate | Egyptian | 1201 |
| Project Finance Manager | Lebanese | 1301 |
| Project Communications Manager | American | 1302 |

4.2	Sub-contracts

| Name of contractee | Address | Budget Line (2101, 2201, 2301, etc) |
| --- | --- | --- |
| WWF Indonesia | Graha Simatupang, Tower 2 Unit C, 7th-11th floor, Jalan TB Simatupang, Jakarta 12540, Indonesia | 2101, 2102 |
| Blue Ventures | Omnibus Business Centre, 39-41 North Road, London, N7 9DP, UK | 2105, 2106, 2136 |
| Conservation Centrée sur la Communauté (C3) | Lot IB 65 Bis, Immeuble Feedback Isoraka, Antananarivo, Madagascar | 2107 |
| Madagascar National Parks (COSAP) | Maromandia, District of Analalava, Région SOFIA, Madagascar | 2108 |
| WCS | 2300 Southern Boulevard, Bronx, New York, USA | 2110 |
| Reef Check Malaysia | Box # 606, Unit 5.19 Wisma Central, Jalan Ampang, 50450, Kuala Lumpur, Malaysia | 2111 |
| Center for Marine and Coastal Studies, Universiti Sains Malaysia | Universiti Sains Malaysia,11800 USM,Pulau Pinang,Malaysia | 2113 |
| The MareCet Research Organization | 3-1-1, Antilla Lagoon Villas, Jalan Anggerik Malaxis 31/171, Kota Kemuning, 40460 Shah Alam, Malaysia | 2114 |
| SARAWAK FORESTRY Corporation | Lot 218, KCLD, Jalan Tapang, Kota Sentosa, 93250 Kuching, Sarawak, Malaysia | 2115 |
| Dugongos.org | Rua 4.400 No. 403. Bairro Laulane, Maputo, Mozambique | 2117, 2118 |
| Endangered Wildlife Trust (EWT) | Building K2, Pinelands Office Park, Modderfontein, 1609, Johannesburg, South Africa | 2119 |
| Ministry of Land, Environment and Rural Development | Rua de Kassuende, no.167, P.O.Box 2020, Maputo, Mozambique | 2120, 2121 |
| WorldFish | WorldFish Headquarters (Malaysia), Jalan Batu Maung, Batu Maung, 11960 Bayan Lepas, Penang, Malaysia | 2122, 2124, 2126 |
| SICCP | P.O.Box 2378, SIDT Building, Honiara, Solomon Islands | 2125 |
| BEAR (Biodiversity Education And Research) | 92/2, Ananda Rajakaruna Mawatha, Colombo 10. Sri Lanka | 2127 |
| DWC | 811/A, Jayanthipura Road, Mattaramulla, Sri Lanka | 2128 |
| IUCN Sri Lanka | 53, Horton Place, Colombo 07, Sri Lanka | 2130 |
| National Aquatic Resources Research and Development Agency (NARA) | Crow Island, Colombo 15, Sri Lanka | 2131 |
| Ocean Resources Conservation Association (ORCA) | No,9, Balapokuna place, Colombo 6, Sri Lanka | 2132 |
| Sri Lanka Turtle Conservation Project (SLTCP) | 72/4, Old Galle Road, Walana, Panadura, Sri Lanka | 2133 |
| Conservation International Foundation (CI) | 2011 Crystal Drive, Suite 500, Arlington, VA 22202, USA | 2135, 2137 |
| MCIE-DNBPR | Ministry of Commerce, Industry and Environment, Timor-Leste Edificio Fomento, Mandarin, Dili, Timor-Leste | 2138 & 2138.1 |
| VESS | Rue de Reece Discombe, Nambatu, Port Vila, Vanuatu | 2139 & 2140 |
| Monarch Ltd | Masdar City, Abu Dhabi, United Arab Emirates | 2205 |

4.3	Meetings

Please refer to Appendix 1 of this document

| Meeting type | Title | Venue | Dates (dd/mm) | Convened by | Organized by | Number of participants | Report/ Minutes issued Yes/No | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

4.4	List(s) of meeting participants

Please refer to Appendix 2 of this document

| No. | Name of participant | Nationality |
| --- | --- | --- |

4.5	Documents, other printed materials, videos, and soft products (such as CDs or websites)

Please refer to Appendix 3 of this document

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication date |
| --- | --- | --- | --- | --- | --- | --- |

| Name of Project Manager: Maya Bankova-Todorova | Name of Project Manager Supervisor: Dr Frederic Launay |
| --- | --- |
| Signature: | Date: 02 February 2017 | Signature: | Date: 02 February 2017 |

APPENDIX 1 – SECTION 4.3 MEETINGS

| Meeting type | Title | Venue | Dates (dd/mm) | Convened by | Organized by | Number of participants | Report/ Minutes issued Yes/No | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ID 1 |
| Expert group meeting | Dugong and Seagrass NPOA draft development | MMAF, Jakarta | 18 July 2016 | CMB | CMB | 15 | Y (draft 1 NPOA) | IND | 20 Jul 2016 |
| Coordina-tion meeting | National Dugong Conser-vation Committee (NDCC) | Santika Hotel, Bogor | 2 Aug 2016 | CMB | CMB | 15 | N (present-ation material only) | IND | 2 Aug 2016 |
| Public consultation meeting | DSCP implement-tation | Kotawaringin Barat Fisheries Agency Office | 4 Aug 2016 | Kotawaringin Barat Fisheries Agency | CMB | 26 | Y | IND & ENG executive summary | 22 Dec 2016 |
| Public consultation meeting | DSCP implement-tation | Alor Fisheries Agency Office | 9 Aug 2016 | Alor Fisheries Agency | CMB | 40 | Y | IND & ENG executive summary | 22 Dec 2016 |
| Public consultation meeting | DSCP implement-ation | Bumi Harapan Hotel, Tolitoli | 10 Aug 2016 | Tolitoli Fisheries Agency | CMB | 44 | Y | IND & ENG executive summary | 22 Dec 2016 |
| Expert group meeting | NDCC and Dugong and Seagrass NPOA draft development | Pajajaran Suites Hotel, Bogor | 20 Sep 2016 | CMB | CMB | 18 | Y (revision of draft NPOA) | IND | 22 Sep 2016 |
| Coordina-tion meeting | Consultation with PCT and DTG Meeting | MMAF | 17-18 Oct 2016 | CMB | DSCP PCT | 18 | N (present-ation materials only) | IND & ENG | 17 & 18 Oct 2016 |
| Expert group meeting | Dugong and Seagrass NPOA draft development | Santika Hotel, Bogor | 21 Oct 2016 | CMB | CMB | 23 | Y (final draft of NPOA) | IND & ENG | 21 Nov 2016 & 9 Jan 2017 |
| Coordina-tion meeting | Executive Project Steering Committee | Kuala Lumpur | 1-2 Nov 2016 | DSCP PCT | DSCP PCT | 18 | Y (report from DSCP PCT & present-ation material) | ENG | 9 Dec 2016 |
| Coordina-tion meeting | EPSC follow up meeting | MMAF | 21 Nov 2016 | MMAF | MMAF | 20 | Y (minutes of meeting) | IND | 21 Nov 2016 |
| ID 2 |
| Coordination meeting | Preliminary survey preparation | MMAF | 21 July 2016 | CMB | LIPI | 11 | N (ppt only) | IND | 21 Jul 2016 |
| Coordination meeting | Preliminary survey preparation | Santika Hotel, Bogor | 2 Aug 2016 | CMB | LIPI | 10 | N (ppt only) | IND | 2 Aug 2016 |
| Coordination meeting | Preliminary survey preparation | LIPI | 16 Aug 2016 | LIPI | LIPI | 8 | N (ppt only) | IND | 16 Aug 2016 |
| Coordination meeting | Preliminary survey preparation | LIPI | 1 Sep 2016 | LIPI | LIPI | 7 | N (ppt only) | IND | 1 Sep 2016 |
| Coordination meeting | Preliminary survey preparation | LIPI | 30 Sep 2016 | LIPI | LIPI | 10 | N (ppt only) | IND | 30 Sep 2016 |
| Coordination meeting | Communi-cation strategy workshop preparation | WWF | 15 Nov 2016 | WWF | WWF | 6 | Y (MoM) | IND | 17 Nov 2016 |
| Coordination meeting | Communi-cation strategy workshop preparation | WWF | 2 Dec 2016 | WWF | WWF | 5 | N (draft ToR) | IND | 2 Dec 2016 |
| Coordination meeting | Training preparation | MMAF | 15 Dec 2016 | MMAF | WWF | 20 | Y (MoM) | IND | 17 Nov 2016 |
| Coordination meeting | Communi-cation strategy workshop preparation | MMAF | 16 Dec 2016 | MMAF | WWF | 8 | N (workshop agenda) | IND | 23 Dec 2016 |
| Coordination meeting | Communi-cation strategy workshop preparation | MMAF | 20 Dec 2016 | MMAF | WWF | 9 | N (final ToR, workshop form) | IND | 23 Dec 2016 |
| MG 1 |
| 1. Community meeting | Consultation on creating a permanent reserve ; Presentation of S. Roger | Nosy Lava | 01/07 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | Y | French | 19/08 |
| 2. Community meeting | Management measures identification and validation; Presentation of S. Roger | Nosy Maroantaly | 02-03/07 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | Y | French | 19/08 |
| 3. Community meeting | Presentation of S. Roger | Ampandikoara | 04/07 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | Y | French | 19/08 |
| 4. Community meeting | Management measures identification and validation; Presentation of S. Roger | Beloba | 05/07 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | Y | French | 19/08 |
| 5. Community meeting | Presentation of S. Roger | Manombo | 06/07 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | Y | French | 19/08 |
| 6. Community meeting | Presentation of S. Roger | Nosy Marify | 07/07 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | Y | French | 19/08 |
| 7. Community meeting | Awareness raising about habitats and participatory mapping | Nosy Abohazo | 24-25/07 | Blue Ventures | Vezo Miray, Blue Ventures |  | Y | English | 02/08 |
| 8. Community meeting | Awareness raising about habitats and participatory mapping | Nosy Manandra | 26-27/07 | Blue Ventures | Vezo Miray, Blue Ventures |  | Y | English | 02/08 |
| 9. Community meeting | Awareness raising about habitats and participatory mapping | Nosy Marify | 28-29/07 | Blue Ventures | Vezo Miray, Blue Ventures |  | Y | English | 02/08 |
| 10. Workshop | Presentation of mapping results | Maintirano | 18/08 | Blue Ventures | Blue Ventures |  | Y | French | 29/08 |
| 11. Community meeting | Discussion on the MCS programme | Ambalahonko | 11/10 | Blue Ventures | Vezo Miray, Blue Ventures |  | N |  |  |
| 12. Community meeting | Discussion on the MCS programme | Ampasimandroro sector 1-2 | 12/10 | Blue Ventures | Vezo Miray, Blue Ventures |  | N |  |  |
| 13. Community meeting | Discussion on the MCS programme | Ampasimandroro sector 3 | 13/10 | Blue Ventures | Vezo Miray, Blue Ventures |  | N |  |  |
| 14. Workshop | Elaborating the general ouline of the MCS programme | Maintirano | 17-22/10 | Blue Ventures | Blue Ventures |  | Y | French | 02/11 |
| 15. Community meeting | Public validation of the general outline of the MCS programme | Nosy Manandra | 09-10/11 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | N |  |  |
| 16. Community meeting | Public validation of the general outline of the MCS programme | Nosy Maroantaly | 11/11 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | N |  |  |
| 17. Community meeting | Public validation of the general outline of the MCS programme | Nosy Lava | 12/11 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | N |  |  |
| 18. Community meeting | Public validation of the general outline of the MCS programme | Nosy Andrano - Mangily | 13/11 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | N |  |  |
| 19. Community meeting | Public validation of the general outline of the MCS programme | Ampandikoara | 18/11 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | N |  |  |
| 20. Community meeting | Public validation of the general outline of the MCS programme | Beloba | 19/11 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | N |  |  |
| 21. Community meeting | Public validation of the general outline of the MCS programme | Manombo | 20/11 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | N |  |  |
| 22. Community meeting | Public validation of the general outline of the MCS programme | Soahany | 23/11 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | N |  |  |
| MG 2 |
| Education workshop | Dugong education and awareness day | Nosy Hara-Diego | 8 July 2016 | MIHARI | MIHARI | 75 | Yes | French | 10 Aug 2016 |
| 2. Focus group | Focus group with fishers for the site identification | Ambanja, Ambilobe and Analalava | 08 – 14 Dec 2016 | MIHARI | MIHARI | 130 | Yes | French | 4 Jan 2017 |
| MG 3 |
| Community Park Management represen-tatives meeting | Monthly meeting with CLP in Lalandaka | Lalandaka | 26th july 2016 | C3 | RANDRIANJAFIMANANA Nambinint-soa Tahiry, Senior Progr-amme Officer RALAIFANASINA Andria-nady Tahina, Prog-ramme Officer Database | 07 | Y | Malagasy |  |
| Community Park Management represen-tatives meeting | Monthly meeting with CLP in Anjiamaloto | Anjiamaloto | 23rd August 2016 | C3 | RALAIFANASINA Andria-nady Tahina, Progr-amme Officer | 01 | Y | Malagasy |  |
| Community Park Management representatives meeting | Monthly meeting with CLP in Ampasindava | Ampasin-dava | 23rd Nov | C3 | Lalarisoa Rakotoarimino, PC, Mihary Ramiandri-soa, SPO, Anwar Salimo, PO Anatoli Velondia, PO | 09 | Y | Malagasy |  |
| Community Park Management represen-tatives meeting | Community consultation about goat farm in Lalandaka/ CLP meeting | Lalandaka | 25th Nov | C3 | Anwar Salimo, PO Anatoli Velondia, PO | 13 | Y | Malagasy |  |
| Community Park Management represen-tatives meeting |  |  |  | C3 |  |  |  |  |  |
| Community Park Management represen-tatives meeting | Monthly meeting with CLP in Andrano-mavo | Andrano-mavo | 17th Dec 2016 | C3 | Mihary Ramiandrisoa, SPO Patrice, Student | 09 | Y | Malagasy |  |
| Community consultation | FIVE-PANOHA Consultation about poultry farm and restaurant | Ampasin-dava | 23rd Nov | C3 | Lalarisoa Rakotoari-mino, PC, Mihary Ramiandri-soa, SPO, Anwar Salimo, PO Anatoli Velondia, PO | 14 | Y | Malagasy |  |
| Internal planning meeting | C3 staff quarterly meeting on GEF plans | C3 Diego field office |  | C3 | Lalarisoa Rakotoarimino, PC | 4 | Y | Malagasy |  |
| NGO GEF partner meeting |  | SEMER office Antana-narivo |  |  |  |  | Y |  |  |
| COSAP meeting |  |  |  | COSAP |  | 1 | Y |  |  |
| MG 4 |
| Community workshop at Mahadera | Establishing new governance structure and “dina”. | Mahadera village | 10/09/2016 | Local Administrati-ve Authorities (Mayors, Chief of the Village) | COSAP | 57 | Y | Malagasy | 18/11/2016 |
| Community workshop at Ambalabao | Establishing new governance structure and “dina”. | Ambalabaovillage | 10/09/2016 | Administrati-ve Authorities (Mayors, Chief of the Village) | COSAP | 28 | Y | Malagasy | 18/11/2016 |
| First meeting for local communities at Berafia | Preparation of the first outreach event “Dugong Festival” | Berafia-village | 17/09/2016 | Administrati-ve Authorities (Mayors, Chief of the Village) | COSAP | 128 | Y | Malagasy | 2/11/2016 |
| Second meeting for local communities at Berafia | Preparation of the first outreach event “Dugong Festival” | Berafia village | 18/10/2016 | Administrati-ve Authorities (Mayors, Chief of the Village) | COSAP | 126 | Y | Malagasy | 2/1&/2016 |
| Local participation of community members in the festival | First edition of the dugong festival in Berafia | Berafia Village | 28 – 29/10/2016 | Administrati-ve Authorities (Chiefs of Region and District, Mayors, Chief of the Villages) | COSAP | 167 | Y | Malagasy | 18/11/2016 |
| MG 6 |
| Community meeting | Information meeting on the acoustic recorders | Eight villages of Ambaro and Ankify Bays | Sept. 2016 | Armel Bezafy (Field Technical Assistant) | Armel Bezafy (Field Technical Assistant) | Villagers and local/tradi-tional authorities | Y mission report | French | Sept.2016 |
| MY 1 |
| Internal project partners meeting |  | Putrajaya | 1st July 2016 | Depart-ment of Marine Parks Malaysia (DMPM) | (DMPM) | 3 | N | English |  |
| National Project coordi-nation Meeting | National Facilitation Meeting | Department of Fisheries office, Putrajaya | 4th October | Depart-ment of Fisheries (DoF) | Depart-ment of Fisheries (DoF) |  | N |  |  |
| Project Briefing to DMPM staff in Johor | Briefing on GEF Dugong-Seagrass Project-MY1 | Department of Marine Park Johor | 20th October | Depart-ment of Marine Park | Depart-ment of Marine Park | 15 | N | Bahasa |  |
| State technical meeting | Dugong Sanctuary Technical Committee Meeting | Kota Iskandar, Iskandar Puteri, Johor | 11th October 2016 | Johor State Govern-ment | Johor State Govern-ment |  | Y | Bahasa |  |
| National Project coordi-nation Meeting | National Facilitation Meeting | Department of Fisheries office, Johor. | 25th October 2016 | Depart-ment of Fisheries (DoF) | Depart-ment of Fisheries (DoF) |  | N | Bahasa |  |
| Discussion With Project Coordinator Team | Discussion With Project Coordinator Team | Hotel Royale Chulan Damansara, Kuala Lumpur | 31 October | PCT | Depart-ment of Fisheries (DoF) | 10 | N | English |  |
| MY 2 |
| Coordi-nating Project Activities | 1 Meeting For Coordi-nating the Project Activities of MY1, MY3 and MY4 on 4 October 2016, Putrajaya | Putrajaya | 4 October 2016 | National Focal Point | National Focal Point | 12 | yes | Malay | 10 Oct 2016 |
| National Facilitating Team | 2. Second Meeting on National Facilitating Team 25 October 2016, Johor Bahru | Johor Bahru | 25 October 2016 | National Focal Point | National Focal Point | 9 | yes | Malay | 7 Nov 2016 |
| Review Project Progress | 3. Meeting to Review the Progress of Malaysia Project Dugong GEF 5 With Project Coordinator Team (PCT) on 31 October 2016, Kuala Lumpur | Kuala Lumpur | 31 October 2016 | National Focal Point | PCT | 10 | No (But every Project Partner take note on the advised and suggestion given by PCT) |  |  |
| Stake holder Consultation | 4. Organise Discussion With Local Communities at Sibu and Tinggi Islands together with the PCT on 3 & 4 November 2016. | Sibu Island & Tinggi Island | 3 – 5 November 2016 | National Focal Point | National Focal Point | ‘ 14 | No (But every Project Partner take note on the advised and suggestion given by PCT) |  |  |
| MY 3 |
| Internal meeting | Preparatory meeting for printing of educational material and ordering of tablet | USM | 24/8/2016 | Leela Rajamani | Leela Rajamani | 3 | N | English | 24/8/2016 |
| Partner and focal point consultation meeting | Meeting for coordination of project activities GEF 5 for project MY1, MY3, MY4. | Fisheries Department Malaysia Putrajaya | 4/10/2016 | Syed Abdullah | Syed Abdullah | 7 | N | English | 4/10/2016 |
| Internal meeting | Discussion of upcoming trip and activities (24-28th Oct 2016) | USM | 20/10/2016 | Leela Rajamani | Leela Rajamani | 4 | N | English | 20/10/2016 |
| Project coordinator meeting between partners focal point and agencies | National meeting for facilitating team | State Fisheries Deparment Johor | 25/10/2016 | Syed Abdullah | Syed Abdullah | 11 | N | Malay | 25/10/2016 |
| Project coordinator meeting GEF dugong project | Discussion with project coordinator team project | Hotel Royale Chulan Kuala Lumpur | 31/10/2016 | Syed Abdullah | Syed Abdullah | 14 | N | English | 31/10/2016 |
| Internal meeting | Project coordination meeting MY3 | USM | 22/11/2016 | Leela Rajamani | Leela Rajamani | 5 | N | English | 22/11/2016 |
| Internal meeting | Project activities meeting for January 2017 | USM | 27/12/2016 | Leela Rajamani | Leela Rajamani | 4 | N | English | 27/12/2016 |
| MY 5 |
| Coordination meeting | Project coordination and local participation meetings with Miri Regional Office Staff | Miri, Sarawak, Malaysia | 24-Jan-16 | Project Manager | SFC | 20 | N | Bahasa Malaysia |  |
| Workshop | BootCamp on QGIS & R | Kuala Lumpur, Malaysia | 6 - 10 Mar 16 | Biodi-versity Conser-vation Society of Sarawak (BCSS) | BCSS | 20 | N | English |  |
| Training | Drone (UAS) flight, mainte-nance and mission training | Sandakan, Sabah, Malaysia | 13 – 20 Mar 16 | Hornbill Surveys | SFC | 4 | N | English |  |
| Training/ Workshop | Health Assessment for Endangered Marine Species | Trang, Thailand | 23-30 June 16 | Dept. of Marine and Coastal Re-sources Thailand | Phuket Marine Biodi-versity Centre | 25 | N | English |  |
| Meeting | GEF Dugong and Seagrass National Coordi-nation Meeting | Putrajaya, Malaysia | 30 Apr 16 | National Coordinator | Dept of Fisheries Malaysia | 10 | N | Bahasa Malaysia |  |
| MZ 1 |
| Meeting | 1. Meeting with Inhassoro District Administrator | Inhassoro | 1-July-2016 | Urszula Stankiewicz, Isabelle Giddy | Urszula Stankiewicz, Isabelle Giddy | 3 | N |  |  |
| Community Meeting | 2. Introductory Meeting with Zenguelemo Community | Zenguelemo, Bazaruto Island | 4-July-2016 | Lionel Massicane | Isabelle Giddy | 56 | Y | English | 4-July- 2016 |
| Focus Group | 3.General Focus Group | Maxulane, Bazaruto | 7-July-2017 | Lionel Massicane | Isabelle Giddy | 27 | Y | English | 18-July-2016 |
| Focus Group | 4.General Focus Group | Pangaia, Bazaruto | 8-July-2016 | Lionel Massicane | Isabelle Giddy | 20 | Y | English | 18-July-2016 |
| Focus Group | 5.General Focus Group | Zenguelemo, Bazaruto | 8-July-2016 | Lionel Massicane | Isabelle Giddy | 45 | Y | English | 18-July-2016 |
| Training | 6.Health Survey Training | Sitone, Bazaruto Island | 13-July-2016 | Urszula Stankiewicz, Isabelle Giddy | Urszula Stank-iewicz, Isabelle Giddy | 7 | N |  |  |
| Training | 7.Focus Group Training | Sitone, Bazaruto | 7-September-2016 | Lionel Massicane | Urszula Stank-iewicz, Isabelle Giddy | 6 | N |  |  |
| Focus Group | 8.Family Planning Focus Group | Sitone, Bazaruto | 8-September-2016 | Lionel Massicane | Urszula Stank-iewicz, Isabelle Giddy | 26 | Y | English | 26-October-2016 |
| Focus Group | 9.Family Planning Focus Group | Machulane, Bazaruto | 9-September-2016 | Lionel Massicane | Urszula Stank-iewicz, Isabelle Giddy | 26 | Y | English | 26-October-2016 |
| Focus Group | 10.Family Planning Focus Group | Pangaia, Bazaruto | 12-Sept-2016 | Lionel Massicane | Urszula Stank-iewicz, Isabelle Giddy | 26 | Y | English | 26-October-2016 |
| Focus Group | 11.Family Planning Focus Group | Zenguelemo, Bazaruto | 12-Sept-2016 | Lionel Massicane | Urszula Stank-iewicz, Isabelle Giddy | 26 | Y | English | 26-October-2016 |
| Partner Meeting | 12.Meeting with PSI | Maputo | 7-Nov-2016 | Urszula Stankiewicz | Urszula Stan-kiewicz | 2 | N |  |  |
| Workshop | 13. Alternative Livelihood Workshop- Machila Magic | Vilankulus | 17-Nov-2016 | Machila Magic | Machila Magic | 15 | N |  |  |
| MZ 2 |
| No meetings indicated in Partner’s HYR |
| MZ 4 |
| Fisher Meeting | ICT4 Fisheries | Fishhoek, Cape Town | 7-10 Nov 2016 | Serge Raemaek-ers | WIOMSA, UCT and Blue Ventures | 55 | Y | ENG | Nov 2016 |
| Fisher Meeting | Introduction of Fisher App in Bazaruto | Thomba Yedhu, Zenguelemo | 11 Oct 2016 | Isabelle Giddy | EWT | 3 | N |  |  |
| Fisher Meeting | Follow up on Fisher App | Thomba Yedhu, Zenguelemo | 18 Oct 2016 | Isabelle Giddy | EWT | 6 | N |  |  |
| Fisher Meeting | Follow up and feedback on fisher app | Thomba Yedhu, Zenguelemo | 20 Nov 2016 | Isabelle Giddy | EWT | 6 | N |  |  |
| MZ 5 |
| Meeting | Meeting with Provincial Director | Provincial Directorate of Land, Environ-ment and Rural Develop-ment of Inhambane | 19-Sep | DINAB | Anselmo Gaspar | 5 | Y | Portug-uese |  |
| Meeting | Meeting with Head of the Department of Environmental Management | Provincial Directorate of Sea, Inland Waters and fisheries of Inhambane | 19-Sep | DINAB | Anselmo Gaspar | 5 | Y | Portug-uese |  |
| Meeting | Meeting with Vilankulo District Services of Infrastructure and Planning (SDPI), | SDPI | 21-Sep | DINAB | Anselmo Gaspar | 8 | Y | Portug-uese |  |
| Meeting | Meeting with Vilankulo District Delegation of Sea, Inland Waters and fisheries | Vilankulo | 21-Sep | DINAB | Anselmo Gaspar | 9 | Y | Portug-uese |  |
| Meeting | Meeting with Vilankulo District Services of Economics Activities (SDAE), | SDAE | 21-Sep | DINAB | Anselmo Gaspar | 11 | Y | Portu-guese |  |
| Meeting | Meeting with Inhassoro District Maritime Autority (ADMAR) | ADMAR | 21-Sep | DINAB | Anselmo Gaspar | 9 | Y | Portu-guese |  |
| Focus group | Interview Fisheries Communities Consul (CCP) of Macunhe | Bulande, Vilankulo | 22-Sep | DINAB | Anselmo Gaspar | 23 | Y | Portu-guese |  |
| Focus group | Interview of CCP of Guitine | Guitine, Vilankulo | 22-Sep | DINAB | Anselmo Gaspar | 13 | Y | Portu-guese |  |
| Focus group | Interview of CCP of Mangalice | Mangalice, Vilankulo | 23-Sep | DINAB | Anselmo Gaspar | 14 | Y | Portu-guese |  |
| Focus group | Interview of CCP of Mabandene | Mabandene, Vilankulo | 23-Sep | DINAB | Anselmo Gaspar | 13 | Y | Portu-guese |  |
| Focus group | Interview of CCP of Mundego | Mundego, Vilankulo | 23-Sep | DINAB | Anselmo Gaspar | 13 | Y | Portu-guese |  |
| Focus group | Interview of Fishery Association of Vilankulo (APV) | Centre, Vilankulo | 23-Sep | DINAB | Anselmo Gaspar | 13 | Y | Portu-guese |  |
| Focus group | Interview of Artisanal Fishery Association of Mangalice (APAMA) | Mangalice, Vilankulo | 23-Sep | DINAB | Anselmo Gaspar | 14 | Y | Portu-guese |  |
| Focus group | Interview of CCP of Chingonguene | Chingonguene, Vilankulo | 24-Sep | DINAB | Anselmo Gaspar | 40 | Y | Portu-guese |  |
| Focus group | Interview of CCP of Marape | Marape, Vilankulo | 24-Sep | DINAB | Anselmo Gaspar | 29 | Y | Portu-guese |  |
| Focus group | Interview of CCP of Chichocane | Chichocane, Vilankulo | 24-Sep | DINAB | Anselmo Gaspar | 15 | Y | Portu-guese |  |
| Focus group | Interview of Fishery Association of Marape | Marape, Vilankulo | 24-Sep | DINAB | Anselmo Gaspar | 29 | Y | Portu-guese |  |
| Focus group | Interview of Fishery Association of Kanyikwedu | Benguera Island, Vilankulo | 24-Sep | DINAB | Anselmo Gaspar | 12 | Y | Portu-guese |  |
| MZ 6 |
| Meeting | Meeting with Partners | DINAB | 10-Aug | DINAB | Anselmo Gaspar | 11 | Y | Portu-guese, English |  |
| Meeting | Meeting with Provincial Director | Provincial Directorate of Land, Environment and Rural Development of Inhambane | 19-Sep | DINAB | Anselmo Gaspar | 5 | Y | Portu-guese |  |
| Meeting | Meeting with Head of the Depar-tment of Environ-mental Manage-ment | Provincial Directorate of Sea, Inland Waters and fisheries of Inhambane | 19-Sep | DINAB | Anselmo Gaspar | 6 | Y | Portu-guese |  |
| Meeting | Meeting with Inhassoro District Services of Infra-structure and Planning (SDPI), | SDPI | 27-Sep | DINAB | Anselmo Gaspar | 8 | Y | Portu-guese |  |
| Meeting | Meeting with Inhassoro District Delegation of Sea, Inland Waters and fisheries | Inhassoro | 27-Sep | DINAB | Anselmo Gaspar | 9 | Y | Portu-guese |  |
| Meeting | Meeting with Inhassoro District Services of Economics Activities (SDAE), | SDAE | 27-Sep | DINAB | Anselmo Gaspar | 9 | Y | Portu-guese |  |
| Meeting | Meeting with Inhassoro District Maritime Autority (ADMAR) | ADMAR | 27-Sep | DINAB | Anselmo Gaspar | 9 | Y | Portu-guese |  |
| Focus group | Interview CCP of Fequete | Fequete, Inhassoro | 27-Sep | DINAB | Anselmo Gaspar | 15 | Y | Portu-guese |  |
| Focus group | Interview CCP of Peta+ne 1 | Petane 1, Inhassoro | 27-Sep | DINAB | Anselmo Gaspar | 15 | Y | Portu-guese |  |
| Focus group | Interview of Fishery Association (FA) of Inhassoro (API) | Petane 1, Inhassoro | 27-Sep | DINAB | Anselmo Gaspar | 15 | Y | Portu-guese |  |
| Focus group | Interview Fisheries Communities Consul (CCP) of Tzondzo | Tsondzo, Inhassoro | 28-Sep | DINAB | Anselmo Gaspar | 14 | Y | Portu-guese |  |
| Focus group | Interview CCP of Mucocuene | Mucocuene, Inhassoro | 28-Sep | DINAB | Anselmo Gaspar | 14 | Y | Portu-guese |  |
| Focus group | Interview CCP of Nhagondzo | Nhagondzo, Inhassoro | 28-Sep | DINAB | Alexandre Bartolomeu | 23 | Y | Portu-guese |  |
| Focus group | Interview CCP of Vuca | Vuca, Inhassoro | 28-Sep | DINAB | Anselmo Gaspar | 33 | Y | Portu-guese |  |
| Focus group | Interview of Mozambican FA of Inhassoro (AMOPI) | Inhassoro | 28-Sep | DINAB | Alexandre Bartolomeu | 13 | Y | Portu-guese |  |
| Focus group | Interview of Trading Fishery of Inhassoro (ACOPEI) | Mucocuene, Inhassoro | 28-Sep | DINAB | Anselmo Gaspar | 13 | Y | Portu-guese |  |
| Meeting | Meeting with Bazaruto Arquipelago National Park (BANP) | BANP | 29-Sep | DINAB | Anselmo Gaspar | 11 | Y | Portu-guese |  |
| Focus group | Interview CCP of Bazaruto | Sitone, Inhassoro/Bazaruto | 29-Sep | DINAB | Anselmo Gaspar | 16 | Y | Portu-guese |  |
| Meeting | Meeting with Partners | Chiuta Guest House | 14-Oct | DINAB | Anselmo Gaspar | 8 | Y | Portu-guese |  |
| Meeting | NFC meeting | DINAB | 17-Oct | DINAB | Anselmo Gaspar | 21 | Y | Portu-guese |  |
| SB 1 – SB 5 |
| SB 2 – SB 4 |
| National | Seagrass and Dugong Project – National Facilitating Meeting | Ministry of Fisheries (MoF) (Honiara) | 12th December | Ministry of Environment (MoE), Ministry of Fisheries (MoF) SICCP, WorldFish, | Ministry of Environment (MoE) | 4 | No | N/A | N/A |
| Workshop/ training | Seagrass and Dugong Marovo seageass and Dugong training | SIDT Building (Honiara) | 28th September | Marovo and Tetepare Represent-atives | SICCP | 11 | No | N/A | N/A |
| SB 3 |
| LK 1 |
| No meetings indicated in Partner’s HYR |
| LK 2 |
| Project Steering Committee | National Facilitating Committee | IUCN | 1-07-16 | IUCN | NF | 11 | Y | English |  |
|  | National Facilitating committee | DWC | 10-10-16 | Marine unit | Marine unit | 06 | Y | English/ Sinhala |  |
|  | National steering committee | DWC | 16-11-16 | Marine unit | Marine unit | 07 | Y | English/ Sinhala |  |
| Training workshop | National Level awareness – Puttalam District | In Field | 04-07-16 | Marine Unit | Marine Unit | 54 | Y | English |  |
|  | National Level awareness – Jaffna District | In Field | 05-09-16 | Marine Unit | Marine Unit | 50 | Y | English |  |
|  | National Level awareness – Killinochchi District | In Field | 06-09-16 | Marine Unit | Marine Unit | 27 | Y | English |  |
|  | National Level awareness – Mannar District | In Field | 06-09-16 | Marine Unit | Marine Unit | 29 | Y | English |  |
| LK 4 |
| National project partners | Review of ongoing activities and planning meeting | DWC | 1 July 2016 | National Facilitator | NF/ DWC | 11 | Minutes available | English | 1 July 16 |
| National Steering Committee meeting | National Steering Committee meeting | DWC | 28 July 2016 | National Facilitator | NF/ DWC | 30 | Minutes available | English | 28 July 16 |
| District level meetings | Puttalam District meeting | District Secretariat, Puttalam | 4 July 2016 | District Secretary, Puttalam | DWC & partners | 58 | Minutes available | English | 4 July 2016 |
| District Level Meetings | Jaffna District meeting | District Secretariat, Jaffna | 5 Sep 2016 | District Secretary, Jaffna | DWC & partners | 50 | Minutes available | English | 5 Sep 2016 |
| District Level Meetings | Kilinochchi District meeting | District Secretariat, Kilinochchi | 5 Sep 2016 | District Secretary, Kilinochchi | DWC & partners | 30 | Minutes available | English | 5 Sep 2016 |
| District Level Meetings | Mannar District meeting | District Secretariat, Mannar | 6 Sep 2016 | District Secretary, Mannar | DWC & partners | 32 | Minutes available | English | 6 Sep 2016 |
| Community meetings | Kandakuliya/Kudawa meeting | Sugath’s guest house | 8 Oct 2016 | IUCN | IUCN | 8 | Discussion notes | English | 8 Oct 2016 |
| Awareness for clergy of Mannar District | Awareness programme for parish priests | Bishops House, Mannar | 17 Oct 2016 | Bishop of Mannar | Diocese of Mannar and IUCN | App 50 parish priests of Mannar District | Discussion notes | English | 17 Oct 2016 |
| Community meetings | Arippu | Arippu church | 19 Nov 2016 | IUCN | IUCN | 15 | Discussion notes | English | 19 Nov 2016 |
| Community meetings | Vidataltivu | Fisheries Society Community centre | 20 Nov 2016 | IUCN | IUCN | 20 | Discussion notes | English | 20 Nov 2016 |
| LK 5 |
| National facilitating committee meeting | Discuss about the mid term review | Wild Life Dept | 10.10.16 | Wild Life dept. | Project team | 8 | N | English/ Sinhala |  |
| Expert group meeting | Discuss about the project activities | NARA | 16.11.16 | NARA management | NARA Management | 3 | N | English/ Sinhala |  |
| National facilitating committee meeting | Discuss about the progress & logistics | Wild Life Dept | 16.11.16 | Wild Life dept. | Wild Life Dept, Sri Lanka | 5 | N | English |  |
| LK 6 |
| LK 7 |
| Meeting with Batik trainee group | Designs for Batik products | Kandakuliya | 19. 08. 2016 | Head of the batik trainee group | Sri Lanka Turtle Conservation Project | 11 | N | Sinhalese |  |
| Meeting with community leader | Inspection of Canal construction | Palliwasath-urei | 19. 08. 2016 | Sri Lanka Turtle Conservation Project | Sri Lanka Turtle conservation Project | 3 | N | Sinhalese |  |
| Meeting with community leader | Inspection of Completion of toilet construction | Soththupitiya | 19. 08. 2016 | Sri Lanka Turtle conservation Project | Sri Lanka Turtle Conservation Project | 3 | N | Sinhalese |  |
| Meeting with the Assistant Director and relevant staff | Awareness programme on Dugong & Sea grass | District Fisheries office, Puttalam | 21. 09. 2016 | Assistant Director, Fisheries | Sri Lanka Turtle Conservation Project | 9 | N | Sinhalese |  |
| Meeting with the Principle and subject related teachers | Awareness programme on Dugong & Sea grass | Nagamaduwa Kanishta Vidyalaya, Vanathavillu | 21. 09. 2016 | Sri Lanka Turtle Conservation Project | Sri Lanka Turtle Conservation Project | 6 | N | Sinhalese |  |
| Meeting with the Principle and subject related teachers | Awareness programme on Dugong & Sea grass | Vijayapura K. vidyalaya, Vanathavillu | 21. 09. 2016 | Sri Lanka Turtle Conservation Project | Sri Lanka Turtle Conservation Project | 5 | N | Sinhalese |  |
| Meeting with Officer in Charge | Awareness programme on Dugong & Sea grass | Sri Lanka Police, Kalpitiya | 21. 09. 2016 | Sri Lanka Turtle conservation Project | Sri Lanka Turtle conservation Project | 5 | N | Sinhalese |  |
| Meeting with community leader | Project progress | Anawasala | 21. 09. 2016 | Sri Lanka Turtle conservation Project | Sri Lanka Turtle conservation Project | 4 | N | Sinhalese |  |
| Meeting with the Principle and subject related teachers | Awareness programme on Dugong | St. Sebastian Sinhala vidyalaya, Kandakuliya | 22. 09. 2016 | Sri Lanka Turtle conservation Project | Sri Lanka Turtle conservation Project | 5 | N | Sinhalese |  |
| Meeting with the Principle and subject related teachers | Dugong & Sea Grass Awareness programme on Dugong & Sea grass | Nirmala- matha Sinhala-maha vidyalaya, Kalpitiya | 22. 09. 2016 | Sri Lanka Turtle conservation Project | Sri Lanka Turtle conservation Project | 4 | N | Sinhalese |  |
| Meeting with the Principle and subject related teachers | Awareness programme on Dugong | Romanu Katholika Sinhala Vidyalaya, Kurinchi-pitiya | 22. 09. 2016 | Sri Lanka Turtle conservation Project | Sri Lanka Turtle conservation Project | 4 | N | Sinhalese |  |
| Meeting with community leader | Project progress | Soththupitiya | 22. 09. 2016 | Sri Lanka Turtle conservation Project | Sri Lanka Turtle Conservation Project | 4 | N | Sinhalese |  |
| Meeting with sewing instructor | Sewing training programme progress | Serakkuliya | 15. 11. 2016 | Sri Lanka Turtle conservation Project | Sri Lanka Turtle Conservation Project | 3 | N | Sinhalese |  |
| Meeting with beneficiaries | Ornamental fish programme | Serakkuliya | 15.11.2016 | Sri Lanka Turtle Conservation Project | Sri Lanka Turtle Conservation Project | 4 | N | Sinhalese |  |
| Meeting with beneficiaries | Progress of Batik training programme | Kandakuliya | 16.11.2016 | Leader of Batik trainee group | Sri Lanka Turtle Conservation Project |  |  |  |  |
| Meeting with community leader | Palliwasathurei | Palliwasath-urei | 16. 11. 2016 | Sri Lanka Turtle Conservation Project | Sri Lanka Turtle Conservation Project. | 3 | N | Sinhalese |  |
| Meeting with community leader | Project progress | Thirikkapall-ama | 22.11.2016 | Sri Lanka Turtle Conservation Project | Sri Lanka Turtle Conservation Project | 4 | N | Sinhalese |  |
| Meeting with beneficiaries | Project progress | Soththupitiya | 29.11.2016 | Community leader | Sri Lanka Turtle Conservation Project | 13 | N | Sinhalese |  |
| Meeting with community leader | Project progress | Palliwasath-urei | 29.11.2016 | Sri Lanka Turtle Conservation Project | Sri Lanka Turtle Conservation Project | 4 | N | Sinhalese |  |
| Meeting with community leader | Project progress | Anawasala | 29.11.2016 | Sri Lanka Turtle Conservation Project | Sri Lanka Turtle Conservation Project | 3 | N | Sinhalese |  |
| Meeting with community leader | Project progress | Kandakuliya | 30.11.2016 | Sri Lanka Turtle Conservation Project | Sri Lanka Turtle Conservation Project | 3 | N | Sinhalese |  |
| LK 8 |
| Project Steering Committee | National Facilitating Committee | IUCN | 1-07-16 | IUCN | NF | 11 | Y | English |  |
|  | National Facilitating committee | DWC | 10-10-16 | Marine unit | Marine unit | 06 | Y | English |  |
|  | National Facilitating committee | DWC | 16-11-16 | Marine unit | Marine unit | 07 | Y | English |  |
| TL 1 |
| Stakeholder meeting (Atauro Isd.) | Project introduction meeting | Atauro community | 4th August 2016 | CI and Atauro Conservation Group and BV | CI and Atauro Conservation Group | 40+ | N |  |  |
| Partner | New project funding for cetacean survey (incl dugong) | Skype | 10 August | CI Hong Kong | CI Hong Kong | 6 | N | English |  |
| Training | WWF Marine turtle workshop | Darwin | 24 to 26 August | WWF Australia | WWF Australia | 30 | N | English |  |
| Stakeholder meeting (Oecuse) | Project introduction and Public awareness campaign | Oecuse community | 24-28th August 2016 | Ministry of Commerce, Industry, and Environ-ment and CI | MCIE and Conservation International | 100+ | N |  |  |
| Training | CSIRO Marine planning workshop | Hotel Timor | 6 to 8 Sept | Ministry of Commerce, Industry, and Environ-ment, & CSIRO | Ministry of Commerce, Industry, and Environ-ment | 20+ | N | English |  |
| Partner | Cetacean Survey meeting | Skype | 16th Sept | CI Timor-Leste | Conser-vation Inter-national | 2 | N | English |  |
| Stakeholder meeting | Public awareness campaign | Timor Plaza and Atauro Island | 21 to 22 Sept | Conser-vation Inter-national | Conser-vation Inter-national | 100+ | N | Tetun-English |  |
| Stakeholder meeting and Training | Sea grass, Turtle and Cetacean monitoring training | Conser-vation Inter-national | 27-28th Sept-2016 | Conser-vation Inter-national | Conser-vation Inter-national | 15+ | N | Tetun-English |  |
| Survey’s Team meeting | Survey question-airre Discussion | Conser-vation Inter-national | 29th Sept-2016 | Conser-vation Inter-national | Conser-vation Inter-national | +15 | N | Tetun |  |
| Field staff and CCG member training | Sea grass, Turtle and Cetacean monitoring | Com (Nino Konis Santana NP | November 2016 | Conser-vation Inter-national | Conser-vation Inter-national | + 20 | N | Tetun |  |
| TL 2 |
| NFC Meeting | 2nd Project NFC Meeting | CRS Conference room Dili | 11 June 2016 | Project coordi-nator | MCIE, Conser-vation Inter-national, Blue Ventures, MAF, | 40+ | Y | Tetun, English | N |
| Workshop | Community based cetacean tourism workshop | Roman Luan offices, Vila Maumeta, Atauro | 12th July | Professor Karen Edyvane/Roman Luan | Roman Luan | 15+ | N | N | N |
| Local consultation meeting | Local consultation meeting | Posto Administrativo, Suku Vila Maumeta,, Atauro | 25th July | Blue Ventures | N/A | 3 | N | NA | N |
| Local consultation meeting | Local consultation meeting | Posto Administrativo, Suku Vila Maumeta,, Atauro | 26th July | Blue Ventures | N/A | 5 | N | NA | N |
| Partner consultation meeting | GEF projects methodology alignment meeting | Ministry of Agriculture and Fisheries | 1st August | Blue Ventures | Blue Ventures/ Ministry of Agri-culture and Fisheries | 4 | N | NA | N |
| Local consultation meeting/ workshop | Blue Ventures community conservation workshop | Barry’s Place, Suku Beloi, Atauro | 4th August | Blue Ventures | Blue Ventures | 12 | N | NA | N |
| Government Meeting | Community based tourism meeting | Ministry of Tourism | 15, August | Blue Ventures / Karen Edyvane | Blue Ventures, Karen Edyvane | 4 | N | English | N |
| Government meeting | Zeesm Seed Fund | Zeesm conference room Dili | 17, August | Zeesm | Zeesm | 20 | N | Tetun, English | N |
| National workshop | Sustainable Ocean Initiative national workshop | Hotel Timor, Dili | 6th, 7th, 8th Sept | Ministry of Commerce, Industry and Environ-ment | Ministry of Com-merce, Industry and Environ-ment/ CSIRO | 50+ | Y | English/ Tetun | N |
| Local Consultation meeting | 2016 Atauro Marine and Terrestrial Rapid Assessment results presentation | Roman Luan offices, Vila Maumeta, Atauro | 22nd Sept- | Conser-vation Inter-national | Conser-vation Inter-national/ Ministry of Agri-culture and Fisheries | 20+ | Y | English | NA |
| Training workshop | Seagrass Watch monitoring and mapping training workshop | Conservation International offices, Dili | 27th. 28th Sept | Conser-vation Inter-national | Conser-vation Inter-national/ Ministry of Agri-culture and Fisheries | 15+ | N | NA | N |
| Partner consultation meeting | Partner Catch up with Worldfish | Agora LELI, Dili | 28th Sept | Blue Ventures | Blue Ventures | 2 | N | NA | N |
| Partner Meeting CI | Partner Catch up with CI | Dili, | 20th October | Conser-vation Inter-national, Blue Ventures | Blue Ventures | 2 | N | English | N |
| Inter-national Conference | Inter-national Conference in Emerging Tourism Desti-nations: Challenges and Oppor-tunities | Dili Convention Centre, Dili | 24th, 25th October | Dili Institute of Tech-nology, University of Algarve, Ministry of Arts, Culture and Tourism | Dili Institute of Tech-nology, University of Algarve, Ministry of Arts, Culture and Tourism | 200+ | Y | English/Tetun | NA |
| Workshop | Workshop on supporting community supplement-ary livelihoods in Timor Leste | Orchid Room, Timor Plaza, Dili | 8th, 9th Nov | Worldfish Centre | Worldfish Centre | 20 + | N | English Tetun | N |
| Workshop | Timor-Leste Cetacean Mana-gement Workshop | Conservation Inter-national offices, Dili | 10th Nov | Conser-vation Inter-national/ Ministry of Agriculture and Fisheries | Conser-vation Inter-national/ Ministry of Agri-culture and Fisheries | 15 | N | NA | N |
| Project inception meeting | CI ADB-CTP Phase 2 inception meeting | Barry’s Place, Suku Beloi, Atauro | 29th Nov | Conser-vation Inter-national/ Worldfish Centre | Conser-vation Inter-national/ Worldfish Centre | 25 | N | NA | N |
| TL 3 |
| Stakeholder meeting (Dili) | Public awareness campaign | Media (TVE) Office – Dili | 8th July, 2016 | CEO/ Direc-torate of TVE TL, MCIE and CI | MCIE and Conser-vation Inter-national | 5+ | N | Tetun |  |
| Stakeholder meeting (Dili-Schools) | Public awareness campaign | Sao Miguel College (Dili) | July 2016 | MCIE and Conservation International | MCIE and Conser-vation Inter-national | 100+ | N | Tetun-English |  |
| Stakeholder meeting (Atauro Isd.) | Project introduction meeting | Atauro community | 4th August 2016 | CI and Atauro Conser-vation Group and BV | CI and Atauro Conser-vation Group | 40+ | N |  |  |
| Stakeholder meeting (Oecuse) | Project introduction and Public awareness campaign | Oecuse community | 24-28th August 2016 | Ministry of Commerce, Industry, and Environ-ment and CI | MCIE and Conser-vation Inter-national | 100+ | N |  |  |
| Stakeholder meeting and Training | Sea grass, Turtle and Cetacean monitoring training | Conser-vation Inter-national | 27-28th Sept-2016 | Conservation International | Conser-vation Inter-national | 15+ | N | Tetun-English |  |
| Survey’s Team meeting | Survey questionnaire Discussion | Conser-vation Inter-national | 29th Sept-2016 | Conser-vation Inter-national | Conser-vation Inter-national | +15 | N | Tetun |  |
| Suco’s Council & Community meeting | Workshop & Partici-patory Planning for Sea grass Conser-vation | Vila & Varoana (Atauro Isd) | Dec-2016 | Fisheries & Conser-vation Inter-national | Conser-vation Inter-national | + 100 | N | Tetun |  |
| Suco’s Council & Community meeting | Workshop & Partici-patory Planning for Sea grass Conser-vation | Com (Lautem Munici-pality) | Nov-2016 | Fisheries & Conser-vation Inter-national | Conser-vation Inter-national | + 30 | N | Tetun |  |
| TL 4 |
| Formal meeting | Meeting with Director of TVe Timor Leste | TVeT Studio, Dili |  | TL4 | TL4 | 5 |  | English/ Tetum | Jul |
| Formal/ Public awareness/Fair | National Fair | Dili |  | MCIA, TL4 | MCIA, TL4 | ±2000 |  | Ennglish/Tetum | Jul |
| Formal/ workshop/ meeting | Blue Venture,TL2, TL4, Govern-ment represent-tatives, Local Authorities, NGO and com-munities. | Atauro Island |  | TL2,TL4 | TL2, TL4 | ±15 |  | English/ Tetum | Aug |
| Formal/Workshop/Public awareness | TL5, MCIA, TL4, Com-munities, local Authorities | Oecusi |  | TL5, TL4, MCIA | TL5, TL4, MCIA | ±100 |  | English/ Tetum | Aug |
| Formal/ Workshop | National Capacity Develop-ment Workshop for Timor Leste | Dili |  | MCIA | MCIA | ±60 |  | English/ Tetum | Sept |
| Formal/ workshop | Teresterial and Marine Survey project of Atauro | Dili, Atauro |  | CI | CI | ±100 |  | English/ Tetum | Sept |
| Formal/ Workshop/meeting | Workshop/ Public awareness | Atauro Island |  | TL4, MCIA | TL4, MCIA | ±50 |  | Tetum | Sept |
| Formal/ Workshop/Public Awareness | TL4, MCIA (Director General Enviroment, Director, etc..), local Authorities, Comunities (fisher-men’s) . | Atauro |  | TL4, MCIA | TL4, MCIA | ±60 |  | Tetum | Oct |
| Formal/ stake holder meeting/ workshop | TL4,TL1, CI, Represen-tatives MCIA,MAP (Fisheries), Tourism, etc…), NGO’s. | Com Lautem |  | TL4, TL!, CI | TL4, TL1, CI | ±More then 50 |  | English/ Tetum | Nov |
| National Fair /Public Awareness | TL4, MCIA (Directors, Staffs), other ministries represen-tatives Com-munities local and National | Lospalos |  | TL4, MCIA. | TL4, MCIA | ±More then 20000 people |  | Tetum | Nov |
| Formal/TV adverts for public awareness | TL4, Director of TV Education Timor Leste | Dili |  | TL4 | TL4 | 5 |  | Tetum | Dec |
| TL 5 |
| Inter-national meeting | COP 13 | Cancun, Mexico | 4 -17 Dec 2016 | UNCBD Secret-ariat and Govern-ment of Mexico | UNCBD Secret-ariat and Govern-ment of Mexico |  | CBD website | English |  |
| VU 1 |
| Expert group meeting | Meeting of NFC | VESS Office | 28th October 2016 | Dugong Focal Point / DEPC | Trinison Tari / Christina Shaw | 7 | Y | English | 28th Oct 2016 |
| VU 2 |
| Expert group meeting | Meeting of NFC | VESS Office | 298h October 2016 | Dugong Focal Point / DEPC | Trinison Tari / Christina Shaw | 7 | Y | English | 28th Oct 2016 |
| Project Coordination Team (PCT) |
| Field visit | Johor field visit | Johor, Malaysia | 3 – 5 Nov 2016 | PCT | Project Partners in Malaysia |  | Y (a mission report) | English | 22 Nov 2016 |
| Executive Project Steering Committee Meeting | Second Executive Project Steering Committee Meeting | Kuala Lumpur, Malaysia | 1 – 2 Nov 2016 | PCT | PCT | 12 | Yes | English | 09 Dec 2016 |
| National meeting | National meeting with Malaysia Project Partners | Kuala Lumpur, Malaysia | 31 Oct 2016 | PCT | PCT | 17 | Yes (two missions reports) | English | 21 and 22 Nov 2016 |
| Fundraising meeting | Meeting to explore fundraising collabor-ation | Kuala Lumpur, Malaysia | 30 Oct 2016 | PCT | PCT | 4 | Yes (a mission report) | English | 21 Nov 2016 |
| Technical catch-up | Technical catch-up with the Dugong MoU Secretariat | Kuala Lumpur, Malaysia | 30 Oct 2016 | PCT | PCT | 4 | Yes (a mission report) | English | 21 Nov 2016 |
| National meeting | National Meeting with Indonesia Project Partners | Jakarta, Indonesia | 17 – 18 Oct 2016 | PCT |  |  | N |  |  |

APPENDIX 2 – SECTION 4.4 LIST OF MEETINGS PARTICIPANTS

| No. | Name of participant | Nationality |
| --- | --- | --- |
| ID 1 |
| 1 | Andi Rusandi | Indonesian |
| 2 | Syamsul B. Lubis | Indonesian |
| 3 | Firdaus Agung | Indonesian |
| 4 | Suraji | Indonesian |
| 5 | Mudatsir | Indonesian |
| 6 | Erina Nelly | Indonesian |
| 7 | Ahmad Sofiullah | Indonesian |
| 8 | Yudha Miasto | Indonesian |
| 9 | Rian Puspita Sari | Indonesian |
| 10 | Dharmadi | Indonesian |
| 11 | Marina Monintja | Indonesian |
| 12 | Syifa Annisa | Indonesian |
| 13 | Abdul Karim | Indonesian |
| 14 | Anita Kusumawati | Indonesian |
| 15 | Niken | Indonesian |
| 18 | Agustin Rustam | Indonesian |
| 19 | Wawan Ridwan | Indonesian |
| 20 | Veda Santiadji | Indonesian |
| 21 | Dwi Suprapti | Indonesian |
| 22 | Yoppy Endano | Indonesian |
| 23 | Casandra Tania | Indonesian |
| 24 | Wawan Ridwan | Indonesian |
| 25 | Wawan Kiswara | Indonesian |
| 26 | Sekar Mira | Indonesian |
| 27 | Adriani Sunuddin | Indonesian |
| 28 | Juraij Bawazier | Indonesian |
| 29 | Fitriyah Anggraeni | Indonesian |
| 30 | Deny Noviana | Indonesian |
| 31 | Huda Shalahudin Darusman | Indonesian |
| 32 | Sari Novita | Indonesian |
| 33 | Indriatmoko | Indonesian |
| 34 | Muta A. Khalifa | Indonesian |
| 35 | Fitty Machmudah | Indonesian |
| 36 | Gatot Winarso | Indonesian |
| 37 | Atit Wistati | Indonesian |
| 38 | Wenni Wulansari | Indonesian |
| 39 | Rizal Rifai | Indonesian |
| 40 | Alief Farid | Indonesian |
| 41 | Haryo Indrajaya | Indonesian |
| 42 | Rizal Rifai | Indonesian |
| 43 | Haryo Indrajaya | Indonesian |
| 44 | Maya Bankova | Non Indonesian |
| 45 | Nicholas Pilcher | Non Indonesian |
| 46 | Donna Kwan | Non Indonesian |
| ID 2 |
| 1 | Syamsul B. Lubis | Indonesian |
| 2 | Suraji | Indonesian |
| 3 | Yudha Miasto | Indonesian |
| 4 | Erina Nelly | Indonesian |
| 5 | Marina Monintja | Indonesian |
| 6 | Syifa Annisa | Indonesian |
| 7 | Rian Puspita Sari | Indonesian |
| 8 | Mudatsir | Indonesian |
| 9 | Ahmad Sofiullah | Indonesian |
| 10 | Adi Susilo | Indonesian |
| 11 | Veda Santiadji | Indonesian |
| 12 | Dwi Suprapti | Indonesian |
| 13 | Casandra Tania | Indonesian |
| 14 | Yoppy Endano | Indonesian |
| 15 | Wawan Kiswara | Indonesian |
| 16 | Rahmat Nurdin | Indonesian |
| 17 | Sekar Mira | Indonesian |
| 18 | Sam Wouthuyzen | Indonesian |
| 19 | Udhi | Indonesian |
| 20 | Adriani Sunuddin | Indonesian |
| 21 | Juraij Bawazier | Indonesian |
| 22 | Fitriyah Anggraeni | Indonesian |
| 23 | Andreas Hutahaean | Indonesian |
| 24 | Agustin Rustam | Indonesian |
| 25 | Muta Ali Khalifa | Indonesian |
| 26 | Ngurah Wiadnyana | Indonesian |
| 27 | Dharmadi | Indonesian |
| 28 | Dewi Striani | Indonesian |
| 29 | Dwi Ario Cipto Handono | Indonesian |
| 30 | Emilia Bassar | Indonesian |
| 31 | Zia Ulhaq | Indonesian |
| 32 | Heri Daulay | Indonesian |
| MG 1 |
| 1 | Cecile Fattebert, BV | Swiss |
| 2 | Kevin Chambon, BV | French |
| 3 | Jean-Berthieu Nomenjanahary, BV | Malagasy |
| 4 | Abdou Bin Julien Felix, BV | Malagasy |
| 5 | Toalidy, BV | Malagasy |
| 6 | Charles Andrianaivojaona, Consultant BV | Malagasy |
| 7 | Hery , DR-EEF Melaky | Malagasy |
| 8 | Gaetan Evariste, DR-RHP Melaky | Malagasy |
| 9 | Jantie, CSP Melaky | Malagasy |
| 10 | Romule, VM Representative Nosy Lava | Malagasy |
| 11 | Marie-Hélène, VM Representative Nosy Lava | Malagasy |
| 12 | Kaposy, VM Representative Nosy Lava | Malagasy |
| 13 | Fishers Nosy Lava | Malagasy |
| 14 | Robustin, VM Representative Nosy Maroantaly | Malagasy |
| 15 | Gervais, VM Representative Nosy Maroantaly | Malagasy |
| 16 | Dada Fleur, VM Rep Nosy Maroantaly | Malagasy |
| 17 | Fishers Nosy Maroantaly | Malagasy |
| 18 | Zazah, VM Rep Ampandikoara | Malagasy |
| 19 | Bisou, VM Rep Ampandikoara | Malagasy |
| 20 | Fishers Ampandikoara | Malagasy |
| 21 | Lidon, VM Rep Beloba | Malagasy |
| 22 | Fahita, VM Rep Beloba | Malagasy |
| 23 | Fishers Beloba | Malagasy |
| 24 | Tsevilimana, VM Rep Manombo | Malagasy |
| 25 | Mahatsiaro, VM Rep Manombo | Malagasy |
| 26 | Andreneha, VM Rep Manombo | Malagasy |
| 27 | Tsaramisy, VM Rep Manombo | Malagasy |
| 28 | Fishers Manombo | Malagasy |
| 29 | Keita, VM Rep Nosy Marify | Malagasy |
| 30 | Haja Aristide, VM Rep Nosy Marify | Malagasy |
| 31 | Peliny, VM Rep Nosy Marify | Malagasy |
| 32 | Fishers Nosy Marify | Malagasy |
| 35 | Covin, VM Rep Nosy Abohazo | Malagasy |
| 36 | Filgence,VM Rep Nosy Abohazo | Malagasy |
| 37 | Fishers Nosy Abohazo | Malagasy |
| 38 | Fishers of Nosy Manandra | Malagasy |
| 39 | Boto Robert VM Rep Ampasimandroro | Malagasy |
| 40 | Kina, VM Rep Ampasimandroro | Malagasy |
| 41 | Benoît Bonald, VM Rep Ampasimandroro | Malagasy |
| 42 | Elisa, VM Rep Ampasimandroro | Malagasy |
| 43 | Fishers Ampasimandroro | Malagasy |
| 44 | Hervé, VM Rep Andranovoribe Namela | Malagasy |
| 45 | Paul, VM Rep Ambanin’ni Anglais Namela | Malagasy |
| 46 | Zakany Marcellin, VM Rep Ambalahonko Namela | Malagasy |
| 47 | Malama, VM Rep Ambalahonko Namela | Malagasy |
| 48 | Saba, VM Rep Ambalahonko Namela | Malagasy |
| 49 | Fishers Namela | Malagasy |
| 50 | Jean-Baptiste Zamba, RepVM Nosy Andrano-Mangily | Malagasy |
| 51 | Tovo RepVM Nosy Andrano-Mangily | Malagasy |
| 52 | Fishers Nosy Andrano-Mangily | Malagasy |
| 53 | Zafisoa, VM Rep Soahany | Malagasy |
| 54 | Rufin, VM Rep Soahany | Malagasy |
| 55 | Naina, VM Rep Soahany | Malagasy |
| 56 | Kakany, VM Rep Soahany | Malagasy |
| 57 | Fishers Soahany | Malagasy |
| MG 2 |
| 1 | Adrian Levrel | French | Blue Ventures |
| 2 | Ahmed Ben Youssouf | Malagasy | LMMA Community Member |
| 3 | Albert Tombo | Malagasy | LMMA Community Member |
| 4 | Amoza Baraka | Malagasy | LMMA Community Member |
| 5 | Angela Varisoa | Malagasy | LMMA Community Member |
| 6 | Antonjara Moussa | Malagasy | LMMA Community Member |
| 7 | Athouman Tomboravo | Malagasy | LMMA Community Member |
| 8 | Augustin Randrianasolo | Malagasy | LMMA Community Member |
| 9 | Augustine Tsara | Malagasy | LMMA Community Member |
| 10 | Bakarizafy Hervé | Malagasy | MNP Nosy Hara |
| 11 | Bernardin Raphael | Malagasy | LMMA Community Member |
| 12 | Bernardine Ramanamiary | Malagasy | DELC |
| 13 | Clément Mercia | Malagasy | LMMA Community Member |
| 14 | Dominique Voca | Malagasy | SAGE |
| 15 | Edmond Ramadany | Malagasy | LMMA Community Member |
| 16 | Emmanuel Jaoravoana | Malagasy | LMMA Community Member |
| 17 | Estephania | Malagasy | LMMA Community Member |
| 18 | Etienne Rakotonirina | Malagasy | LMMA Community Member |
| 19 | Eugène Matanjaka | Malagasy | LMMA Community Member |
| 20 | Fanony | Malagasy | LMMA Community Member |
| 21 | Félicien Pierre | Malagasy | LMMA Community Member |
| 22 | Félix Randrianasolo | Malagasy | LMMA Community Member |
| 23 | Fenonirina Rakotoarisoa | Malagasy | LMMA Community Member |
| 24 | Géneviève | Malagasy | LMMA Community Member |
| 25 | Georgette Rasoatsara | Malagasy | LMMA Community Member |
| 26 | Gisèle Soa | Malagasy | LMMA Community Member |
| 27 | Grégoire Masizara Famoeza | Malagasy | LMMA Community Member |
| 28 | Guy Célestin Rakotovao | Malagasy | LMMA Community Member |
| 29 | Hasimbola Razafimahefa | Malagasy | GIZ |
| 30 | Heritiana Rakotomalala | Malagasy | WWF |
| 31 | Houssen | Malagasy | LMMA Community Member |
| 32 | Hubert Rakotondrasoa | Malagasy | LMMA Community Member |
| 33 | Ifandeza Miseza | Malagasy | LMMA Community Member |
| 34 | Ignace Vandry | Malagasy | LMMA Community Member |
| 35 | Ihando Andrianjafy | Malagasy | DREEF BOENY |
| 36 | Isdine Andriamalaza | Malagasy | LMMA Community Member |
| 37 | Jaolisy Tolizara | Malagasy | LMMA Community Member |
| 38 | Jaomahazaka | Malagasy | LMMA Community Member |
| 39 | Jaoravo | Malagasy | LMMA Community Member |
| 40 | Jaosoa | Malagasy | LMMA Community Member |
| 41 | Jean Baptiste Zavatra | Malagasy | MNP Sahamalaza |
| 42 | Jery Léoness Raminosoa | Malagasy | Direction regionale du tourisme |
| 43 | Jinoro | Malagasy | LMMA Community Member |
| 44 | Jocelyn Eric Alson | Malagasy | LMMA Community Member |
| 45 | Justin Kinkou | Malagasy | LMMA Community Member |
| 46 | Lezava Guy Tiandraza | Malagasy | LMMA Community Member |
| 47 | Lidwia Rasoanandrasana | Malagasy | LMMA Community Member |
| 48 | Mamy Arthur | Malagasy | LMMA Community Member |
| 49 | Mamy Tiana Rakotonirina | Malagasy | GIZ |
| 50 | Maoulide Abdallah | Malagasy | LMMA Community Member |
| 51 | Marcelin Sanosy | Malagasy | LMMA Community Member |
| 52 | Michel Razafy | Malagasy | LMMA Community Member |
| 53 | Nantenaina Tahiry Andriamalala | Malagasy | PHE |
| 54 | Nicholas | Malagasy | LMMA Community Member |
| 55 | Noel Raymond Avilaza | Malagasy | LMMA Community Member |
| 56 | Ralison Voahangy Aimée | Malagasy | DREEF SOFIA |
| 57 | Raymond Isaia | Malagasy | COSAP Sahamalaza |
| 58 | Razafiarison | Malagasy | LMMA Community Member |
| 59 | Richard Adrien | Malagasy | LMMA Community Member |
| 60 | Rosine Hantasoa Kazy | Malagasy | CIRHP Nosy Be |
| 61 | Said Boana | Malagasy | LMMA Community Member |
| 62 | Saidou | Malagasy | LMMA Community Member |
| 63 | Santisy A.Andriamiravo | Malagasy | WCS |
| 64 | Solofo Andry Randriamanantena | Malagasy | LMMA Community Member |
| 65 | Sylvie Raharimalala | Malagasy | DRRHP Diana |
| 66 | Tahina Andranady Ralaifanasina | Malagasy | C3 |
| 67 | Tahiry Andrianjafimanana | Malagasy | C3 |
| 68 | Tinanty | Malagasy | LMMA Community Member |
| 69 | Tombohasy | Malagasy | LMMA Community Member |
| 70 | Tsiferana Rafaliarimanana | Malagasy | MIHARI |
| 71 | Vatosoa Rakotondrazafy | Malagasy | MIHARI |
| 72 | Velondraza | Malagasy | LMMA Community Member |
| 73 | Velonjara Philgence | Malagasy | LMMA Community Member |
| 74 | Yacinthe Razafimandimby | Malagasy | CI |
| 75 | Zeze Barthelemy | Malagasy | LMMA Community Member |
| 76 | Sebane Ben Said | Malagasy | Communauté Marotaolana |
| 77 | Levelo | Malagasy | Communauté Marotaolana |
| 78 | Antila | Malagasy | Communauté Marotaolana |
| 79 | Tsaramanana | Malagasy | Communauté Marotaolana |
| 80 | Eloi | Malagasy | Communauté Marotaolana |
| 81 | Paly Alimidy | Malagasy | Communauté Marotaolana |
| 82 | Sidiny | Malagasy | Communauté Marotaolana |
| 83 | Hadje | Malagasy | Communauté Marotaolana |
| 84 | Tsarahita | Malagasy | Communauté Marotaolana |
| 85 | Zokintonga | Malagasy | Communauté Marotaolana |
| 86 | Bertran | Malagasy | Communauté Marotaolana |
| 87 | Lemainty | Malagasy | Communauté Marotaolana |
| 88 | Désiré | Malagasy | Communauté Marotaolana |
| 89 | Patric | Malagasy | Communauté Marotaolana |
| 90 | Aliphane | Malagasy | Communauté Marotaolana |
| 91 | Fitariha | Malagasy | Communauté Fongony |
| 92 | Zilio | Malagasy | Communauté Fongony |
| 93 | Jocellin | Malagasy | Communauté Fongony |
| 94 | Tepera | Malagasy | Communauté Fongony |
| 95 | Dada | Malagasy | Communauté Fongony |
| 96 | Mbodiny | Malagasy | Communauté Fongony |
| 97 | Rastany | Malagasy | Communauté Fongony |
| 98 | Dodona | Malagasy | Communauté Fongony |
| 99 | Zafizara | Malagasy | Communauté Fongony |
| 100 | Ibrahim | Malagasy | Communauté Ambalahonko |
| 101 | Sily | Malagasy | Communauté Ambalahonko |
| 102 | Solo | Malagasy | Communauté Ambalahonko |
| 103 | Zezara | Malagasy | Communauté Ambalahonko |
| 104 | Velonozy | Malagasy | Communauté Ambalahonko |
| 105 | Flobert | Malagasy | Communauté Ambalahonko |
| 106 | Jean | Malagasy | Communauté Ambalahonko |
| 107 | Sameline | Malagasy | Communauté Ambalahonko |
| 108 | Sylvain | Malagasy | Communauté Nosy Lana |
| 109 | Aladine | Malagasy | Communauté Nosy Lana |
| 110 | Jolie | Malagasy | Communauté Nosy Lana |
| 111 | Fabie | Malagasy | Communauté Nosy Lana |
| 112 | Saosaony | Malagasy | Communauté Nosy Lana |
| 113 | Dominique | Malagasy | Communauté Nosy Lana |
| 114 | Lepere | Malagasy | Communauté Nosy Lana |
| 115 | Manjé | Malagasy | Communauté Nosy Lana |
| 116 | Arabo | Malagasy | Union des Fédérations des pêcheurs |
| 117 | Jean fernand | Malagasy | Fédérations des pêcheurs |
| 118 | Houssen | Malagasy | Communauté Ankazomborona |
| 119 | Christian | Malagasy | Fédérations des pêcheurs |
| 120 | Manafo | Malagasy | Fédérations des pêcheurs |
| 121 | Delor | Malagasy | Communauté Ankazomborona |
| 122 | Antida | Malagasy | Fédérations des pêcheurs |
| 123 | Mena | Malagasy | Fédérations des pêcheurs |
| 124 | Ahmed | Malagasy | Communauté Ankazomborona |
| 125 | Serany | Malagasy | Communauté Ankazomborona |
| 126 | Nourdine | Malagasy | Communauté Ankazomborona |
| 127 | Paul be | Malagasy | Communauté Ankazomborona |
| 128 | Jean louis | Malagasy | Fédérations des pêcheurs |
| 129 | Chriso | Malagasy | Fédérations des pêcheurs |
| 130 | Adany | Malagasy | Communauté Ankigny |
| 131 | Camardine | Malagasy | Communauté Ankigny |
| 132 | Jean chris | Malagasy | Communauté Ankigny |
| 133 | Jaovita | Malagasy | Fédérations des pêcheurs |
| 134 | Baban’i houssen | Malagasy | Communuaté Ankigny |
| 135 | Sebastien | Malagasy | Fédérations des pêcheurs |
| 136 | Mami | Malagasy | Fédérations des pêcheurs |
| 137 | Bonary | Malagasy | Communauté Antsahampano |
| 138 | Bera | Malagasy | Communauté Antsahampano |
| 139 | Atoumani | Malagasy | Communauté Antsahampano |
| 140 | Bekamisy arnaud | Malagasy | Communauté Antsahampano |
| 141 | Herman | Malagasy | Communauté Antsahampano |
| 142 | Dimbimanarina donald | Malagasy | Communauté Antsahampano |
| 143 | Deric | Malagasy | Communauté Antsahampano |
| 144 | Bera | Malagasy | Communauté Antsahampano |
| 145 | Jaosoa jean fridolin | Malagasy | Communauté Antsahampano |
| 146 | Jaotombo | Malagasy | Communauté Antsahampano |
| 147 | Felix | Malagasy | Communauté Antsahampano |
| 148 | Betombo | Malagasy | Communauté Antsahampano |
| 149 | Arona | Malagasy | Communauté Antsahampano |
| 150 | Nico | Malagasy | Communauté Antsahampano |
| 151 | Olivier | Malagasy | Communauté Antsahampano |
| 152 | Jacqueline | Malagasy | Communauté Ankigny |
| 153 | Jacquot | Malagasy | Communauté Ankigny |
| 154 | Tino | Malagasy | Communauté Ankigny |
| 155 | Tomboravo | Malagasy | Communauté Ankigny |
| 156 | Adanoro | Malagasy | Communauté Ankigny |
| 157 | Kamar | Malagasy | Communauté Ankigny |
| 158 | Sambo | Malagasy | Communauté Ankigny |
| 159 | Roméo | Malagasy | Communauté Ankigny |
| 160 | Anicet | Malagasy | Communauté Ankigny |
| 161 | Tombozafy | Malagasy | Communauté Ankigny |
| 162 | Georges jaosara | Malagasy | Communauté Ankigny |
| 163 | Pierrot | Malagasy | Communauté Nosy faly |
| 164 | Tonga | Malagasy | Communauté Nosy faly |
| 165 | Avizara | Malagasy | Communauté Nosy faly |
| 166 | Zafy | Malagasy | Communauté Nosy faly |
| 167 | Jean Dano | Malagasy | Communauté Nosy faly |
| 168 | Nico | Malagasy | Communauté Nosy faly |
| 169 | Francis | Malagasy | Communauté Nosy faly |
| 170 | Marcellia | Malagasy | Communauté Nosy faly |
| 171 | Edmon | Malagasy | Communauté Nosy faly |
| 172 | Jean jacques | Malagasy | Communauté Nosy faly |
| 173 | Jaovita | Malagasy | Communauté Nosy faly |
| 174 | Tsila | Malagasy | Communauté Nosy faly |
| 175 | Faralahy | Malagasy | Communauté Nosy faly |
| 176 | Joariziky | Malagasy | Communauté Nosy faly |
| 177 | Dino | Malagasy | Communauté Nosy faly |
| 178 | Ahmed salimo | Malagasy | Communauté Antsohimbondrona |
| 179 | Tombo | Malagasy | Communauté Antsohimbondrona |
| 180 | Kassimo | Malagasy | Communauté Antsohimbondrona |
| 181 | Franco | Malagasy | Communauté Antsohimbondrona |
| 182 | Kajy | Malagasy | Communauté Antsohimbondrona |
| 183 | Sabo | Malagasy | Communauté Antsohimbondrona |
| 184 | Roméo | Malagasy | Communauté Antsohimbondrona |
| 185 | Fatouma | Malagasy | Communauté Antsohimbondrona |
| 186 | Tino | Malagasy | Communauté Antsohimbondrona |
| 187 | Meva | Malagasy | Communauté Antsohimbondrona |
| 188 | Mananjara | Malagasy | Communauté Antsohimbondrona |
| 189 | Befanogny | Malagasy | Communauté Antsohimbondrona |
| 190 | Beanjara | Malagasy | Communauté Antsohimbondrona |
| 191 | Benefice | Malagasy | Communauté Antsohimbondrona |
| 192 | Ludo | Malagasy | Communauté Antsohimbondrona |
| 193 | Veve | Malagasy | Communauté Ampasindava |
| 194 | Jaotombo Sosten | Malagasy | Communauté Ampasindava |
| 195 | Totozafy eric | Malagasy | Communauté Ampasindava |
| 196 | Maharavo | Malagasy | Communauté Ampasindava |
| 197 | Berto | Malagasy | Communauté Ampasindava |
| 198 | Tsitondro | Malagasy | Communauté Ampasindava |
| 199 | Issouf | Malagasy | Communauté Ampasindava |
| 200 | Jean robert | Malagasy | Communauté Ampasindava |
| 201 | Toto | Malagasy | Communauté Ampasindava |
| 202 | mamodo | Malagasy | Communauté Ampasindava |
| 203 | Fenozandry clovis | Malagasy | Communauté Ampasindava |
| 204 | Tsimagneky | Malagasy | Communauté Ampasindava |
| 205 | Mevalaza frederic | Malagasy | Communauté Ampasindava |
| MG 3 |
|  | RANDRIANJAFIMANANA Nambinintsoa Tahiry, Senior Programme Officer RALAIFANASINA Andrianady Tahina, Programme Officer Database JAOZANDRY, CLP President BERAVO, CLP Eloah Joseph, Conservation Ambassador Moussa Bakar, Conservation Ambassador VOASAOTRA André, Conservation Ambassador JAOTIANA DAMA Passo, Conservation Ambassador BEANJARA, Conservation Ambassador | Malagasy |
|  | RALAIFANASINA Andrianady Tahina, Programme Officer JACQUI Adama, Conservation Ambassador | Malagasy |
|  | Lalarisoa Rakotoarimino, PC Mihary Ramiandrisoa, SPO Anwar Salimo, PO Anatoli Velondia, PO Women from FIVEPANOHA | Malagasy |
|  | Lalarisoa Rakotoarimino, PC Mihary Ramiandrisoa, SPO Anwar Salimo, PO Anatoli Velondia, PO CLP members from Andranomavo: Zaramasy & Rajoel Manjaka Hova CLP from Akingameloka: Mahatoly be & Randria CLP from Bobatolagna: Memena & Pierre Felicien CLP from Ampasindava: Charlie Rakotonirina, Fatoma Therese & Samy William | Malagasy |
|  | Anwar Salimo, PO Anatoli Velondia, PO 13 CLP President of the Lalandaka village | Malagasy |
|  | Mihary Ramiandrisoa, SPO Patrice, Student CLPs from Andranomavo : Razafy Rajoel; Beanjara Jean; Damo, Zaramasy; Tombohasy, 0341627403 CLPs of Ambararata : Betombo Tomboanjara Aymar, 0349761887 Marcel Mila Fasimila Be Peter | Malagasy |
| MG 4 |
| Meeting for establishing the governance structure of Mahadera on 10September 2016 |
| 01 | Razafimamonjy Nestor | Madagascar |
| 02 | Honorine | Madagascar |
| 03 | Tongaravo | Madagascar |
| 04 | Tobozara | Madagascar |
| 05 | Rémi André | Madagascar |
| 06 | Mohamed | Madagascar |
| 07 | Joslin | Madagascar |
| 08 | Fetin’I Vahoaka | Madagascar |
| 09 | Androse | Madagascar |
| 10 | Fidele | Madagascar |
| 11 | Jaomamory Jean Claude | Madagascar |
| 12 | Tombozara | Madagascar |
| 13 | Tongazara | Madagascar |
| 14 | Jaotody | Madagascar |
| 15 | Theophile | Madagascar |
| 16 | Jaomanompo | Madagascar |
| 17 | Tongalaza | Madagascar |
| 18 | Marie | Madagascar |
| 19 | Raharimalala Marie Aline | Madagascar |
| 20 | Celine | Madagascar |
| 21 | Marisika | Madagascar |
| 22 | Nosy | Madagascar |
| 23 | Tianjara | Madagascar |
| 24 | Samalazara Lucie Malaka | Madagascar |
| 25 | Tongaravo | Madagascar |
| 26 | Avizara | Madagascar |
| 27 | Etienne | Madagascar |
| 28 | Jaomarisika | Madagascar |
| 29 | Abdou | Madagascar |
| 30 | Assimo | Madagascar |
| 31 | Franco | Madagascar |
| 32 | Jaoviloma | Madagascar |
| 33 | Nirina | Madagascar |
| 34 | Soaline | Madagascar |
| 35 | Jaotiana | Madagascar |
| 36 | Flavien | Madagascar |
| 37 | Narce Florent | Madagascar |
| 38 | Florence | Madagascar |
| 39 | Zafijery | Madagascar |
| 40 | Josiane | Madagascar |
| 41 | Solo Jean | Madagascar |
| 42 | Jaozandry | Madagascar |
| 43 | Justin | Madagascar |
| 44 | Jeannot David | Madagascar |
| 45 | Jean Noel | Madagascar |
| 46 | Tombozara Jules | Madagascar |
| 47 | Patrice | Madagascar |
| 48 | Christian | Madagascar |
| 49 | Rasta | Madagascar |
| 50 | Albert | Madagascar |
| 51 | Venance | Madagascar |
| 53 | Chamsdine | Madagascar |
| 54 | Gaston Norbert | Madagascar |
| 55 | Geda | Madagascar |
| 56 | Randrianarivelo Urbain Joeal | Madagascar |
| 57 | Isaia Raymond | Madagascar |
| Meeting for establishing the governance structure of Ambalabao on 10September 2016 |
| 01 | Dily Jaovola | Madagascar |
| 02 | Fidizara Nestor | Madagascar |
| 03 | Razanatsara Hortence | Madagascar |
| 04 | Johnson William | Madagascar |
| 05 | Akram | Madagascar |
| 06 | Betombo Robin | Madagascar |
| 07 | Robert | Madagascar |
| 08 | Flave | Madagascar |
| 09 | François | Madagascar |
| 10 | Live | Madagascar |
| 11 | Rabezara | Madagascar |
| 12 | Rapanoela Didi Léon | Madagascar |
| 13 | Robera | Madagascar |
| 14 | Narcis | Madagascar |
| 15 | Rasoamanosoka | Madagascar |
| 16 | Soa | Madagascar |
| 17 | Rasoanivo | Madagascar |
| 18 | Vonimasy | Madagascar |
| 19 | Zania | Madagascar |
| 20 | Mariane | Madagascar |
| 21 | Jenette | Madagascar |
| 22 | Manombo | Madagascar |
| 23 | Soamanidry | Madagascar |
| 24 | Diamary | Madagascar |
| 25 | Blandine | Madagascar |
| 26 | Olivier | Madagascar |
| 27 | Jao Marcel | Madagascar |
| 28 | Randria Norbert | Madagascar |
| First meeting for preparing the first edition of the dugong festivalat Berafia on 17September 2016 |
| 01 | Abdala | Madagascar |
| 02 | Rasilien | Madagascar |
| 03 | Andrianera | Madagascar |
| 04 | Labeny | Madagascar |
| 05 | Todiarivo | Madagascar |
| 06 | Hamba | Madagascar |
| 07 | Julienne | Madagascar |
| 08 | Marcelline | Madagascar |
| 09 | Soavina | Madagascar |
| 10 | Vongizara | Madagascar |
| 11 | Anteonjara | Madagascar |
| 12 | Celestine | Madagascar |
| 13 | Latifa | Madagascar |
| 14 | Adija | Madagascar |
| 15 | Landy | Madagascar |
| 16 | Salimonajimo | Madagascar |
| 17 | Pascal | Madagascar |
| 18 | Jacquelin | Madagascar |
| 19 | Tsiavic | Madagascar |
| 20 | Damien | Madagascar |
| 21 | Manohizara Clement | Madagascar |
| 22 | Djailane Bruno Abdou | Madagascar |
| 23 | Tolindraza Rom Georgino | Madagascar |
| 24 | Mahamoudou | Madagascar |
| 25 | Finjara | Madagascar |
| 26 | Marinosy | Madagascar |
| 27 | Marimina | Madagascar |
| 28 | Jacqueline | Madagascar |
| 29 | Tsontso | Madagascar |
| 30 | Safina | Madagascar |
| 31 | Mbotisoa | Madagascar |
| 32 | Claudine | Madagascar |
| 33 | Soamadamo | Madagascar |
| 34 | Angarena | Madagascar |
| 35 | Laurette | Madagascar |
| 36 | Moana Florine | Madagascar |
| 37 | Meline | Madagascar |
| 38 | Vitasoa | Madagascar |
| 39 | Moana Florine | Madagascar |
| 40 | Soatody | Madagascar |
| 41 | Jaosily | Madagascar |
| 42 | Anandra | Madagascar |
| 43 | Andre | Madagascar |
| 44 | Tsafitsaka Zara | Madagascar |
| 45 | Tombozara | Madagascar |
| 46 | Amiry | Madagascar |
| 47 | Tiazara | Madagascar |
| 48 | Tomboraza | Madagascar |
| 49 | James | Madagascar |
| 50 | Zily | Madagascar |
| 51 | Hada | Madagascar |
| 52 | Manompo | Madagascar |
| 53 | Jaosily | Madagascar |
| 54 | Makavita Bezily | Madagascar |
| 55 | Banono | Madagascar |
| 56 | Saotra | Madagascar |
| 57 | Zafitombo | Madagascar |
| 58 | Tsiantandra | Madagascar |
| 59 | Seizatiana | Madagascar |
| 60 | Zislin | Madagascar |
| 61 | Mananga | Madagascar |
| 62 | Amana | Madagascar |
| 63 | Bezara | Madagascar |
| 64 | Salimo | Madagascar |
| 65 | Randrianarison Jules | Madagascar |
| 66 | Michel | Madagascar |
| 67 | Luc | Madagascar |
| 68 | Veve | Madagascar |
| 69 | Rosy | Madagascar |
| 70 | Velo | Madagascar |
| 71 | Lio | Madagascar |
| 72 | Attomany Aly | Madagascar |
| 73 | Solovita | Madagascar |
| 74 | Jiabiry | Madagascar |
| 75 | Juldas Assan | Madagascar |
| 76 | Tianjara | Madagascar |
| 77 | Donne | Madagascar |
| 78 | Mac Simo | Madagascar |
| 79 | Marchel | Madagascar |
| 80 | Angeline | Madagascar |
| 81 | Zaitony | Madagascar |
| 82 | Robin | Madagascar |
| 83 | Beanjara Betombo | Madagascar |
| 84 | Souf | Madagascar |
| 85 | Misizara | Madagascar |
| 86 | Ampizara | Madagascar |
| 87 | Assany Houssen | Madagascar |
| 88 | Ali | Madagascar |
| 89 | Aboudou | Madagascar |
| 90 | Lusette | Madagascar |
| 91 | Sania | Madagascar |
| 92 | Jacline | Madagascar |
| 93 | Olizette | Madagascar |
| 94 | Nafisa | Madagascar |
| 95 | Roseline | Madagascar |
| 96 | Noeline | Madagascar |
| 97 | Laurance | Madagascar |
| 98 | Rabezafy Camille | Madagascar |
| 99 | Fidizara Nestor | Madagascar |
| 100 | Geda | Madagascar |
| 101 | Bienvenue Alexis | Madagascar |
| 102 | Tomboravo Attomany | Madagascar |
| 103 | Saidou | Madagascar |
| 104 | Tafara Ahiada Beny | Madagascar |
| 105 | Ravondaza Jean Narcisse | Madagascar |
| 106 | Radonarivelo Paulin | Madagascar |
| 107 | Hampy | Madagascar |
| 108 | Tiaraza | Madagascar |
| 109 | Tsiafindra | Madagascar |
| 110 | Bevoay Razaky | Madagascar |
| 111 | Faly Jean Robin | Madagascar |
| 112 | Sambizara Tsiafindra | Madagascar |
| 113 | Anzidane | Madagascar |
| 114 | Antoenjara | Madagascar |
| 115 | Faidaly Aboubakar | Madagascar |
| 116 | Ampizara | Madagascar |
| 117 | Attomany Ahidary | Madagascar |
| 118 | Solovelo Mahavita | Madagascar |
| 119 | Sidy | Madagascar |
| 120 | Ahidar | Madagascar |
| 121 | Aboudou | Madagascar |
| 122 | Jaosengy | Madagascar |
| 123 | Djinoro | Madagascar |
| 124 | Houssen | Madagascar |
| 125 | Hababe | Madagascar |
| 126 | Arson | Madagascar |
| 127 | Jaobe | Madagascar |
| 128 | Will | Madagascar |
| Second meeting for preparing the first edition of the dugong festival at Berafia on 18October 2016 |
| 01 | Rabezafy Camille | Madagascar |
| 02 | Fidizara Nestor | Madagascar |
| 03 | Geda | Madagascar |
| 04 | Manohizara Clement | Madagascar |
| 05 | Raharimalala Zita Fabiola | Madagascar |
| 06 | Tombolaza Jean René | Madagascar |
| 07 | Faidaly | Madagascar |
| 08 | Antoejanra | Madagascar |
| 09 | Attomany Ahidara | Madagascar |
| 10 | Paul Zara | Madagascar |
| 11 | Zafitombo | Madagascar |
| 12 | Tiaraza | Madagascar |
| 13 | Hadabe | Madagascar |
| 14 | Tombozafy | Madagascar |
| 15 | Bienvenue Alexis | Madagascar |
| 16 | Donné | Madagascar |
| 17 | Tianjara | Madagascar |
| 18 | Arsene Frederic | Madagascar |
| 19 | Richard | Madagascar |
| 20 | Moedine Solo | Madagascar |
| 21 | Abdoul Nordien | Madagascar |
| 22 | Pascal | Madagascar |
| 23 | Todiny | Madagascar |
| 24 | Felix | Madagascar |
| 25 | Dino | Madagascar |
| 26 | Fatima Soalehy | Madagascar |
| 27 | Vitzara | Madagascar |
| 28 | Luc | Madagascar |
| 29 | Tsaramanana Céverien | Madagascar |
| 30 | Claude | Madagascar |
| 31 | Zafy Bertin | Madagascar |
| 32 | Marcel | Madagascar |
| 33 | Angelo | Madagascar |
| 34 | Serge | Madagascar |
| 35 | Hamba Zandry | Madagascar |
| 36 | Arsene | Madagascar |
| 37 | Vitasoa | Madagascar |
| 38 | Valerine | Madagascar |
| 39 | Soazafy | Madagascar |
| 40 | Caroline | Madagascar |
| 41 | Laurette | Madagascar |
| 42 | Justine | Madagascar |
| 43 | Saufa | Madagascar |
| 44 | Abiba | Madagascar |
| 45 | Soamanarina Victorine | Madagascar |
| 46 | Zafinoro | Madagascar |
| 47 | Claudine | Madagascar |
| 48 | Siza | Madagascar |
| 49 | Lazany | Madagascar |
| 50 | Farida | Madagascar |
| 51 | Paso | Madagascar |
| 52 | Vero | Madagascar |
| 53 | Mbotizara | Madagascar |
| 54 | Peta | Madagascar |
| 55 | Rozeline | Madagascar |
| 56 | Florette | Madagascar |
| 57 | Amina | Madagascar |
| 58 | Vitasoa | Madagascar |
| 59 | Zafitombo Olivia | Madagascar |
| 60 | Finjara | Madagascar |
| 61 | Maromina | Madagascar |
| 62 | Torine | Madagascar |
| 63 | Zacline | Madagascar |
| 64 | Mbotisoa | Madagascar |
| 65 | Volahita | Madagascar |
| 66 | Marilaza | Madagascar |
| 67 | Angarena | Madagascar |
| 68 | Zanine | Madagascar |
| 69 | Rozaline | Madagascar |
| 70 | Agatte | Madagascar |
| 71 | Ivonne | Madagascar |
| 72 | Sesil | Madagascar |
| 73 | Masilaza | Madagascar |
| 74 | Zafinoro | Madagascar |
| 75 | Salima | Madagascar |
| 76 | Zarameva | Madagascar |
| 77 | Josephine | Madagascar |
| 78 | Tsotso | Madagascar |
| 79 | Marinjafy | Madagascar |
| 80 | Poety | Madagascar |
| 81 | Asiata | Madagascar |
| 82 | Ziline | Madagascar |
| 83 | Lazamary | Madagascar |
| 84 | Françoise | Madagascar |
| 85 | Noeline | Madagascar |
| 86 | Marisana Duela | Madagascar |
| 87 | Saida | Madagascar |
| 88 | Razay | Madagascar |
| 89 | Gline | Madagascar |
| 90 | Soaliza | Madagascar |
| 91 | Raissa | Madagascar |
| 92 | Norozara | Madagascar |
| 93 | Phipine | Madagascar |
| 94 | Ahidar | Madagascar |
| 95 | Tombo Assany | Madagascar |
| 96 | Tomboravo Atomany | Madagascar |
| 97 | Mahamoudou | Madagascar |
| 98 | Seizatiana | Madagascar |
| 99 | Tongazara | Madagascar |
| 100 | Jaosengy | Madagascar |
| 101 | Tombolaza | Madagascar |
| 102 | Soa | Madagascar |
| 103 | Saidou | Madagascar |
| 104 | Antoeny | Madagascar |
| 105 | Hada I | Madagascar |
| 106 | Andrianera | Madagascar |
| 107 | Ahmed | Madagascar |
| 108 | Tsiosa | Madagascar |
| 109 | Velondraza | Madagascar |
| 110 | Jaofasy | Madagascar |
| 111 | Jaohasy | Madagascar |
| 112 | René | Madagascar |
| 113 | Anjara | Madagascar |
| 114 | Tomboravo Atomany | Madagascar |
| 115 | Andre | Madagascar |
| 116 | Zarany | Madagascar |
| 117 | Richard | Madagascar |
| 118 | Henobelle | Madagascar |
| 119 | Jaosiny | Madagascar |
| 120 | Manajara | Madagascar |
| 121 | Anandra | Madagascar |
| 122 | Jaoraza | Madagascar |
| 123 | Bezara | Madagascar |
| 124 | Michel | Madagascar |
| 125 | Juslin | Madagascar |
| 126 | Djalanne Bruno Abdou | Madagascar |
| Local community participating in the first edition of the dugong festival at Berafia on 28-29October 2016 |
| 01 | Rabezafy Camille | Madagascar |
| 02 | Fidizara Nestor | Madagascar |
| 03 | Razanatsara Horthence | Madagascar |
| 04 | Gilbert | Madagascar |
| 05 | Léonida | Madagascar |
| 06 | Nosy | Madagascar |
| 07 | Zafimaro | Madagascar |
| 08 | Ramanirina Justine | Madagascar |
| 09 | Ravaomampionona Justine | Madagascar |
| 10 | Fiamina | Madagascar |
| 11 | Toalifa | Madagascar |
| 12 | Bao Zafihavana | Madagascar |
| 13 | Bevavy | Madagascar |
| 14 | Salima | Madagascar |
| 15 | Asmine | Madagascar |
| 16 | Ciline | Madagascar |
| 17 | Sanadera Eulodie | Madagascar |
| 18 | Rasoa Marie | Madagascar |
| 19 | Roseline | Madagascar |
| 20 | Gnetsany | Madagascar |
| 21 | Soazafy | Madagascar |
| 22 | Sandia | Madagascar |
| 23 | Adijà | Madagascar |
| 24 | Viaviny | Madagascar |
| 25 | Rasoa | Madagascar |
| 26 | Marie Claire | Madagascar |
| 27 | Sirazy | Madagascar |
| 28 | Dette | Madagascar |
| 29 | Fara | Madagascar |
| 30 | Sella | Madagascar |
| 31 | Soa | Madagascar |
| 32 | Soajery | Madagascar |
| 33 | Bemary | Madagascar |
| 34 | Tsarandro | Madagascar |
| 35 | Edwidge | Madagascar |
| 36 | Soazandry | Madagascar |
| 37 | Ravaonoro Roseline | Madagascar |
| 38 | Vanja Marie | Madagascar |
| 39 | Marindraza | Madagascar |
| 40 | Botra Jacquelin | Madagascar |
| 41 | Zafisoa Florine | Madagascar |
| 42 | Mahasosoko | Madagascar |
| 43 | Jaotombo Marcelline | Madagascar |
| 44 | Zakia | Madagascar |
| 45 | Tsaranarana | Madagascar |
| 46 | Mahadimby Nicolas | Madagascar |
| 47 | Rahatsimalandy Mahazaka | Madagascar |
| 48 | Zavatra Jean Baptiste | Madagascar |
| 49 | Rabemilarison Edmond | Madagascar |
| 50 | Rasolomiarina Friedel | Madagascar |
| 51 | Velondia Anatoli Altobeli | Madagascar |
| 52 | Jaosolo | Madagascar |
| 53 | Raherindray Raymond | Madagascar |
| 54 | Paranison Wald Edikoff | Madagascar |
| 55 | Victor Antonio | Madagascar |
| 56 | Randrianambinina | Madagascar |
| 57 | Ramantena Laingo Vivien | Madagascar |
| 58 | Mahavita Besily | Madagascar |
| 59 | Zaky | Madagascar |
| 60 | Zara Elysé | Madagascar |
| 61 | Euphrasie | Madagascar |
| 62 | Sabrina | Madagascar |
| 63 | Ernest | Madagascar |
| 64 | Tizara | Madagascar |
| 65 | Claude | Madagascar |
| 66 | Zafinoro Claudine | Madagascar |
| 67 | Isaia Raymond | Madagascar |
| 68 | Samalazara Lucie Malaka | Madagascar |
| 69 | Ramarozatovo Dina | Madagascar |
| 70 | Rasojarivelo Jean Bosco | Madagascar |
| 71 | Rakotondrazafy Vatosoa | Madagascar |
| 72 | Venance Damascene | Madagascar |
| 73 | Ratsimalandy Mahazaka | Madagascar |
| 74 | Jaosolo dit Jimmy | Madagascar |
| 75 | Fananara | Madagascar |
| 76 | Ginette | Madagascar |
| 77 | Tomboravo Atomany | Madagascar |
| 78 | Mahavitan’i Tombodily | Madagascar |
| 79 | Tsiatandra | Madagascar |
| 80 | Hamba Fidele | Madagascar |
| 81 | Saidou | Madagascar |
| 82 | A Olsen Banguie | Madagascar |
| 83 | Robi Herman | Madagascar |
| 84 | Polizara | Madagascar |
| 85 | Siamy | Madagascar |
| 86 | Aziza | Madagascar |
| 87 | Faidaly | Madagascar |
| 88 | Vony | Madagascar |
| 89 | Tombozafy Roger | Madagascar |
| 90 | Assany | Madagascar |
| 91 | Edson | Madagascar |
| 92 | Richard | Madagascar |
| 93 | Jaosengy | Madagascar |
| 94 | Richard | Madagascar |
| 95 | Vohavy | Madagascar |
| 96 | Tomboravo | Madagascar |
| 97 | Jaozandry | Madagascar |
| 98 | Eric | Madagascar |
| 99 | Léoquatre Mora | Madagascar |
| 100 | Stéphanie | Madagascar |
| 101 | Archille Elia | Madagascar |
| 102 | Phyrose | Madagascar |
| 103 | Folera | Madagascar |
| 104 | Zaramisy Jean Philbert | Madagascar |
| 105 | Randriamizaka Sherina | Madagascar |
| 106 | Anorontsany | Madagascar |
| 107 | Abdallah Rachid | Madagascar |
| 108 | Ampizara Odette | Madagascar |
| 109 | Randriamizaka Alina Anastha | Madagascar |
| 110 | Zozo | Madagascar |
| 111 | Soafeno | Madagascar |
| 112 | Zafitombo | Madagascar |
| 113 | Cnien | Madagascar |
| 114 | Mandigny | Madagascar |
| 115 | Vavitombo | Madagascar |
| 116 | Jaosenga | Madagascar |
| 117 | Clément | Madagascar |
| 118 | André | Madagascar |
| 119 | Mario | Madagascar |
| 120 | Viloma Laza | Madagascar |
| 121 | Beny | Madagascar |
| 122 | Horaza | Madagascar |
| 123 | Soanavony | Madagascar |
| 124 | Solo | Madagascar |
| 125 | Daule | Madagascar |
| 126 | Toutou | Madagascar |
| 127 | Théo | Madagascar |
| 128 | Tombo | Madagascar |
| 129 | Faby | Madagascar |
| 130 | Maurice | Madagascar |
| 131 | Tianjara | Madagascar |
| 132 | Adabe | Madagascar |
| 133 | Balà | Madagascar |
| 134 | Jaomarsel | Madagascar |
| 135 | Nordine | Madagascar |
| 136 | Zaid Aly | Madagascar |
| 137 | Mananjara Christian | Madagascar |
| 138 | Besiny | Madagascar |
| 139 | Erika | Madagascar |
| 140 | Hortensia | Madagascar |
| 141 | Azraf | Madagascar |
| 142 | Lôlô | Madagascar |
| 143 | Soazy | Madagascar |
| 144 | Afosoaky | Madagascar |
| 145 | Nassour Aly | Madagascar |
| 146 | Hambazandry | Madagascar |
| 147 | Sikina | Madagascar |
| 148 | Anicette | Madagascar |
| 149 | Fatoma | Madagascar |
| 150 | Safy | Madagascar |
| 151 | Maurela | Madagascar |
| 152 | Auguste | Madagascar |
| 153 | Amouzia | Madagascar |
| 154 | Tianjafy | Madagascar |
| 155 | Afdine | Madagascar |
| 156 | Chiamsdine | Madagascar |
| 157 | Claudio | Madagascar |
| 158 | Berto | Madagascar |
| 159 | Jaotody | Madagascar |
| 160 | Hamzah | Madagascar |
| 161 | Lamela | Madagascar |
| 162 | Adeline | Madagascar |
| 163 | Filao | Madagascar |
| 164 | Safimoana | Madagascar |
| 165 | Zara | Madagascar |
| 166 | Elise | Madagascar |
| 167 | Vonisolo | Madagascar |
| MG 6 |
| N/A |
| MY 1 |
| 1. | Syed Abdullah Syed Abdul Kadir | Malaysian |
| 2. | Abdul Muntalib Juli | Malaysian |
| 3. | Izarenah Md Repin | Malaysian |
| 4. | Julian Hyde | British |
| 5. | Lau Chai Ming (Edmund) | Malaysian |
| 6. | Nazirul Amin | Malaysian |
| 7. | Louisa Shobini Ponnampalam | Malaysian |
| 8. | Fairul Izmal | Malaysian |
| 9. | Nicolas Pilcher |  |
| 10. | Leela Rajamani | Malaysian |
| 11. | Sim Yee Kwang | Malaysian |
| MY 2 |
| 1 | Syed Abdullah, Mohd Tamimi, Dr Louisa Ponampalan, Dr Leela Rajamani, Julian Hyde, Edmund Lau, Abu Muntalib, Izarenah Md Repin, Dr Nicolas Picher, Mohd Noor, Hemalatha, Fairuz Izmal | Malaysia |
| 2 | Syed Abdullah, Dr Louisa Ponampalan, Fairuz Izmal, Dr Leela Rajamani, Edmund Lau, Abu Muntalib, Izarenah Md Repin, James Bali and Toloy Keriping | Malaysia |
| 3 | Syed Abdullah, Mohd Tamimi, Dr Louisa Ponampalan, Fairuz Izmal, Dr Leela Rajamani, Edmund Lau, Abu Muntalib, Izarenah Md Repin, James Bali and Toloy Keriping | Malaysia |
| 4 | Syed Abdullah, Mohd Tamimi, Dr Louisa Ponampalan, Dr Leela Rajamani, Edmund Lau, Abu Muntalib, Izarenah Md Repin, James Bali, Toloy Keriping. Yuniza, Maya Bankova, Donna Kwan, Duthler Kirk and Nicolas Pilcher | Malaysia and PCT from Abu Dhabi (UAE) |
| MY 3 |
| 1 | Wan Mustaffa bin Wan Din | Malaysian |
|  | Sim Yee Kwang | Malaysian |
|  | Leela Rajamani | Malaysian |
| 2 | Edmund Lau Chai Ming | Malaysian |
|  | Fairul Izmal | Malaysian |
|  | Louisa S.Ponnampalam | Malaysian |
|  | Nicolas Pilcher | British |
|  | Julian Hyde | Malaysian |
|  | Leela Rajamani | Malaysian |
|  | Syed Abdullah bin Syed Abdul Kadir | Malaysian |
| 3 | Wan Mustaffa bin Wan Din | Malaysian |
|  | Sim Yee Kwang | Malaysian |
|  | Leela Rajamani | Malaysian |
|  | Rosita Victor | Malaysian |
| 4 | Abdul Muntalib | Malaysian |
|  | Izarenah bt Mh Repin | Malaysian |
|  | Louisa S.Ponnampalam | Malaysian |
|  | Leela Rajamani | Malaysian |
|  | Syed Abdullah bin Syed Abdul Kadir | Malaysian |
|  | Edmund Lau Chai Ming | Malaysian |
|  | Ng Jol Ern | Malaysian |
|  | James Bali | Malaysian |
| 5 | Maya Bankova-Todorova | Bulgarian |
|  | Mariam | Egyptian |
|  | Kirk | American |
|  | Donna Kwan | Australian |
|  | Abdul Muntalib | Malaysian |
|  | Izarenah bt Mh Repin | Malaysian |
|  | Louisa S.Ponnampalam | Malaysian |
|  | Leela Rajamani | Malaysian |
|  | Syed Abdullah bin Syed Abdul Kadir | Malaysian |
|  | Edmund Lau Chai Ming | Malaysian |
|  | Ng Jol Ern | Malaysian |
|  | James Bali | Malaysian |
|  | Julian Hyde | British |
| 6 | Wan Mustaffa bin Wan Din | Malaysian |
|  | Sim Yee Kwang | Malaysian |
|  | Leela Rajamani | Malaysian |
|  | Norizan Esa | Malaysian |
|  | Ong Ke Shin | Malaysian |
| 7 | Sim Yee Kwang | Malaysian |
|  | Leela Rajamani | Malaysian |
|  | Nurul Farhana Low bt. Abdullah | Malaysian |
|  | Ong Ke Shin | Malaysian |
| MZ 1 |
| 1 | Isabelle Giddy, EWT Project Coordinator | South Africa |
| 2 | Urszula Stankiewicz, BV PHE Support Officer | USA |
| 3 | Leone Massicane, Park Community Liason Officer | Mozambique |
| 4 | Inhassoro District Administrator | Mozambique |
| 5 | Community Members | Mozambique |
| 6 | Ryan Kelley, PSI Country Director | USA |
| 7 | Machila Magic Staff | Mozambican |
| MZ 4 |
| 01 | Isabelle Giddy | South African |
| 02 | Crimildo Zivane | Mozambican |
| 03 | Isabelle Giddy | South African |
| 04 | Crimildo Zivane | Mozambican |
| 05 | Carlos Zivane | Mozambican |
| 06 | Isabelle Giddy | South African |
| 07 | Crimildo Zivane | Mozambican |
| 08 | Carlos Zivane | Mozambican |
| 09 | Manito Nhadave | Mozambican |
| 10 | Faztudo Mazelete | Mozambican |
| 11 | Nelson Zivane | Mozambican |
| 12 | Isabelle Giddy | Mozambican |
| 13 | Crimildo Zivane | Mozambican |
| 14 | Carlos Zivane | Mozambican |
| 15 | Manito Nhadave | Mozambican |
| 16 | Faztudo Mazelete | Mozambican |
| 17 | Nelson Zivane | Mozambican |
| MZ 5 |
|  | Guilhermina Amurane | Mozambique |
|  | Anselmo Gaspar | Mozambique |
|  | Almeida Guissamulo | Mozambique |
|  | Afonsina Fernandes Madondora | Mozambique |
|  | Alexandre Bartolomeu | Mozambique |
|  | Levin Cuinica | Mozambique |
|  | Armando Benzane | Mozambique |
|  | Isabel Manga | Mozambique |
|  | João Domingos Fernandes | Mozambique |
|  | Faztudo Balata | Mozambique |
|  | André Jaime | Mozambique |
|  | António Alípio de Frestas | Mozambique |
|  | Gomes Raul Mafacitela | Mozambique |
|  | Felismina | Mozambique |
|  | Ofélia Musseia | Mozambique |
|  | Norma Samuel Francisco | Mozambique |
|  | Bento Jorge Manga | Mozambique |
|  | Sansão Rafael Chitsuma | Mozambique |
|  | Milton Zacarias Zivane | Mozambique |
|  | Mateus Alberto | Mozambique |
|  | Jaime José Zivane | Mozambique |
|  | Armando Américo | Mozambique |
|  | Jorge Agostinho Nhamirre | Mozambique |
|  | Alfredo Mário Manga | Mozambique |
|  | Sérgio Rafael | Mozambique |
|  | Jordão Bernardo | Mozambique |
|  | Armando Mário | Mozambique |
|  | Jorge Marurussane Nhamirre | Mozambique |
|  | Passado Khipisse | Mozambique |
|  | Rui Passado | Mozambique |
|  | Mário Eusébio | Mozambique |
|  | Américo Sinava Mutondo | Mozambique |
|  | Rui João Tangune | Mozambique |
|  | Manuel Machiquane Mutondo | Mozambique |
|  | Luís João Fungue | Mozambique |
|  | Alexandre João | Mozambique |
|  | Gil Martinho Zevane | Mozambique |
|  | Jordão Gil Zevane | Mozambique |
|  | Xavier José | Mozambique |
|  | Geraldo Gil Zevane | Mozambique |
|  | José Gil Zivane | Mozambique |
|  | Mascarenhas Gil Zevane | Mozambique |
|  | Issaca Mihumbo Tanguene | Mozambique |
|  | João Tangune | Mozambique |
|  | João Tangune | Mozambique |
|  | Alberto João | Mozambique |
|  | João Piquiuane | Mozambique |
|  | José Samucece Mutondo | Mozambique |
|  | Afonso Samucene | Mozambique |
|  | Horácio Afonso | Mozambique |
|  | Feliciano Júlio | Mozambique |
|  | Afonso Mutondo | Mozambique |
|  | Tiane Manuel Zevane | Mozambique |
|  | Gustavo Julião Zevane | Mozambique |
|  | Mateus Gustavo Zevane | Mozambique |
|  | Manusse Carlos Buene | Mozambique |
|  | Samito Daniel Zevane | Mozambique |
|  | Júlio Domingos Tembe | Mozambique |
|  | Ronaldo Lourenço Licuco | Mozambique |
|  | Santos Tembe | Mozambique |
|  | Adelino Julião Tembe | Mozambique |
|  | Pesane António Tembe | Mozambique |
|  | Eduardo Daniel Juramento | Mozambique |
|  | Gabriel Maniete Zevane | Mozambique |
|  | Alexandre André Buene | Mozambique |
|  | Fidel Ricardo | Mozambique |
|  | Daniel Juramento | Mozambique |
|  | Francisco Gustavo Zevane | Mozambique |
|  | Alfredo Arnaldo | Mozambique |
|  | Américo Domingos | Mozambique |
|  | Nolfo Domingos | Mozambique |
|  | Orlando Daniel Juramento | Mozambique |
|  | Julião Sebastião | Mozambique |
|  | Catine António Bulumbu | Mozambique |
|  | Maria Dozeta | Mozambique |
|  | Flórida Fabião | Mozambique |
|  | Castro Falange Mufume | Mozambique |
|  | Domingos Jilila | Mozambique |
|  | Elisa Evaristo | Mozambique |
|  | Laura Viagem Mutondo | Mozambique |
|  | Juramento Zevane Inora Arnaldo | Mozambique |
|  | Gilda Arnaldo | Mozambique |
|  | Zaida Carlos Alberto | Mozambique |
|  | Alaide Artur | Mozambique |
|  | Luís Albino Pacule | Mozambique |
|  | Carlos Luzenda Zivane | Mozambique |
|  | Cristina Finirguetane Huo | Mozambique |
|  | Rosa Pascoal | Mozambique |
|  | Quitéria Simião Mucavel | Mozambique |
|  | Amélia Vasco Sambo | Mozambique |
|  | Argentina Armando | Mozambique |
|  | Lurdes Armando | Mozambique |
|  | Cardoso Raul Quehá | Mozambique |
|  | Tomas Simone | Mozambique |
|  | Juramento Elias | Mozambique |
|  | Lourenço Joaquim | Mozambique |
|  | Manecas Lourenço | Mozambique |
|  | Muriane Valente | Mozambique |
|  | Joel Salomão | Mozambique |
|  | José Sousinho | Mozambique |
|  | Francisco Raul Zevane | Mozambique |
|  | Jacinto Joaquim | Mozambique |
|  | Januário Fanifane | Mozambique |
|  | Constantino Geraldo | Mozambique |
|  | Paulino José Vilanculos | Mozambique |
|  | Arnaldo Ernesto Huo | Mozambique |
|  | Cremildo Ernesto Tembe | Mozambique |
|  | Feliciano Arnaldo Huo | Mozambique |
|  | Celeste Nomiato Kwinhane | Mozambique |
|  | Mário Arnaldo Tembe | Mozambique |
|  | Carlitos Matsiquete Banze | Mozambique |
|  | Fernando Chigamane Kwinhane | Mozambique |
|  | João Lassane Zivane | Mozambique |
|  | João Luís Mandane | Mozambique |
|  | Orlando Jorge Zivane | Mozambique |
|  | João Sebastião Massane | Mozambique |
| MZ 6 |
|  | Ivete Maibaze | Mozambique |
|  | Guilhermina Amurane | Mozambique |
|  | Anselmo Gaspar | Mozambique |
|  | Isabelle Giddy | South Africa |
|  | Urszula Stankiewicz | USA |
|  | Vic Cockcroft | South africa |
|  | Almeida Guissamulo | Mozambique |
|  | Sidónia Muhorro Gueze | Mozambique |
|  | Ana Paula Francisco | Mozambique |
|  | Custódio Mário | Mozambique |
|  | Vilela De Sousa | Mozambique |
|  | Fernandes | Mozambique |
|  | Alexandre Bartolomeu | Mozambique |
|  | Levin Cuinica | Mozambique |
|  | Armando Benzane | Mozambique |
|  | Isabel Manga | Mozambique |
|  | Edson Jossias Salvador | Mozambique |
|  | Fernando Bata Júnior | Mozambique |
|  | Jorge Tembe | Mozambique |
|  | Maurício Machuchuque | Mozambique |
|  | Joaquim Macamo | Mozambique |
|  | José Júlio Cerveja | Mozambique |
|  | Filipe Viegas | Mozambique |
|  | Januário Alberto Queixo | Mozambique |
|  | Hortência Carlos | Mozambique |
|  | Rosana Kham Khim | Mozambique |
|  | Roberto Hai Koma | Mozambique |
|  | Francisco José Mbenhane | Mozambique |
|  | Mário Feliciano de Sousa | Mozambique |
|  | Júlio Massingue | Mozambique |
|  | Verónica Massingue | Mozambique |
|  | Eurico Ching Chong | Mozambique |
|  | Paulo Changua | Mozambique |
|  | Artur Mateus | Mozambique |
|  | Bernardo Carlos Marrangule | Mozambique |
|  | Gildo Manuel Zivane | Mozambique |
|  | Gabriel Mutondo | Mozambique |
|  | Fernando Tempo | Mozambique |
|  | Inácio Guezimane | Mozambique |
|  | Faustino Changaveza- | Mozambique |
|  | Mandigo | Mozambique |
|  | José Viagem Matingane | Mozambique |
|  | Maurício | Mozambique |
|  | Venâncio Zivane | Mozambique |
|  | Hassane Nhamirre | Mozambique |
|  | Januário Gingada | Mozambique |
|  | Arnaldo Chauno | Mozambique |
|  | Daniel Tangane | Mozambique |
|  | Chibalala Suzeho | Mozambique |
|  | Vasco Nhamirre | Mozambique |
|  | Tomás Alexandre Gove | Mozambique |
|  | Sebastião | Mozambique |
|  | António Manganane | Mozambique |
|  | Alberto Lachane | Mozambique |
|  | Arnaldo M. | Mozambique |
|  | Julião Adriano Mufume | Mozambique |
|  | Jorge Gingado | Mozambique |
|  | Adolfo Alberto Zivane | Mozambique |
|  | Joaquim Oliveira Chiparage | Mozambique |
|  | Félix Bernardo | Mozambique |
|  | Ana Jalena | Mozambique |
|  | Celestino | Mozambique |
|  | Rafael Lucas | Mozambique |
|  | Cândida Vicente | Mozambique |
|  | Pascoal Carlos | Mozambique |
|  | Romão Luís | Mozambique |
|  | Ricardo Lucas | Mozambique |
|  | Ricardo José | Mozambique |
|  | Gildo Ricardo | Mozambique |
|  | Alberto João | Mozambique |
|  | Celestino Lucas | Mozambique |
|  | Sérgio José | Mozambique |
|  | Jordão Alexandre | Mozambique |
|  | Ricardo Zacarias | Mozambique |
|  | Milton Luís Zunguze | Mozambique |
|  | João Lucas | Mozambique |
|  | Quizódio Rafael Ngunha | Mozambique |
|  | Oliveira Guerra Vilanculo | Mozambique |
|  | António Guerra Vilanculo | Mozambique |
|  | Alberto Guerra Vilanculo | Mozambique |
|  | Alfredo Selemane | Mozambique |
|  | Aida João | Mozambique |
|  | Rafael Jonasse | Mozambique |
|  | Cacilda Law Chew | Mozambique |
|  | Victor Law Chew | Mozambique |
|  | Vitoriano Jorge Cabrita | Mozambique |
|  | Cacilda Pedro | Mozambique |
|  | Raul Tangane | Mozambique |
|  | Rosa Geito | Mozambique |
|  | Milena Viagem | Mozambique |
|  | Tomas Manasse Chibala | Mozambique |
|  | Benedito Banze | Mozambique |
|  | Emílio Salvador Mutundo | Mozambique |
|  | Patrício Quichado Mutondo | Mozambique |
|  | José Mutondo | Mozambique |
|  | Julae Alberto Nhadave | Mozambique |
|  | Augusto Inácio | Mozambique |
|  | Luciano Augusto | Mozambique |
|  | José Castigo Zevane | Mozambique |
|  | Alima Taju | Mozambique |
|  | Jéssica Julaia | Mozambique |
|  | Raul Micaiela | Mozambique |
|  | Lucas João Inácio | Mozambique |
|  | Miguel Gonçalves | Mozambique |
|  | Álvaro Albino Vine | Mozambique |
|  | Carlos Macaneta | Mozambique |
|  | Maria João Rodrigues | Mozambique |
|  | Paula Santana Afonso | Mozambique |
|  | Oraca Elias Cuambe | Mozambique |
|  | Arsénio Macuácua | Mozambique |
|  | Eugénio Nhantumbo | Mozambique |
|  | Hadija Mussagy | Mozambique |
| SB 1 – SB 5 |
| SB 2 – SB 4 |
| National Facilitating Committee |
| 1 | Chrisianto Daokalia | Solomon Islander |
| 2 | Agnetha Vavekaramui | Solomon Islander |
| 3 | Rosalie Masu | Solomon Islander |
| 4 | Delvene Boso | Solomon Islander |
| 5 | Corzzierrah Posala | Solomon Islander |
| Workshop Training |
| 1 | Morgan Jimuru | Solomon Islander |
| 2 | Abel Hiti | Solomon Islander |
| 3 | Clarrisa Maipio | Solomon Islander |
| 4 | Kanibule Whitney | Solomon Islander |
| 5 | Nose Masu | Solomon Islander |
| 6 | Talu Simeon | Solomon Islander |
| 7 | Dani Jerry | Solomon Islander |
| 8 | Derrisa Michael | Solomon Islander |
| 9 | Amalyia Papae | Solomon Islander |
| 10 | Annie Danials | Solomon Islander |
| 11 | Cynthia Liconia | Solomon Islander |
| SB 3 |
| LK 2 |
| 1 | Dr. U.K.L. Peiris (National Facilitator) |  |
| 2 | Mr. Thushan Kapurusinghe |  |
| 3 | Mr. Tharanga Herath |  |
| 4 | Mr. Prasanna Weerakkody |  |
| 5 | Mr. H.M.D. Sajith Subashana |  |
| 6 | Dr. V. Pahalawattaarachchi |  |
| 7 | Dr. D.D.G.L. Dahanayaka |  |
| 8 | Mr. Arjan Rajasuriya |  |
| 9 | Ms. Shana Ranasinghe |  |
| 10 | Ms. Matheesha Katuwawala |  |
| 11 | Ms. Harini Nishshanka |  |
| 1 | Dr. U.K.L.Peiris | Sri Lankan |
| 2 | Mr.Channa Suraweera | Sri Lankan |
| 3 | Mr.Arjan Rajasuriya | Sri Lankan |
| 4 | Mr. Prasanna Weerakkody | Sri Lankan |
| 5 | Mr. H.M.D. Sajith Subhasinghe | Sri Lankan |
| 6 | Mr. Thushan Kapurusinghe | Sri Lankan |
| 1 | Dr. U.K.L.Peiris | Sri Lankan |
| 2 | Mr.Channa Suraweera | Sri Lankan |
| 3 | Mr.Arjan Rajasuriya | Sri Lankan |
| 4 | Mr. Prasanna Weerakkody | Sri Lankan |
| 5 | Mr. H.M.D. Sajith Subhasinghe | Sri Lankan |
| 6 | Mr. D.D.G.L.Dahanayake | Sri Lankan |
| 7 | Mr. Asanka Gunawardana | Sri Lankan |
|  | 1. Mr. N.H.M. Chitrananda 2. Ms. Sanjeewani Herath 3. Mr. L.D.C.Jayasinghe 4. Mr. S.P.Weerasekera 5. Mr. H.M.M.S.Herath 6. Mr. M.M.N.Somathilaka 7. Mr. G.M Somaratna 8. Mr. S. D. S. P. Sandanayake 9. Mr. R.A.Wanniarachchi 10. Mr. Anura Gunawardena 11. A.P.K.Subasinghe 12. R.M.N.Kumaratunga 13. Lt. Col. Shirantha Millagala 14. Dr. Vasantha Pahalawattaarachchi 15. Dr. Sisira Haputhantri 16. Dr. D.D.G.L. Dahanayaka 17. Mr. C.B.Medagedara 18. Mr. I.B.Amarasinghe 19. Mr. A.C.M.Shafiee 20. Mr. Y. Upul Sanjeewa 21. Mr. K.S.Perera 22. Mr. A.A.Wickramasinghe 23. Mr. A. Jayasekera 24. Mr. J.K.H.Perera 25. Mr. I.M.Sarath Chandranayaka 26. Mr. B.M.D.Balasooriya 27. Mr. Manjula Amararathna 28. Dr. U.K.L.Peiris 29. Mr. W.M.K.S.Chandrathna 30. Mr. Channa Suraweera 31. Mr. Milinda Sampath 32. Mr. P.D.L. Nirasha 33. Mr. I.D.Lakshitha Iddamalgoda 34. Mr. L.I.P.Udugama 35. Mr. Kingsley Peiris 36. Mr. H.T.R. Rajapaksa 37. Mr. M.Gunasekera 38. Mr. L.C.K.Perera 39. Mr. N.C.Dissanayake 40. Mr. L.D.Nishantha 41. Mr. I. N. Priyadarshana 42. Mr. P. G. T. T.Saranga 43. Mr. I.U. Udugamasuriya 44. Mr. R. M. C. C. Ratnayake 45. Mr. R.M.N.S.Ranasinghe 46. Mr. K.Palitha Premakumara 47. Ms. B.H.G.K. Kumari 48. Ms. S.M.Ranasinghe 49. Mr. H.M.D.Sajith Subhashana 50. Mr. Tharanga Herath 51. Mr. B.R.A.G.Kariyawasam 52. Ms. Harini Nishshanka 53. Ms. Matheesha Katuwawala 54. Mr. Arjan Rajasuriya | Sri Lankan |
|  | 1. Mr. N. Vethanayahan 2. Mr. P.Thayanandan 3. Mrs. S.Mathiyalagan 4. Mrs. U.Yasotha 5. Mr. S. Jeyakanth 6. Ms. S. Ahalya 7. Mr. S. Rajiev 8. Mrs. S.Nishanthy 9. Mr. A.G.Inporaja 10. Ms.S.Zibila Rose 11. Mr. J.Sivajirus 12. Mr. T.Sutharshana 13. Mr. K.K.Sivachandran 14. Mrs. T.Meera 15. Mr. R.C.Rathnayake 16. Mr. A.Thanaleden 17. Lt. Col. G.A.K.Botheju 18. Major. N. Weerasinghe 19. Major. U.G.A.N.Gunarathne 20. Captain L.G.G.Lindumahagedera 21. Captain S.P.S.A.Somasiri 22. Mr. K.Jayasinghe 23. Mr. Saman Jayasinghe 24. Flt Lt R.S.M.C. Samaranayake 25. Mr. T.S.Meedin 26. Mr. A.M.Sameera Silva 27. Mr. C.R.R.R.Fristroy 28. Mr. E.U.Edirisinghe 29. Mr. B.M.S.S.K.Basngarika 30. Mr. B.R.Ooyangodas 31. Mr. S.M.R.Senanayaka 32. Mr. J.Suthayera 33. Ms. Diana Nilochkerar 34. Mr. N.Visnuvaurthavar 35. Mr. L.Thuvarakan 36. N.M.N.K.T.Gurathilaka 37. Mr. W.M.R.Dharmabandu 38. Dr. U.K.L.Peiris 39. Mr. Channa Suraweera 40. Ms. B.H.G.K. Kumari 41. Mr. M.G.A.Gunawardana 42. Dr. Vasantha Pahalawattaarachchi 43. Dr. D.D.G.L. Dahanayaka 44. Mr. Tharanga Herath 45. Mr. M.G.G.Dhanushka 46. Mr. Thushan Kapurusinghe 47. Mr. Ranil Nanayakkara 48. Mr. Arjan Rajasuriya 49. Ms. Harini Nishshanka 50. Ms. Matheesha Katuwawala | Sri Lankan |
|  | 1. Mr. M.Y.S. Deshapriya 2. Mr. L.S. Croos 3. Mr. T.A. Daniel 4. Mr. B.S. Mirando 5. Lcdr. H.M.A.S.K. Herath 6. Major H.T.A. de Alwis 7. Major H.G.M. Nishantha 8. Major S. Hettiarachchi 9. Lcdr. A.P.K. Subasinghe 10. Mr. M. Paramathm 11. Mrs. M.S.C. Peiris 12. Mr. S.I. Vaz 13. Mr. S.B. Herath 14. Mr. M. Sriskandakumar 15. Mr. H.T. Sampath 16. Mr. V. Papakaran 17. Mr. N.A.P.S.S. Wichramasingha 18. Ms. M.A.W.A. Prasadi 19. Mr. Thushan Kapurusingha 20. Ms. V. Pahalawattaarachchi 21. Mr. Ranil Nanayakkara 22. Mr. U.K.L. Peiris 23. Mr. M.G.G. Dhanushka 24. Mr. Tharanga Herath 25. Mr. D.D.G.L. Dahanayaka 26. Mr. Arjan Rajasooriya 27. Dr. Lakshman Peiris 28. Mr. Channa Suraweera 29. Mr. M.T.A. Gunawardena | Sri Lankan |
|  | 1. Mr. S. Sathyaseelan 2. Mr. C. Krishnadaran 3. Cdr (NP) W.S. Premarathne 4. Mr. P. Jeyararu 5. Mr. V. Thiyagaraja 6. Mr. M.M.D.N. Chathuranga 7. Mr. M. Nakkeeran 8. Mr. P. Pirashanthan 9. Mr. N. Sriranjam 10. Mr. Kapila Bandara 11. Mr. M.M.J. Ariaywansa 12. Mr. S.A.C.Roshan 13. Mr. S.Saliva 14. Mr. W.M. Sajeewa Piyasena 15. Mr. Thushan Kapurusingha 16. Ms. V. Pahalawattaarachchi 17. Mr. Ranil Nanayakkara 18. Mr. U.K.L. Peiris 19. Mr. M.G.G. Dhanushka 20. Mr. Tharanga Herath 21. Mr. D.D.G.L. Dahanayaka 22. Mr. Arjan Rajasooriya 23. Dr. Lakshman Peiris 24. Mr. Channa Suraweera 25. Mr. Shantha Weerasinghe 26. Mr. M.T.A. Gunawardena 27. Mr. W.M.R. Darmabandu | Sri Lankan |
| LK 4 |
| Included in minutes and discussion notes |
| LK 5 |
|  | 1. Dr. Lakshman Peiris – Assistant Director (Research and Training) 2. Mr. Channa Suraweera, Dept of Wild Life 3. Dr. Vasantha Pahalawaththaarachchi - NARA 4. Mr. PrasannaWeerakkody – ORCA 5. Mr. Sajith Subashana - ORCA 6. Mr. Ranil Nanayakkara - BEAR 7. Mr. Arjan Rajasuriya – 8.Mr.Thushan Kapurusingha -TCP | Sri Lankan |
|  | Dr. Palitha Kithsiri. Actg. Director General, Deputy Director General, NARA, Mr.A.B.A.K. Gunarathna, Director Monitoring and Evaluation, NARA; Dr.V.Pahalawattaaarachchi , GEF project coordinator; Dr. G. Dassanayake (Scientist, NARA) | Sri Lankan |
|  | 1. Dr. Lakshman Peiris – Assistant Director (Research and Training) 2. Dr. Gihan Dahanayake - NARA 3. Mr. PrasannaWeerakkody – ORCA 4. Mr. Sajith Subashana - 5. Mr. Arjan Rajasuriya – IUCN | Sri Lankan |
| LK 7 |
|  | W.J.Jayalath W.Liyo Juniper Fernando W.Priman Ackvinas H.M.Dhanajaya Madumal W.Priyantha Janaka Fernando A.Anna Biyatris W.Pradeep Gayan Fernando H.Dhanasena Silva W. Jude Asitha Prasanga W.Roshan Nishantha W. Francis Jemuni Fernando E.Chaminda Rohita W.Patum Sanjeewa A.P.Jude Nishantha W.J.Mark Thisera W.Pavulu Tissera K.A.Pathum Shirantha A.K.M.Nalir W.Kingsly Priya Shantha W.Rohan Anthony M.Hanifa Jalil W.Cristopher Fernando Jasintha Tissera W.Roshan Manjula H.M.Ranjith W.Nadeeka Sandamali W.Sangeetha Priyadharshani W.Renuka Damayanthi K.Suris Nilantha W.Mary Margaret L.Priman Aquinas W.Roshini Shashikala A.L.Dilinika W.Kusumalatha C.Thushari K.M.Nilmini H.K.Kumuduni Kurera H.A.Champika K.A.Susantha Damayanthi W.Niranjala Samanlatha R.P.Pradeepa Shiromi M.A.Chandani Isurika Dulanjali UpekkaTamali Thanuja Sudarshani Nayomi Shashikala NadeeshaTecklanthi Menaka Wasanthi Mohani Iroshani W.Sajini Kaushalya R.Manjula Dilrukshi A.K.M.Nalir W.Jude Asitha Prasanga W.Kingsly Priyashantha W.NishanthaTissera M.M.Dhananjaya Nimal Vijilas Anzar Amitha Salman Nipasi Azir M.Karunawathi Mallika Kanthi Maheshwari Suseema Deepanjali Renu Piyaseeli Amitha Priyangani Susana Dirijet Shirani Randika Other officials: Mrs. Subhashini Nonis Nonis, Principal, Nagamaduwa Kanishta Vidyalaya, Vanathavillu Mr. Pradeep Aruna Shantha Vijayapura K. vidyalaya, Vanathavillu Mr. Nazeer, Principal, Nirmala matha Sinhala maha vidyalaya, Kalpitiya Mr. Nevious Perera, Principal, St. Sebastian Sinhala vidyalaya, Kandakuliya Mr. Dissanayake Principal, Romanu Katholika Sinhala Vidyalaya, Kurinchipitiyaa Mr. Wickramasinghe, Assistant Director, District Fisheries Office, Puttalam |  |
| LK 8 |
|  | Dr. U.K.L. Peiris (National Facilitator) Mr. Thushan Kapurusinghe Mr. Tharanga Herath Mr. Prasanna Weerakkody Mr. H.M.D. Sajith Subashana Dr. V. Pahalawattaarachchi Dr. D.D.G.L. Dahanayaka Mr. Arjan Rajasuriya Ms. Shana Ranasinghe Ms. Matheesha Katuwawala Ms. Harini Nishshanka | Sri Lankan |
|  | Dr. U.K.L.Peiris Mr.Channa Suraweera Mr.Arjan Rajasuriya Mr. Prasanna Weerakkody Mr. H.M.D. Sajith Subhasinghe Mr. Thushan Kapurusinghe | Sri Lankan |
|  | Dr. U.K.L.Peiris Mr.Channa Suraweera Mr.Arjan Rajasuriya Mr. Prasanna Weerakkody Mr. H.M.D. Sajith Subhasinghe Mr. D.D.G.L.Dahanayake Mr. Asanka Gunawardana | Sri Lankan |
| TL 1 |
| Attendance sheets can be provided for those meetings led by CI |
| TL 2 |
| 1. | Greg Duncan, Trudiann Dale (CI), Rui Pires, Augusto Pinto, Aires Gutteres, Joao Carlos Soares (MCIA), Lino Martins (MAF) + others. | Australian, Timorese |
| 2. | Karen Edyvane (Charles Darwin University), Sean Clement (BV), Kevin Austin (CTF), Avelino Pereira Fernandes, Duarte de Araujo (Roman Luan), Mateus Belo (Atauro Sub-district administrator), Volker Katzung (Atauro Island Dive Resort), Community members from Maquili, Bikeli and Vila Sucos. | Australian, English, Timorese, German, |
| 3. | Sean Clement, Jemima Gomes (BV), Administrative secretary of Atauro Subdistrict offices | English, Timorese |
| 4. | Sean Clement, Jemima Gomes (BV), Kevin Austin, Ricardo Gomes (Coral Triangle Foundation) Administrative secretary of Atauro Subdistrict offices | English, Australian, Timorese |
| 5. | Sean Clement, Almerita dos Santos (BV), Celestinho Barreto de Cunha, Lino Martins (MAF) | English, Timorese |
| 6. | Sean Clement, Greg Duncan, Jemima Gomes (BV), Cornelio do Carmo (MCIA), Duarte de Araujo (Roman Luan), Kevin Austin (CTF), Jose Gereirro (MAF),Alberto Soares (Xefi Suco, Beloi), Zito F. Ximines(Atauro sub district administrative office), Mario Gomes (Worldfish), Aires Guterres (Project manager, TL4) | English, Australian, Timorese |
| 7. | Greg Duncan (BV), Karen Edyvane, Oldegar Massinga (BV), Jose Quintas(MOT) | Australian, Timorese |
| 8. | Greg Duncan(BV), Dr Mari Alkatiri (ZEESM), Regio Da Cruz (ZEESM), Elizabeth Amaral (UNDP), Farrukh Morriani (UNDP). Dawn Lau (Harvard Business School), Bill Tan (Zeesm), David Green, (GoTL). | Australian, Timorese, American, Indian. |
| 9. | Sean Clement (BV), Convened by CSIRO with representatives attending from MCIA, MAF, Conservation International, University of South Pacific, UNTL, PNTL, Maritime Police, Council of Ministers. | English, American, Australian, Timorese |
| 10. | Sean Clement, Jen Craighill, Amos da Costa, Jemima gomes, various ecotourists (BV), Trudi-ann Dale, Anselmo Amaral, Mark van Erdmann, David Emmett, Raimundo Mau (Conservation International), Duarte de Araujo, Avelino Pereira Fernandes, Marcelo (Roman Luan), Mateus Belo, Xefi Sucos from Vila, Beloi, Bikeli and Makili Sucos, Volker Katzung, Barry Hinton (Barry’s Place), Celestinho Baretto de Cunha, Lino Martins, Jose Gereirro (MAF), Aires Guterres (Project manager, TL4), Mario Gomes (Worldfish), delegates and representatives of Atauro communities | English, Australian, American, Timorese, German |
| 11. | Sean Clement, Jemima Gomes (BV), Anselmo Amaral, Raimundo Mau (CI), Students and faculty from University Nacional de Timor-Leste | English, Timorese |
| 12. | Sean Clement (BV), Alex Tilley (Worldfish) | English |
| 13. | Greg Duncan (BV), Trudi-ann Dale (CI) | Australian |
| 14. | Sean Clement (BV), Representatives and delegates from domestic and international companies, NGOs and academic institutions including University of the Algarve, Dili Institute of Technology, Asia Foundation, UK Foreign Office and others | Multiple |
| 15. | David Mills (World Fish), Alex Tilley (World Fish), Hampus Eriksson, Celestino Baretto de Cunha (MAF), Alda da Sousa (MAF), Maria Amado (Empreza Di’ak) Greg Duncan (BV), Oldegar Massinga (BV), Mario Gomes (World Fish), Sarah Lawless, Hugh Govern, Jose Nunes (MAF) Angelina Arujo (Plan International), Avelino Pereira Fernandes (Roman Luan) | Australian, Swedish, Timorese, Portuguese, |
| 16. | Sean Clement, Jen Craighill (BV), Karen Edyvane (CDU), Trudi-Ann Dale, Anselmo Amaral, Olive Andrews, Raimundo Mau (CI), Acacio Gutteres, Celestinho Baretto de Cunha (MAF), Representatives from Maritime Police and UNTL | English, Australian, Timorese, New Zealand |
| 17. | Sean Clement (BV), Mario Gomes, Al Tilley (Worldfish), Mateus Belo, Trudi-Ann Dale, Raimundo Mau, Anselmo Amaral, Celestino Barreto de Cunha, Acacio Gutteres, Jose Gereirro (MAF), Avelino Pereira Fernandes (Roman Luan), Representatives from communities across Atauro. | English, Australian, Timorese |
| TL 3 |
| Attendance sheets can be provided for those meeting led by CI |
| TL 4 |
| 1. 2. 3. 4. 5. 6. 7. 8. 9. 10. | Aires Anselmo Greg DIr. Rui Dir. Augosto Che. Andre Augosto Sean DG Joao And many more participants from National and other international Also local Authorities, communities, NGO’s | Timorese Timorese Australia Timorese Timorese Timorese Timorese UK Timorese |
| TL 5 |
| See attached document (List of participants; appendix 1) of HYR – see captured below: |
| VU 1 |
| Names are listed in minutes of the NFC meeting |
| VU 2 |
| Names are listed in minutes of the NFC meeting |

APPENDIX 3 – SECTION 4.5 DOCUMENTS, OTHER PRINTED MATERIALS, VIDEOS, AND SOFT PRODUCTS (SUCH AS CDS OR WEBSITES)

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication date |
| --- | --- | --- | --- | --- | --- | --- |
| ID 1 |
| 1 | Technical Report | Technical Report-Public Consultation on DSCP Implementation in Kotawaringin Barat, Tolitoli and Alor | CMB | CMB | - | 22 December 2016 |
| 2 | Document | National Plan of Action for Dugong and Seagrass in Indonesia | CMB | CMB | - | 23 December 2016 |
| ID 2 |
| 1 | Technical Report | Report of Dugong and Its Seagrass Habitat Survey in Alor, 30 Mei-6 Juni 2016 | Juraij, Khaifin, Tutus Wijanarko, Syarif Yulius Hadinata, Maulid Dio Suhendro (WWF-ID) | Not yet published | - | - |
| 2 | Technical Report | Report of Dugong and Its Seagrass Habitat Survey in Sangihe, 25 Juli-6 Agustus 2016 | Juraij (WWF-ID) | Not yet published | - | - |
| 3 | Technical Report | Report of Preliminary Survey for Dugong and Its Seagrass Habitat Survey in Bintan, 22-27 2016 | Rr. Sekar Mira C.H., Prof. Sam Wouthuyzen, Achmad Arifin, Niken Rahayu Sepa, Adriani Sunuddin, Juraij, Nunung Noer Azizah, Casandra Tania, Riswanto (DSCP Survey Team) | Not yet published | - | - |
| 4 | Technical Report | Report of Preliminary Survey for Dugong and Its Seagrass Habitat Survey in Tolitoli, 19-26 September 2016 | Rr. Sekar Mira C.H., Juraij, Erik Munandar, Riswanto, Acmad Arifin, Fitriyah Anggraeni, Suhardi, Dwi Suprapti, Yoppy Endano, Syarif Yulius Hadinata (DSCP Survey Team) | Not yet published | - | - |
| 5 | Technical Report | Report of Preliminary Survey for Dugong and Its Seagrass Habitat Survey in Kotawaringin Barat, 10-16 October 2016 | Rr. Sekar Mira C.H., Juraij, Muta Khalifa, Riswanto, Acmad Arifin, Fitriyah Anggraeni, Suhardi, Casandra Tania, Syarif Yulius Hadinata (DSCP Survey Team) | Not yet published | - | - |
| 7 | Technical Report | Symposium and Workshop Report on Second Southeast Asian Marine Mammal Stranding Network Pattaya, 8-12 November 2016 | Sheyka Nugrahani Fadela (WWF-ID) | Not yet published | - | - |
| 8 | Map | Maps of Preliminary Results Survey | Dyah Rahmatika DD (WWF-ID) | Not yet published | - | - |
| MG 1 |
| 1 | Powerpoint presentation | Community presentatin on mapping results (Cartographie participative des habitats marins de l’archipel des Îles Barren) | Kevin Chambon | NA | NA | NA |
| 2 | Report | Report on mission to present results ( Atelier formation des représentants Vezo Miray Nosy Barren, 17-18.08.2016: Rapport) | Cecile Fattebert | NA | NA | NA |
| 3 | Report | Mapping mission report | Jean Berthieu Nomenjanahary | NA | NA | NA |
| 4 | Excel | Mapping data global (results form mapping missions) | Kevin Chambon | NA | NA | NA |
| 5 | Maps | Habitats mapping the BI archipelago - 4 maps | Kevin Chambon | NA | NA | NA |
| 6 | Doc | Briefing documents about the mapping which include the method | Kevin Chambon |  |  |  |
| 7 | Pictures | Seagrass in the BI archipelago | Kevin Chambon | NA | NA | NA |
| 8 | PV | Minutes from the workshop series about the MCS programme development for the BI MPA (17-22.10.2016) | Charles Andrianaivojaona | NA | NA | NA |
| 9 | PV | Minutes from the workshop series about the MCS programme development for the BI MPA (22.10.2016 | Charles Andrianaivojaona | NA | NA | NA |
| 10 | Report | Atelier d’élaboration du programme MCS pour l’AP Îles Barren : Rapport | Cecile Fattebert | NA | NA | NA |
| MG 2 |
| 1 | Meeting report | Dugong and seagrass education and awareness day | MIHARI Network | NA | NA | 13 Septembre 2016 |
| 2 | Online article | Communities leading seagrass and dugong conservation https://mihari-network.org/news/communities-leading-seagrass-dugong-conservation/ | MIHARI Network | NA | NA | January 2017 |
| 3 | Report | Priority site identification - mission reports where focus groups took place | MIHARI Network | NA | NA | January 2017 |
| 4 | Map | Priority site maps | MIHARI Network | NA | NA | January 2017 |
| 5 | Excel | Summary of priority sites | MIHARI Network | NA | NA | January 2017 |
| MG 3 |
| 1 | Film | C3 community outreach film |  | C3 |  | November 2016 |
| 2 | Postcard | Dugong postcard |  | C3 |  | July 2017 |
| 3 | Brochure | Womens ecotourism restaurant promotional brochure |  | C3 |  | August 2016 |
| 4 | Report | Feasibility report and business plan for two livelihood |  | C3 |  | August 2016, reviewed November 2016 |
| 5 | System | Fisher identification and registration system |  | C3 |  | July 2016 |
| 6 | Press release | http://latribune.cyber-diego.com/societe/2097-ong-c3-prendre-en-main-la-protection-de-l-environnement.html |  | La Tribune de Diego |  | 9th August 2016 |
| 7 | Press release | http://us9.campaign-archive2.com/?u=4a97b0ee2d7c527ef4fe39cee&id=bd39123011 |  | PHE network newsletter |  | September 2016 |
| 8 | Press release | http://www.newsmada.com/2016/12/05/dugong-nosy-hara-suivi-continu-de-la-population/ |  | News Mada |  | 05 December 2016 |
| MG 4 |
| MG 6 |
| N/A |
| MY 1 |
| 1. | Research Report | Status Report On The Marine Environment Of The Mersing Marine Park Islands, And Indicative Proposal For The Establishment Of A Marine Protected Area (MPA) Network | Dr. Jillian Ooi |  |  |  |
| 2. | Research Report | A Study Of Potential New Areas To Be Gazetted As State Of Johor Marine Parks | Assoc. Prof. Dr. Rosman bin Abdullah |  |  |  |
| MY 2 |
| NONE |
| MY 3 |
| 1 | Poster | Dugong Education Poster (English) | Leela Rajamani |  |  | October 2016 |
| 2 | Poster | Dugong Education Poster (Malay) | Leela Rajamani |  |  | October 2016 |
| 3 | A4 Stickers | A4 Sticker Best Practice and Boats (English) | Leela Rajamani |  |  | October 2016 |
| 4 | A4 Stickers | A4 Sticker Best Practice and Boats (Malay) | Leela Rajamani |  |  | October 2016 |
| 5 | Facebook page | Community Management of Dugong and Seagrass in Malaysia Facebook address : https://www.facebook.com/Community-Management-of-Dugong-and-Seagrass-in-Malaysia1691388057846078/?ref=aymt_homepage_panel | Leela Rajamani |  |  | 22nd October 2016 |
| MZ 1 |
| 1 | Report | Population, Health, and the Environment: Addressing Family Planning Needs on Bazaruto Island | Isabelle Giddy, Urszula Stankiewicz, Lionel Massicane |  |  | October 2016 |
| 2 | Report | Seaweed Mariculture in Bazaruto Archipelago: Environmental, Economic, and Social Considerations | Isabelle Giddy |  |  | July 2016 |
| 3 | Report | Collective Community Sculpting: Understanding Community Structure on Bazaruto Island | Isabelle Giddy, Urszula Stankiewicz, Lionel Massicane |  |  | July 2016 |
| MZ 4 |
| 1 | Report | Collective Community Sculpting: Understanding community structure on Bazaruto | Isabelle Giddy (Au), Urszula Stankievicz and Lionel Massicane | N/A | N/A | N/A |
| 2 | Report | Seaweed mariculture in Bazaruto Archipelago: Environmental, Economic and Social considerations | Isabelle Giddy (Au) | N/A | N/A | N/A |
| 3 | Report | ICT4Fisheries: Responsible small-scale fisheries management and its relevance to Bazaruto | Isabelle Giddy (Au), Crimildo Zivane | N/A | N/A | N/A |
| MZ 5 |
|  | Report | Report on field trip to Inhassoro - 28 September - 02 October 2016 | Anselmo Gaspar & Alexandre Bartolomeu | N/A | N/A | N/A |
|  | Videos | Videos on field trip to Inhassoro - 18 - 27 September 2016 | Armando Benzane | N/A | N/A | N/A |
| MZ 6 |
|  | Report | Minutes of the Partners Meeting of Dugongs and Seagrass Conservation Project - 10 august 2016 | Anselmo Gaspar | N/A | N/A | N/A |
|  | Report | Report on field trip to Inhassoro - 28 September - 02 October 2016 | Anselmo Gaspar & Alexandre Bartolomeu | N/A | N/A | N/A |
|  | Videos | Videos on field trip to Inhassoro - 28 September - 02 October 2016 | Armando Benzane | N/A | N/A | N/A |
|  | Report | Minutes of the Partners Meeting of Dugongs and Seagrass Conservation Project - 14 October 2016 | Anselmo Gaspar | N/A | N/A | N/A |
|  | Report | Minutes of the National Facilitation Committee Meeting of Dugongs and Seagrass Conservation Project - 17 October 2016 | Anselmo Gaspar | N/A | N/A | N/A |
| SB 1 – SB 5 |
| SB 2 – SB 4 |
| N/A |
| LK 1 |
| Not at the moment will have them in about 1 week |
| LK 5 |
| 1 | Printed material | Poster on Seagrasses in Sri Lanka | V.Pahalawattaarachchi |  |  | Ongoing |
| LK 7 |
|  | Newsletter (English- online) | Turtle News | SLTCP | SLTCP |  | 25th Nov 2016 |
|  | Newsletter (English) | Turtle News | SLTCP | SLTCP |  | 20th Nov 2016 |
|  | Educational leaflets | Mangroves, Coral reefs, Marine turtles |  | Sri Lanka Turtle Conservation Project |  | August, 2016 |
| LK 8 |
| 1 | Report | Monthly reports July to Dec 2016 | U.K.L.Peiris |  |  |  |
| 2 | Report | National facilitating Committee meeting | U.K.L.Peiris |  |  |  |
| 3 | Report | National Level Awareness | U.K.L.Peiris |  |  |  |
| 4 | Report | National Steering Committee | U.K.L.Peiris |  |  |  |
| 5 | Report | Training Need Assessment | U.K.L.Peiris |  |  |  |
| TL 2 |
| 1 | Website pages being updated, promoting the volunteer ecotourism project | https://blueventures.org/volunteer/timor-leste/ | BV | BV | NA | NA |
| 2 | Blog | https://blog.blueventures.org/cetacean-migration-whales-dolphins-arrived/ | BV | BV | NA | October 2016 |
| 3 | Meeting report | Homestay meeting output | BV |  |  | October 2016 |
| 4 | Report | Homestay property report | BV |  |  | October 2016 |
| 5 | PowerPoint presentation | Bv Community presentation | BV |  |  | October 2016 |
| 6 | PowerPoint presentation | CBM Sensitisation workshop | BV |  |  | October 2016 |
| 7 | PowerPoint presentation | Seagrass monitoring training, 1, 2 and 3 | BV |  |  | October-December 2016 |
| TL 4 |
| 1 | Banners/Posters | For Public Awareness | Aires | TL4, MCIA |  | - |
| 2 | Stickers | For Public Awareness | Aires | TL4 |  | - |
| 3 | Brochures | For Public Awareness | Aires | TL4 |  | - |
| 4 | TV Advert | For Public Awareness | Aires + TV | TL4, TVeT, MCIA |  | Dec-Present |
| TL 5 |
| None |
| VU 1 |
| 1 | Posts on VESS Facebook Page | https://www.facebook.com/vanuatuconservation | Christina Shaw | VESS |  | July – December 2016 |
| 2 | Project Page on VESS website | Our current projects www.vanuatuconservation.org/our-projects/current-projects | Christina Shaw | VESS |  | 15 April 2016 |
| 3 | Poster | Koafis blong Vanuatu | Christina Shaw | VESS |  | Available on the VESS website |
| 4 | Poster | Dugongs of Vanautu | Christina Shaw | VESS |  | Available on the VESS website |
| 5 | Poster | Seagrass facts | Christina Shaw | VESS |  | Available on the VESS website |
| 6 | Poster | Gras Blong Solwata | Christina Shaw | VESS |  | Available on the VESS website |
| 7 | Book | Dugongs and their Seagrass habitat | Christina Shaw | VESS |  | Available on the VESS website |
| 8 | Book | Kaofis mo plis we oli kakae gras blong solwata | Christina Shaw | VESS |  | Available on the VESS website |
| 9 | Minutes | Minutes for Meeting of the National facilitating Committee (NFC) for the GEF Dugong and Seagrass Conservation Project on 28th October 2016 | Christina Shaw | VESS |  | 28th October 2016 |
| 10 | Photos of the survey team conducting surveys | Various photos | Christina Shaw, Douglas Koran and the survey team | VESS |  | July – December 2016 |
| VU 2 |
| 1 | Posts on VESS Facebook Page | https://www.facebook.com/vanuatuconservation | Christina Shaw | VESS |  | July – December 2016 |
| 2 | Project Page on VESS website | Our current projects www.vanuatuconservation.org/our-projects/current-projects | Christina Shaw | VESS |  | 15 April 2016 |
| 3 | Minutes | Minutes for Meeting of the National facilitating Committee (NFC) for the GEF Dugong and Seagrass Conservation Project on 28th October 2016 | Christina Shaw | VESS |  | 28th March 2016 |
| 4 | Magazine article | Discovering Vanuatu’s Dugongs | Alice Grainger | Scuba Diver Australasia Magazine |  | 28th March 2016 |
| Global Dugong and Seagrass Conservation Project |
| 1 | News article | Dugong conservation project makes waves |  | UNEP wesbsite |  | 27 December 2016 |
| 2 | Website Post | Pulau Sibu (MY1) team submits baseline survey data |  | Global Project website |  | 27 December 2016 |
| 3 | Website Post | Field updates: Johor Malaysia – Observations of community from a dugong conservationist |  | Global Project website |  | 22 December 2016 |
| 4 | Website Post | Two events in Abu Dhabi for our partners |  | Global Project website |  | 19 December 2016 |
| 5 | Website Post | Dugong in the Madagascar News |  | Global Project website |  | 06 December 2016 |
| 6 | Website Post | Indonesian project partners convince fisherman to release captive dugong |  | Global Project website |  | 29 November 2016 |
| 7 | Website Post | Great DSCP TV news piece from Kuala Lumpur |  | Global Project website |  | 17 November 2016 |
| 8 | Website Post | Dugong and Seagrass Project in the News |  | Global Project website |  | 13 November 2016 |
| 9 | News article | وفد من أبوظبي يشارك في قمة حفظ الأطوم والأعشاب البحرية بماليزيا (Translation in English: Delegation from Abu Dhabi participates in summit on conserving dugongs and seagrasses in Malaysia) |  | Al Bayan Newspaper - UAE |  | 03 November 2016 |
| 10 | News article | صندوق الكائنات الحية ينفذ المشروع الدولي لحماية الأبقار والأعشاب البحرية (Translation in English: The Mohamed bin Zayed Species Conservation Fund executes the global project on conservation of dugongs and seagrasses) |  | Al Ittihad Newspaper - UAE |  | 03 November 2016 |
| 11 | News article | وفد من أبوظبي يشارك في قمة الحفاظ على الأطوم (Translation in English: Delegation from Abu Dhabi participates in summit on conserving dugongs) |  | Al Khaleej - UAE |  | 03 November 2016 |
| 12 | News article | Fisheries Department calls for MoU on dugong conservation |  | astro AWANI |  | 03 November 2016 |
| 13 | News article | Fisheries Department calls for MoU on dugong conservation |  | Borneo Post online |  | 03 November 2016 |
| 14 | News article | Fisheries Department Calls For Mou On Dugong Conservation |  | malaysiandigest.com |  | 03 November 2016 |
| 15 | Website Post | Second Executive Project Steering Committee of the DSCP met in KL in November 2016 |  | Global Project website |  | 02 November 2016 |
| 16 | News article | وفد من أبوظبي يشارك في قمة حفظ الأطوم والأعشاب البحرية في ماليزيا (Translation in English: Delegation from Abu Dhabi participates in summit on conserving dugongs and seagrasses in Malaysia) |  | Emirates News Agency (WAM) - UAE |  | 02 November 2016 |
| 17 | News article | Malaysia: On the brink of extinction, only 100 dugongs left in Malaysia |  | Wild Singapore |  | 02 November 2016 |
| 18 | News article | On the brink of extinction: Only 100 dugongs left in Malaysia |  | astro AWANI |  | 02 November 2016 |
| 19 | News article | Fisheries Department Calls For MoU On Dugong Conservation |  | bernama.com |  | 02 November 2016 |
| 20 | Website Post | Dugong Festival in Sahamalaza Madagascar at October’s End |  | Global Project website |  | 25 October 2016 |
| 21 | Website Post | Dugong featured on “The Ark” podcast |  | Global Project website |  | 25 October 2016 |
| 22 | Website Post | Environmental and Socio-Economic Reports from Puttlam Langoon, Sri Lanka |  | Global Project website |  | 13 October 2016 |
| 23 | Website Post | A global call to action from the World Seagrass Association |  | Global Project website |  | 12 October 2016 |
| 24 | Website Post | Dugong photographed in Lau Lagoon, Solomon Islands |  | Global Project website |  | 27 September 2016 |
| 25 | Website Post | Facebook pages, websites, education materials – Vanuatu goes ‘dugong’ on conservation |  | Global Project website |  | 22 August 2016 |
| 26 | Website Post | Conducting dugongs surveys and delivering conservation messaging in Vanuatu |  | Global Project website |  | 22 August 2016 |
| 27 | Website Post | Bringing it all together (for dugong and seagrass) in Timor-Leste |  | Global Project website |  | 22 August 2016 |
| 28 | Website Post | ‘I love dugong’ Reaching out to Timor-Leste through National Education TV |  | Global Project website |  | 22 August 2016 |
| 29 | Website Post | Ecotourism off the ground and into the sea in Timor-Leste |  | Global Project website |  | 22 August 2016 |
| 30 | Website Post | CMS Dugong Bycatch Questionnaire adapted for use in Timor-Leste communities |  | Global Project website |  | 22 August 2016 |
| 31 | Website Post | Extensive outreach primes Sri Lankan area for dugong and seagrass conservation |  | Global Project website |  | 22 August 2016 |
| 32 | Website Post | Extensive fieldwork on Sri Lankan seagrasses. Dugongs highly valued for meat in Sri Lanka. |  | Global Project website |  | 22 August 2016 |
| 33 | Website Post | Closing the knowledge gap of seagrass habitats in Sri Lanka |  | Global Project website |  | 22 August 2016 |
| 34 | Website Post | Marine conservation centre well underway in Jaffna Sri Lanka |  | Global Project website |  | 22 August 2016 |
| 35 | Website Post | Field trips and community discussions underway to protect dugongs in Solomon Islands |  | Global Project website |  | 22 August 2016 |
| 36 | Website Post | Reports of dugongs returning after six-year absence in Solomon Islands outpost |  | Global Project website |  | 22 August 2016 |
| 37 | Website Post | Development of community health programme in Mozambique holds promise for enacting conservation |  | Global Project website |  | 22 August 2016 |
| 38 | Website Post | Family planning and alternatives to fishing get off the ground in Mozambique |  | Global Project website |  | 22 August 2016 |
| 39 | Website Post | Team pioneers drone survey in remote areas of Malaysia and local school kids get a little dugong diplomacy |  | Global Project website |  | 22 August 2016 |
| 40 | Website Post | Aerial survey of dugong and seagrass, community interviews, and lobbying keeps Malaysian partner busy in Johor |  | Global Project website |  | 22 August 2016 |
| 41 | Website Post | Learning English with ‘Adventures of Karum the Dugong’ in Malaysia |  | Global Project website |  | 22 August 2016 |
| 42 | Website Post | Madagascar mapping, interviews, and deployed dugong detectors – much success and a few setbacks |  | Global Project website |  | 22 August 2016 |
| 43 | Website Post | Conservation progressing rapidly in Sahamalaza Marine and Costal UNESCO Biosphere Reserve |  | Global Project website |  | 22 August 2016 |
| 44 | Website Post | Madagascar partner sights 18 dugongs and works with communities to protect them |  | Global Project website |  | 22 August 2016 |
| 45 | Website Post | Project team begins work with Madagascar national network of LMMAs |  | Global Project website |  | 22 August 2016 |
| 46 | Website Post | Madagascar communities to establish marine protected areas |  | Global Project website |  | 22 August 2016 |
| 47 | Website Post | First Indonesian symposium on dugong and seagrass habitat |  | Global Project website |  | 22 August 2016 |
| 48 | Website Post | Indonesian fieldwork starts on the ground and goest into the air |  | Global Project website |  | 22 August 2016 |
| 49 | Website Post | T-shirts for dugong conservation in Madagascar |  | Global Project website |  | 22 August 2016 |

# Footnotes

Briefly describe progress made during the previous six months highlighting major outcomes/benchmarks achieved during the period.

Information provided in “Quarterly Expenditure Statement and Explanation of Expenditures Reported” should be in line with output/activity progress reported in this table.

Outputs and activities as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Variance refers to the difference between the expected and actual progress at the time of reporting.

Information on expected date of output completion and progress made is a requirement.

Do not include routine project reporting. Examples of M&E activities include baseline data collection, stakeholder surveys, field surveys, steering committee meetings to assess project progress, peer review of documentation to ensure quality, mid-term review, etc.

Expand table if necessary

Expand table if necessary

Meeting types: Inter-governmental meeting, expert group meeting, project inception workshop, training workshop/seminar, Partners consultation workshop, project Steering Committee meeting, other.

Expand table if necessary

Documents and printed material types are: Report to inter-governmental meeting, technical publication, meeting report, technical/substantive report, brochures, media releases, etc.

Meeting types: Inter-governmental meeting, expert group meeting, project inception workshop, training workshop/seminar, Partners consultation workshop, project Steering Committee meeting, other.