The GEF Dugong and Seagrass Conservation Project

Project Progress Report

| Reporting Period | From: | Jul / 2016 | To: | Dec / 2016 |
| --- | --- | --- | --- | --- |

- PROJECT GENERAL INFORMATION

| National Project Code & Title: | ID 1 – 2101 & Strengthen and Operationalize National Policy Strategy and Action Plan for Dugongs and Seagrass Conservation |
| --- | --- |

| Project Partner(s): | Directorate of Conservation and Marine Biodiversity, Directorate General of Marine Spatial Management, MMAF Indonesia (CMB) Supporting partners: WWF-Indonesia; Indonesian Institute of Sciences, Research Centre for Oceanography (RCO-LIPI); Faculty of Fisheries and Marine Science , Bogor Agricultural University (IPB); Research Center and Development for Fisheries Resources (Puslitbangkan, BALITBANG-MMAF); Research Center and Development for Marine and Coastal Resources (P3SDLP, BALITBANG-MMAF); LAMINA Foundation |
| --- | --- |

| Location (country, region/ district and commune/ city/ village/ region etc.) | Indonesia, Jakarta, Bogor, Alor and Kotawaringin Barat |
| --- | --- |
| Of which areas under protection (please indicate the name and size of protected areas or locally managed marine areas, if applicable) |  |

| Project start date | January 2016 | Project intended completion date | 30 September 2018 |
| --- | --- | --- | --- |

- PROJECT PROGRESS

  - Narrative of project progress during the past semester by Project Activity

4.1.2. Develop Dugong and Seagrass National Plan of Action (NPOA) A final draft of Dugong and Seagrass National Plan of Action is available after being developed through several expert discussions. The final draft still needs to be legalized before it is fully implemented. There were 3 meetings held after the first initial meeting on 14 June 2016, which were on 18 July, 20 September and 21 October 2016. The meetings were attended by 15-23 experts from CMB, P3SDLP, Puslitbangkan, BP2KSDI, BKIPM, PSDKP, PSDI (from MMAF); LAPAN; BIG; Ministry of Environment and Forestry;, RCO-LIPI; IPB; Sultan Ageng Tirtayasa University; LAMINA and WWF-Indonesia.

4.2.1. Establish and operate NDCC (National Dugong Conservation Committee) The future members of NDCC from CMB, BALITBANG KP, RCO LIPI, IPB, Ministry of Environment and Forestry and WWF-Indonesia have been aware of the implementation of DSCP in Indonesia and establishment of NDCC. The first initial meeting was executed on 2 August 2016. The initial meeting was then followed by another meeting on 20 September 2016. However, at this moment, CMB as the coordinator of NDCC is still waiting formal letter responses from P3SDLP (Research Center and Development for Marine and Coastal Resources) and PSDI (Directorate of Fish Resources Management). Thus, resulting in the delay of NDCC establishment and legalization by MMAF Ministerial Decree.

4.3.1. Participate in Executive Project Steering Committee for focal point/Project Coordinator Two Indonesian delegation from CMB (Mr. Firdaus Agung) and WWF-Indonesia (Ms. Casandra Tania) attended the second EPSC Meeting held in Kuala Lumpur on 1-2 November 2016. During the meeting, Mr. Firdaus Agung presented Indonesia’s progress since April 2016. A several issues regarding project implementation and needs for technical supports have been discussed with the PCT, DTG, UNEP and other 7 countries participants (Madagascar, Malaysia, Mozambique, Solomon Islands, Sri Lanka, Timor Leste and Vanuatu)..

  - Project implementation progress

| Outputs & Activities | Expected completion date | Implementation status as of end of reporting period expressed in % | Describe any problems in delivery and any changes/mitigation action required. |
| --- | --- | --- | --- |
| Output 1: Policy, planning and regulatory gaps reviewed (conservation of dugongs and seagrass ecosystems) and recommendations developed |  |  |  |
| Activity 1: Facilitate symposium to collect baseline data and project final status | 31 August 2018 | 50% | - |
| Activity 2: Develop Dugong and Seagrass National Plan of Action (NPOA) | 31 August 2016 | 100% | - |
| Activity 3: Legalize Dugong and Seagrass NPOA | 31 December 2016 | 0% | The NPOA has just accomplished. It will be legalized through a DG decree. Several internal meetings with Legal Division of MSM has been conducted to discuss on legalize process NPOAs include the NPOA of Dugong and Seagrass |
| Output 2: Advocacy programme and advocacy capacity for improved conservation management of dugongs and their seagrass ecosystems developed and implemented |  |  |  |
| Activity 4: Establish and operate NDCC (National Dugong Conservation Committee) | 30 September 2018 | 70% | CMB is still waiting formal letter responses from 2 potential NDCC members which are P3SDLP and PSDI. Communication with P3SDLP and PSDI has been running, the response letter from both of them are still in process |
| Activity 5: Facilitate NDCC regular meetings | 30 June 2018 | 0% | Delayed etablishment of NDCC cause the regular meetings of NDCC has not run yet. Serial meetings among representatives of NDCC potential members have been conducted to establish NDCC and to give inputs for DSCP activities. After decree of DG has been released the formal NDCC regular meeting will be conducted |
| Output 3: Capacity for national and regional networking and contribution to global policy for effective dugong and seagrass conservation in Indian and Pacific Ocean basins |  |  |  |
| Activity 6: Participate in Executive Project Steering Committee for focal point/Project Coordinator | 31 August 2018 | 33% | - |

  - Risk and risk management

Please describe internal and external risks (examples included in brackets) that could affect successful implementation of project activities and the proposed risk mitigation measures.

| Risk group | Description | Risk level (Low/ Medium/ High) | Mitigation measures |
| --- | --- | --- | --- |
| Project Management (team capacity, internal communication, co-financing, budget, financial management, reporting, etc.) | There is still relatively small in-kind contribution from LIPI and IPB because these 2 institutions have not allocated a dedicated budget for supporting DSCP implementation this year. | Low | LIPI and IPB needs to allocate specific independent budget for supporting DSCP implementation in year 2017. |
| Socio-cultural issues (external communications, capacity of and work with stakeholders, cultural aspects) | - | - | - |
| Political risks (Political stability in country, political impacts on the project) | There has been new organization structure implemented at the MMAF that unify the Research Agency and Human Resources Development Agency. This perhaps answers the delay of NDCC establishment, in part, the late response of the P3SDLP due to new structure adaptation. | Low | Continuous communication with key staffs that previously deal with DSCP so that we can quickly adapt with the new structure |
| Environmental risks (severe weather events/ disasters, natural causes negatively affecting project areas, habitats and species) | - | - | - |
| Other (please specify) | - | - | - |

- MONITORING AND EVALUATION

  - Please describe activities for monitoring and evaluation carried out during the reporting period.

Examples include: baseline data collection, stakeholder surveys, field surveys, steering committee meetings to assess project progress, peer review of documentation to ensure quality, mid-term review, etc.

Do not include routine project reporting.

Three public consultation meetings were held in Kotawaringin Barat on 4 August 2016, Alor on 9 August 2016 and Tolitoli on 10 August 2016 following the first public consultation held in Bintan in 19 May 2016. The objectives of the public consultation were to introduce DSCP Indonesia to local government and stakeholders, to gain support from local government, community, and other relevant stakeholders for DSCP implementation in each site, to identify specific potential area (villages) for pilot sites and to map the condition and potential in each project site. The meetings were attended by district government representatives from fisheries agency, regional development planning agency, tourism agency, environment and forestry agency, also representatives from local university and local community from some targeted villages and media. A consultation meeting with PCT (Maya Bankova) and DTG members (Nicholas Pilcher and Donna Kwan) were held on 17-18 October 2016 to assist Indonesian DSCP team to finish and submit ID3 proposal and to give notes about the proposed Mid Term Review. During those 2 day-meeting, Indonesia team managed to present its progress and discussed the proposed ID3. There was misconception about incentive scheme and an action of collecting more feedback from local community was suggested strongly by one of DTG members. A mutual understanding and commitment were achieved after the meeting, resulting in the finalization of ID3 after EPSC meeting in Kuala Lumpur, ID3 submission in December and funding agreement signing by the end of 2016.

- OTHER INFORMATION

  - Meetings

| Meeting type | Title | Venue | Dates | Convened by | Organized by | No. of participants | Report issued Y/N | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Expert group meeting | Dugong and Seagrass NPOA draft development | MMAF, Jakarta | 18 July 2016 | CMB | CMB | 15 | Y (draft 1 NPOA) | IND | 20 Jul 2016 |
| Coordination meeting | National Dugong Conservation Committee (NDCC) | Santika Hotel, Bogor | 2 Aug 2016 | CMB | CMB | 15 | N (presentation material only) | IND | 2 Aug 2016 |
| Public consultation meeting | DSCP implementation | Kotawaringin Barat Fisheries Agency Office | 4 Aug 2016 | Kotawaringin Barat Fisheries Agency | CMB | 26 | Y | IND & ENG executive summary | 22 Dec 2016 |
| Public consultation meeting | DSCP implementation | Alor Fisheries Agency Office | 9 Aug 2016 | Alor Fisheries Agency | CMB | 40 | Y | IND & ENG executive summary | 22 Dec 2016 |
| Public consultation meeting | DSCP implementation | Bumi Harapan Hotel, Tolitoli | 10 Aug 2016 | Tolitoli Fisheries Agency | CMB | 44 | Y | IND & ENG executive summary | 22 Dec 2016 |
| Expert group meeting | NDCC and Dugong and Seagrass NPOA draft development | Pajajaran Suites Hotel, Bogor | 20 Sep 2016 | CMB | CMB | 18 | Y (revision of draft NPOA) | IND | 22 Sep 2016 |
| Coordination meeting | Consultation with PCT and DTG Meeting | MMAF | 17-18 Oct 2016 | CMB | DSCP PCT | 18 | N (presentation materials only) | IND & ENG | 17 & 18 Oct 2016 |
| Expert group meeting | Dugong and Seagrass NPOA draft development | Santika Hotel, Bogor | 21 Oct 2016 | CMB | CMB | 23 | Y (final draft of NPOA) | IND & ENG | 21 Nov 2016 & 9 Jan 2017 |
| Coordination meeting | Executive Project Steering Committee | Kuala Lumpur | 1-2 Nov 2016 | DSCP PCT | DSCP PCT | 18 | Y (report from DSCP PCT & presentation material) | ENG | 9 Dec 2016 |
| Coordination meeting | EPSC follow up meeting | MMAF | 21 Nov 2016 | MMAF | MMAF | 20 | Y (minutes of meeting) | IND | 21 Nov 2016 |

  - List(s) of meeting participants

| No. | Name of participant | Nationality |
| --- | --- | --- |
| 1 | Andi Rusandi | Indonesian |
| 2 | Syamsul B. Lubis | Indonesian |
| 3 | Firdaus Agung | Indonesian |
| 4 | Suraji | Indonesian |
| 5 | Mudatsir | Indonesian |
| 6 | Erina Nelly | Indonesian |
| 7 | Ahmad Sofiullah | Indonesian |
| 8 | Yudha Miasto | Indonesian |
| 9 | Rian Puspita Sari | Indonesian |
| 10 | Dharmadi | Indonesian |
| 11 | Marina Monintja | Indonesian |
| 12 | Syifa Annisa | Indonesian |
| 13 | Abdul Karim | Indonesian |
| 14 | Anita Kusumawati | Indonesian |
| 15 | Niken | Indonesian |
| 18 | Agustin Rustam | Indonesian |
| 19 | Wawan Ridwan | Indonesian |
| 20 | Veda Santiadji | Indonesian |
| 21 | Dwi Suprapti | Indonesian |
| 22 | Yoppy Endano | Indonesian |
| 23 | Casandra Tania | Indonesian |
| 24 | Wawan Ridwan | Indonesian |
| 25 | Wawan Kiswara | Indonesian |
| 26 | Sekar Mira | Indonesian |
| 27 | Adriani Sunuddin | Indonesian |
| 28 | Juraij Bawazier | Indonesian |
| 29 | Fitriyah Anggraeni | Indonesian |
| 30 | Deny Noviana | Indonesian |
| 31 | Huda Shalahudin Darusman | Indonesian |
| 32 | Sari Novita | Indonesian |
| 33 | Indriatmoko | Indonesian |
| 34 | Muta A. Khalifa | Indonesian |
| 35 | Fitty Machmudah | Indonesian |
| 36 | Gatot Winarso | Indonesian |
| 37 | Atit Wistati | Indonesian |
| 38 | Wenni Wulansari | Indonesian |
| 39 | Rizal Rifai | Indonesian |
| 40 | Alief Farid | Indonesian |
| 41 | Haryo Indrajaya | Indonesian |
| 42 | Rizal Rifai | Indonesian |
| 43 | Haryo Indrajaya | Indonesian |
| 44 | Maya Bankova | Non Indonesian |
| 45 | Nicholas Pilcher | Non Indonesian |
| 46 | Donna Kwan | Non Indonesian |

  - Documents, other printed materials, videos, and soft products (such as CDs or websites)

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Technical Report | Technical Report-Public Consultation on DSCP Implementation in Kotawaringin Barat, Tolitoli and Alor | CMB | CMB | - | 22 December 2016 |
| 2 | Document | National Plan of Action for Dugong and Seagrass in Indonesia | CMB | CMB | - | 23 December 2016 |

| Name of Project Manager: Syamsul B. Lubis | Name of Project Manager Supervisor: Andi Rustandi |
| --- | --- |
| Signature: | Date: | Signature: | Date: |

# Footnotes

Briefly describe progress made during the previous six months highlighting major outcomes/benchmarks achieved during the period.

Information provided in “Quarterly Expenditure Report” should be in line with output/activity progress reported in this table.

Outputs and activities as described in the project proposal or in any updated project revision. Expand table as necessary.

Expand table as necessary

Meeting types: e.g. expert group meeting, project inception workshop, training workshop/seminar, partners consultation workshop, project Steering Committee meeting etc.

Expand table as necessary

Documents and printed material types: e.g. technical publication, meeting report, technical/substantive report, brochures, media releases, etc