The GEF Dugong and Seagrass Conservation Project

Project Progress Report

| Reporting Period | From: | July 2016 | To: | December 2016 |
| --- | --- | --- | --- | --- |

- PROJECT GENERAL INFORMATION

| National Project Code & Title: | LK2 - 2128 Improving communication and collaboration amongst all relevant stakeholders in Sri Lanka to enhance seagrass and dugong conservation |
| --- | --- |

| Project Partner(s): | DWC |
| --- | --- |

| Location (country, region/ district and commune/ city/ village/ region etc.) | Sri Lanka, North Western and Northern provinces, Puttalam / Mannar / Kilinochchi / Jaffna District |
| --- | --- |
| Of which areas under protection (please indicate the name and size of protected areas or locally managed marine areas, if applicable) | Bar Reef Marine Sanctuary - 30670ha Delft National Park - 1846.28 ha Adam’s Bridge Marine National Park - 18990 ha Nagarkovil Nature Reserve - 7882 ha Wedithalathive Nature Reserve - 29180 ha |

| Project start date | June 2015 | Project intended completion date | September 2018 |
| --- | --- | --- | --- |

- PROJECT PROGRESS

  - Narrative of project progress during the past semester by Project Activity

Marine Sector Conservation Plan has been developed. This will be the overall plan of marine conservation sector. A mobile base application for the communication network is developed and the equipment’s for the network has been purchased. Institutions which are the part of the communication network have been identified and they have been trained in the necessary activities. Site to establish Dugong conservation coordination centre was selected and field inspection was done to assess the suitability for establishing communication centre within the site. Marine mammal’s observation guidelines were reviewed and yet to approve from the Cabinet of the Parliament. Final validation workshop scheduled to be held within 1st quarter of the year 2017.

  - Project implementation progress

| Outputs & Activities | Expected completion date | Implementation status as of end of reporting period expressed in % | Describe any problems in delivery and any changes/mitigation action required. |
| --- | --- | --- | --- |
| Output 1: |  |  |  |
| Activity 1: Identified the Partners for communication network. | December 2016 | 100% |  |
| Output 2: |  |  |  |
| Activity 2: Marine mammal tourism guidelines reviewed | July 2017 | 90% | Need to get the approval from the Cabinet of the Sri Lanka Parliament |
| Output 3: |  |  |  |
| Activity 3: At least 5 local people recruited | March 2017 | 60% | 2 person yet to recruit |
| Activity 4: Maintenance of a database | Throughout the Project | 20% |  |
| Activity 5: Collecting information through communication network | Throughout the Project | 05% | Recently started |
| Output 4: |  |  |  |
| Activity 6: National Plan of Action | July 2017 | 0% |  |
| Activity 7: Policy framework | July 2017 | 05% | Only in the drafting process |
| Activity 8: Initial meetings, Discussions on national project planning | July 2015 | 100% |  |
| Activity 9: Staff Training | March 2017 | 20% |  |
| Activity 10: Equipment and infrastructure for communication network | December 2016 | 95% | Almost all the equipment purchased and few equipment left |

  - Risk and risk management

Please describe internal and external risks (examples included in brackets) that could affect successful implementation of project activities and the proposed risk mitigation measures.

| Risk group | Description | Risk level (Low/ Medium/ High) | Mitigation measures |
| --- | --- | --- | --- |
| Project Management (team capacity, internal communication, co-financing, budget, financial management, reporting, etc.) | Non |  |  |
| Socio-cultural issues (external communications, capacity of and work with stakeholders, cultural aspects) | Communication to the different cultural groups | Low | Communicate through local community leaders |
| Political risks (Political stability in country, political impacts on the project) | Non |  |  |
| Environmental risks (severe weather events/ disasters, natural causes negatively affecting project areas, habitats and species) | Non |  |  |
| Other (please specify) |  |  |  |

- MONITORING AND EVALUATION

  - Please describe activities for monitoring and evaluation carried out during the reporting period.

Examples include: baseline data collection, stakeholder surveys, field surveys, steering committee meetings to assess project progress, peer review of documentation to ensure quality, mid-term review, etc.

Do not include routine project reporting.

Progress has been monitored in regular progress monitoring meetings of the DWC.

- OTHER INFORMATION

  - Meetings

| Meeting type | Title | Venue | Dates | Convened by | Organised by | No. of participants | Report issued Y/N | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Steering Committee | National Facilitating Committee | IUCN | 1-07-16 | IUCN | NF | 11 | Y | English |  |
|  | National Facilitating committee | DWC | 10-10-16 | Marine unit | Marine unit | 06 | Y | English/Sinhala |  |
|  | National steering committee | DWC | 16-11-16 | Marine unit | Marine unit | 07 | Y | English/Sinhala |  |
| Training workshop | National Level awareness – Puttalam District | In Field | 04-07-16 | Marine Unit | Marine Unit | 54 | Y | English |  |
|  | National Level awareness – Jaffna District | In Field | 05-09-16 | Marine Unit | Marine Unit | 50 | Y | English |  |
|  | National Level awareness – Killinochchi District | In Field | 06-09-16 | Marine Unit | Marine Unit | 27 | Y | English |  |
|  | National Level awareness – Mannar District | In Field | 06-09-16 | Marine Unit | Marine Unit | 29 | Y | English |  |

  - List(s) of meeting participants

| No. | Name of participant | Nationality |
| --- | --- | --- |
| 1 | Dr. U.K.L. Peiris (National Facilitator) Mr. Thushan Kapurusinghe Mr. Tharanga Herath Mr. Prasanna Weerakkody Mr. H.M.D. Sajith Subashana Dr. V. Pahalawattaarachchi Dr. D.D.G.L. Dahanayaka Mr. Arjan Rajasuriya Ms. Shana Ranasinghe Ms. Matheesha Katuwawala Ms. Harini Nishshanka |  |
| 2 | Dr. U.K.L.Peiris Mr.Channa Suraweera Mr.Arjan Rajasuriya Mr. Prasanna Weerakkody Mr. H.M.D. Sajith Subhasinghe 6. Mr. Thushan Kapurusinghe | Sri Lankan |
| 3 | Dr. U.K.L.Peiris Mr.Channa Suraweera Mr.Arjan Rajasuriya Mr. Prasanna Weerakkody Mr. H.M.D. Sajith Subhasinghe Mr. D.D.G.L.Dahanayake Mr. Asanka Gunawardana | Sri Lankan |
| 4 | 1. Mr. N.H.M. Chitrananda 2. Ms. Sanjeewani Herath 3. Mr. L.D.C.Jayasinghe 4. Mr. S.P.Weerasekera 5. Mr. H.M.M.S.Herath 6. Mr. M.M.N.Somathilaka 7. Mr. G.M Somaratna 8. Mr. S. D. S. P. Sandanayake 9. Mr. R.A.Wanniarachchi 10. Mr. Anura Gunawardena 11. A.P.K.Subasinghe 12. R.M.N.Kumaratunga 13. Lt. Col. Shirantha Millagala 14. Dr. Vasantha Pahalawattaarachchi 15. Dr. Sisira Haputhantri 16. Dr. D.D.G.L. Dahanayaka 17. Mr. C.B.Medagedara 18. Mr. I.B.Amarasinghe 19. Mr. A.C.M.Shafiee 20. Mr. Y. Upul Sanjeewa 21. Mr. K.S.Perera 22. Mr. A.A.Wickramasinghe 23. Mr. A. Jayasekera 24. Mr. J.K.H.Perera 25. Mr. I.M.Sarath Chandranayaka 26. Mr. B.M.D.Balasooriya 27. Mr. Manjula Amararathna 28. Dr. U.K.L.Peiris 29. Mr. W.M.K.S.Chandrathna 30. Mr. Channa Suraweera 31. Mr. Milinda Sampath 32. Mr. P.D.L. Nirasha 33. Mr. I.D.Lakshitha Iddamalgoda 34. Mr. L.I.P.Udugama 35. Mr. Kingsley Peiris 36. Mr. H.T.R. Rajapaksa 37. Mr. M.Gunasekera 38. Mr. L.C.K.Perera 39. Mr. N.C.Dissanayake 40. Mr. L.D.Nishantha 41. Mr. I. N. Priyadarshana 42. Mr. P. G. T. T.Saranga 43. Mr. I.U. Udugamasuriya 44. Mr. R. M. C. C. Ratnayake 45. Mr. R.M.N.S.Ranasinghe 46. Mr. K.Palitha Premakumara 47. Ms. B.H.G.K. Kumari 48. Ms. S.M.Ranasinghe 49. Mr. H.M.D.Sajith Subhashana 50. Mr. Tharanga Herath 51. Mr. B.R.A.G.Kariyawasam 52. Ms. Harini Nishshanka 53. Ms. Matheesha Katuwawala 54. Mr. Arjan Rajasuriya | Sri Lankan |
| 5 | 1. Mr. N. Vethanayahan 2. Mr. P.Thayanandan 3. Mrs. S.Mathiyalagan 4. Mrs. U.Yasotha 5. Mr. S. Jeyakanth 6. Ms. S. Ahalya 7. Mr. S. Rajiev 8. Mrs. S.Nishanthy 9. Mr. A.G.Inporaja 10. Ms.S.Zibila Rose 11. Mr. J.Sivajirus 12. Mr. T.Sutharshana 13. Mr. K.K.Sivachandran 14. Mrs. T.Meera 15. Mr. R.C.Rathnayake 16. Mr. A.Thanaleden 17. Lt. Col. G.A.K.Botheju 18. Major. N. Weerasinghe 19. Major. U.G.A.N.Gunarathne 20. Captain L.G.G.Lindumahagedera 21. Captain S.P.S.A.Somasiri 22. Mr. K.Jayasinghe 23. Mr. Saman Jayasinghe 24. Flt Lt R.S.M.C. Samaranayake 25. Mr. T.S.Meedin 26. Mr. A.M.Sameera Silva 27. Mr. C.R.R.R.Fristroy 28. Mr. E.U.Edirisinghe 29. Mr. B.M.S.S.K.Basngarika 30. Mr. B.R.Ooyangodas 31. Mr. S.M.R.Senanayaka 32. Mr. J.Suthayera 33. Ms. Diana Nilochkerar 34. Mr. N.Visnuvaurthavar 35. Mr. L.Thuvarakan 36. N.M.N.K.T.Gurathilaka 37. Mr. W.M.R.Dharmabandu 38. Dr. U.K.L.Peiris 39. Mr. Channa Suraweera 40. Ms. B.H.G.K. Kumari 41. Mr. M.G.A.Gunawardana 42. Dr. Vasantha Pahalawattaarachchi 43. Dr. D.D.G.L. Dahanayaka 44. Mr. Tharanga Herath 45. Mr. M.G.G.Dhanushka 46. Mr. Thushan Kapurusinghe 47. Mr. Ranil Nanayakkara 48. Mr. Arjan Rajasuriya 49. Ms. Harini Nishshanka 50. Ms. Matheesha Katuwawala | Sri Lankan |
| 6 | 1. Mr. M.Y.S. Deshapriya 2. Mr. L.S. Croos 3. Mr. T.A. Daniel 4. Mr. B.S. Mirando 5. Lcdr. H.M.A.S.K. Herath 6. Major H.T.A. de Alwis 7. Major H.G.M. Nishantha 8. Major S. Hettiarachchi 9. Lcdr. A.P.K. Subasinghe 10. Mr. M. Paramathm 11. Mrs. M.S.C. Peiris 12. Mr. S.I. Vaz 13. Mr. S.B. Herath 14. Mr. M. Sriskandakumar 15. Mr. H.T. Sampath 16. Mr. V. Papakaran 17. Mr. N.A.P.S.S. Wichramasingha 18. Ms. M.A.W.A. Prasadi 19. Mr. Thushan Kapurusingha 20. Ms. V. Pahalawattaarachchi 21. Mr. Ranil Nanayakkara 22. Mr. U.K.L. Peiris 23. Mr. M.G.G. Dhanushka 24. Mr. Tharanga Herath 25. Mr. D.D.G.L. Dahanayaka 26. Mr. Arjan Rajasooriya 27. Dr. Lakshman Peiris 28. Mr. Channa Suraweera 29. Mr. M.T.A. Gunawardena, | Sri Lankan |
| 7 | 1. Mr. S. Sathyaseelan 2. Mr. C. Krishnadaran 3. Cdr (NP) W.S. Premarathne 4. Mr. P. Jeyararu 5. Mr. V. Thiyagaraja 6. Mr. M.M.D.N. Chathuranga 7. Mr. M. Nakkeeran 8. Mr. P. Pirashanthan 9. Mr. N. Sriranjam 10. Mr. Kapila Bandara 11. Mr. M.M.J. Ariaywansa 12. Mr. S.A.C.Roshan 13. Mr. S.Saliva 14. Mr. W.M. Sajeewa Piyasena 15. Mr. Thushan Kapurusingha 16. Ms. V. Pahalawattaarachchi 17. Mr. Ranil Nanayakkara 18. Mr. U.K.L. Peiris 19. Mr. M.G.G. Dhanushka 20. Mr. Tharanga Herath 21. Mr. D.D.G.L. Dahanayaka 22. Mr. Arjan Rajasooriya 23. Dr. Lakshman Peiris 24. Mr. Channa Suraweera 25. Mr. Shantha Weerasinghe 26. Mr. M.T.A. Gunawardena 27. Mr. W.M.R. Darmabandu | Sri Lankan |

  - Documents, other printed materials, videos, and soft products (such as CDs or websites)

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication date |
| --- | --- | --- | --- | --- | --- | --- |

| Name of Project Manager: | Name of Project Manager Supervisor: |
| --- | --- |
| Signature: | Date: | Signature: | Date: |

# Footnotes

Briefly describe progress made during the previous six months highlighting major outcomes/benchmarks achieved during the period.

Information provided in “Quarterly Expenditure Report” should be in line with output/activity progress reported in this table.

Outputs and activities as described in the project proposal or in any updated project revision. Expand table as necessary.

Expand table as necessary

Meeting types: e.g. expert group meeting, project inception workshop, training workshop/seminar, partners consultation workshop, project Steering Committee meeting etc.

Expand table as necessary

Documents and printed material types: e.g. technical publication, meeting report, technical/substantive report, brochures, media releases, etc.