The GEF Dugong and Seagrass Conservation Project

Project Progress Report

| Reporting Period | From: | 01 Jul/ 2016 | To: | 31 Dec/ 2016 |
| --- | --- | --- | --- | --- |

- PROJECT GENERAL INFORMATION

| National Project Code & Title: | LK 7. Providing incentives to local communities in return for wise stewardship of coastal habitats |
| --- | --- |

| Project Partner: | Sri Lanka Turtle Conservation Project (SLTCP) |
| --- | --- |

| Location | Six fishing villages along Puttalam lagoon, Puttalam District, North-western province, Sri Lanka. Anawasala : 8⁰13′ N 79⁰45′ E Kandakkuliya : 8⁰12′ N 79⁰42′ E Sotthupitiya : 8⁰06′ N 79⁰42′E Palliwasathurei : 8⁰11′ N 79⁰44′ E Thirikkapallama: 8⁰12′N 79⁰51′E Serakkuliya : 8⁰13′N 79⁰48′E |
| --- | --- |
| Of which areas under protection | Bar Reef sanctuary- 306. 7 sq. km Wilpattu National Park- 131667.1ha |

| Project start date | 1st May, 2015 | Project intended completion date | 30th April, 2017 |
| --- | --- | --- | --- |

- PROJECT PROGRESS

  - Narrative of project progress during the past semester by Project Activity

Activity 2.1.2- Batik group was given designs of dugongs and sea grass in their products in order to encourage conservation and awareness of the Dugong, sea grass and other marine and coastal resources. A tool kit including 3 colours of dye and other batik material for 9 members were donated to encourage the production. Some additional colours (dye) and material were donated later in the period. Activity 2.1.4 - Sewing programme is running throughout the period. Fabric material was given to manufacture cotton gift bags for the beneficiaries in August. A set of 238 cotton bags were received by the organization by paying them the sewing cost. Dugong and seagrass conservation message and images were printed on these bags. These products were used in prize giving ceremony of the ‘Werale Asiriya’ art competition while it aimed encouragement of community incentives as well as awareness of school children. Another order has been placed to get manufactured another set of cotton bags, by supplying fabric material in December. In Serakkuliya, they have started to sell their products by putting up a basic outlet. Activity 2.1.5- Monetary support to construct fish rearing tanks given to 2 sites namely Soththupitiya and Serakkuliya, 4 and 3 each. After completion of construction of tanks, Platy varieties were given to the tanks at Serakkuliya 2 times. Grown fishes were purchased by the organization from the same site. Activity 2.2.1 & Activity 2.2.2 - 19 Awareness lectures and 19 film shows on Dugong and Seagrass conservation have been conducted. The rest of awareness lectures and film shows have been planned for the next period. These target mainly fishing communities and schools. This programme included the police station and the sites located all along the Puttalam lagoon both in mainland and in peninsula. Activity 2.2.3 - ‘Werale asiriya’- National level art competition Annual art competition ‘Werale asiriya’ on marine and coastal environment for school students was conducted and prize giving ceremony was held on 3rd September. Over 500 guests participated in the event, while hon. minister of Megapolis and western development was the chief guest. The artworks were categorized as 4 sections as per age groups. 1st, 2nd and 3rd places of each section were selected and prizes and certificates were awarded. The rest of 50 best art works were selected and artists were invited to the ceremony. They were awarded credit certificates. 51st to 100th places of each section were selected and ‘commended’ certificates were posted. Selection of paintings was done by a panel of independent expert artists. Artworks that won 1st, 2nd and 3rd places for each category and 5 other best artworks of each section were displayed to the public during the prize giving ceremony. Activity 2.2.4- Production and publication of organization’s newsletter ‘Turtle News’ of Oct- December, 2016 quarter was completed. Sinhala version newsletter named ‘werale asiriya’ has been designed. The online version has been published on organization’s web site. 250 copies of ‘Turtle News’ were printed and distributed amongst relevant authorities, institutions and personnel. Activity 2.2.6 - ‘Min Visithuru’- Annual exhibition of Ornamental fish aquaria was held in convention center, Colombo on 5th to 7th August. SLTCP had a stall to exhibit Platy varieties bred under the ornamental fish breeding programme of the organization. Awards for 1st and 2nd place for Platy new varieties were won by the SLTCP. In addition, SLTCP participated in a school educational exhibition organized by and held at Defense school, Colombo on 29th September, 2016. Educational panels and turtle models were used and displayed at the stall to educate about marine and coastal resources and conservation. School children and parents of schools in Colombo and suburbs attended the exhibition. Activity 2.2.7- Several educational materials in order to be used to create awareness via lectures, workshops and exhibitions were produced. Leaflets on Mangroves, Coral reefs and turtles were produced and published. A model of dugong in fibre glass was manufactured.

  - Project implementation progress

| Outputs & Activities | Expected completion date | Implementation status as of end of reporting period expressed in % | Describe any problems in delivery and any changes/mitigation action required. |
| --- | --- | --- | --- |
| Output 2.1. Management and incentive mechanisms and tools for sustainable fisheries- pilots and capacity building (Local community and government) |  |  |  |
| Activity 2.1.1. Provide legal fishing nets to replace illegal nets | 30th June, 2016 | 100% | Income earned is less when compared to what earned form the illegal nets. |
| Activity 2.1.2. Batik programme | 30th April, 2017 | 100% | Beneficiaries more or less dependent on creativity and market finding. |
| Activity 2.1.3. Coir mat programme | 30th April, 20 | 0% | Coconut fibre, which is the raw material for products, is not produced locally. In order to initiate the production, they should be transported from southern part of the island. This is an expense that wouldn’t be effective to earn a profit by coir productions. This issue has been addressed to the PCT and decided to not to implement. |
| Activity 2.1.4. Sewing programme | 30th April, 2017 | 100% |  |
| Activity 2.1.5. Ornamental Fish breeding programme | 30th April, 2017 | 70% | - |
| Activity 2.1.6. Sea Bass aquaculture programme | 30th April, 2017 | 100% | reported in previous HYR |
| Activity 2.1.7. Crab culture programme | 30th April, 2017 | 100% |  |
| Activity 2.1.8. Provide training on marketing, branding and finance management | 31st Oct, 2016 | 0 % | Delay in final products of batik noted. After receipt of such products, this programme will be conducted. |
| Activity 2.1.9. Sign MoUs between SLTCP and beneficiaries | 31st Aug, 2016 | 100% | - |
| Activity 2.1.10. Salt packet production | 30th April, 2017 | 100% |  |
| Activity 2.1.11. Construction of 5 toilets | 31st Jan, 2016 | 80% | Time taken to construct exceeded the expected time caused by the low income of construction workers, who go for other income generating ways. |
| Activity 2.1.12. Construction of a shelter, which facilitates boat landing | 31st May, 2016 | 100% |  |
| Activity 2.1.13. Provide a water storage tank to a rural school | 31st Oct, 2015 | 100% |  |
| Activity 2.1.14. Improve facilities in two primary schools | 30th June, 2016 | 100% |  |
| Output 2.2. Awareness raising and social marketing programmes contributing to more sustainable practices (subsistence and small- scale artisanal fisheries) in target areas |  |  |  |
| Activity 2.2.1. Organize and conduct awareness lectures/workshops | 30th April, 2017 | 79% | - Sometimes less participation noted, when conducting programmes for fishing communities. They are reluctant to attend these programmes instead going fishing, which generates income for them. |
| Activity 2.2.2. Organize and conduct environmental film shows | 30th April, 2017 | 79% | - Sometimes less participation noted, when conducting programmes for fishing communities. They are reluctant to attend these programmes instead going fishing, which generates income for them. |
| Activity 2.2.3. Organize and conduct national level art competition | 31st Aug, 2016 | 100% | - |
| Activity 2.2.4. Produce online/printed newsletter | 30th April, 2017 | 80% | - |
| Activity 2.2.5. Organise a media exposure tour | 31st July, 2016 | 0% | Based on fishing season, harvesting season, and completion of products this activity is delayed to a more effective time. |
| Activity 2.2.6. Organize and conduct environmental exhibitions | 30th June, 2016 | 100% |  |
| Activity 2.2.7. Produce educational materials | 30th April, 2017 | 70% |  |
| Activity 2.2.8. Development of a website |  | 100% |  |
| Output 3.1. Critical knowledge gaps (dugongs and seagrass ecosystems) identified and surveys initiated/ completed |  |  |  |
| Activity 3.1.1. Pre socio-economic survey | 29th Feb, 2016 | 100% |  |
| Activity 3.1.2. Pre habitat assessment survey | 29th Feb, 2016 | 100% |  |
| Activity 3.1.3. Post socio-economic survey | 30th April, 2017 | 0% | - |
| Activity 3.1.4. Post habitat assessment survey | 30th April, 2017 | 0% |  |

  - Risk and risk management

| Risk group | Description | Risk level | Mitigation measures |
| --- | --- | --- | --- |
| Project Management | _ |  |  |
| Socio-cultural issues | Low concern on long term sustainability among fisher community. | Medium | Further awareness |
| Political risks | Community leaders show a tendency to give benefits to whom that support the same political party that he supports. | Medium |  |
| Environmental risks |  |  |  |
| Other (please specify) |  | Medium |  |

- MONITORING AND EVALUATION

  - Please describe activities for monitoring and evaluation carried out during the reporting period.

Project sites were visited as usual on weekly basis to observe, monitor and guide the works in progress. Both community leaders and beneficiaries were met during visits. Regular meetings with the staff members were held at the Colombo office, negotiations were done to decide future plans and changes, based on the field surveys done at each site.

- OTHER INFORMATION

  - Meetings-

Following is the list of meetings that the organization conducted with communities. Except these meetings, SLTCP participated meetings and workshops organized by national steering committee at Colombo, Puttalam, Mannar, Jaffna and Kilinochchi. The attendance sheets of educational programmes are available.

| Meeting type | Title | Venue | Dates | Convened by | Organised by | No. of participants | Report issued Y/N | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Meeting with Batik trainee group | Designs for Batik products | Kandakuliya | 19. 08. 2016 | Head of the batik trainee group | Sri Lanka Turtle Conservation Project | 11 | N | Sinhalese |  |
| Meeting with community leader | Inspection of Canal construction | Palliwasathurei | 19. 08. 2016 | Sri Lanka Turtle Conservation Project | Sri Lanka Turtle conservation Project | 3 | N | Sinhalese |  |
| Meeting with community leader | Inspection of Completion of toilet construction | Soththupitiya | 19. 08. 2016 | Sri Lanka Turtle conservation Project | Sri Lanka Turtle Conservation Project | 3 | N | Sinhalese |  |
| Meeting with the Assistant Director and relevant staff | Awareness programme on Dugong & Sea grass | District Fisheries office, Puttalam | 21. 09. 2016 | Assistant Director, Fisheries | Sri Lanka Turtle Conservation Project | 9 | N | Sinhalese |  |
| Meeting with the Principle and subject related teachers | Awareness programme on Dugong & Sea grass | Nagamaduwa Kanishta Vidyalaya, Vanathavillu | 21. 09. 2016 | Sri Lanka Turtle Conservation Project | Sri Lanka Turtle Conservation Project | 6 | N | Sinhalese |  |
| Meeting with the Principle and subject related teachers | Awareness programme on Dugong & Sea grass | Vijayapura K. vidyalaya, Vanathavillu | 21. 09. 2016 | Sri Lanka Turtle Conservation Project | Sri Lanka Turtle Conservation Project | 5 | N | Sinhalese |  |
| Meeting with Officer in Charge | Awareness programme on Dugong & Sea grass | Sri Lanka Police, Kalpitiya | 21. 09. 2016 | Sri Lanka Turtle conservation Project | Sri Lanka Turtle conservation Project | 5 | N | Sinhalese |  |
| Meeting with community leader | Project progress | Anawasala | 21. 09. 2016 | Sri Lanka Turtle conservation Project | Sri Lanka Turtle conservation Project | 4 | N | Sinhalese |  |
| Meeting with the Principle and subject related teachers | Awareness programme on Dugong | St. Sebastian Sinhala vidyalaya, Kandakuliya | 22. 09. 2016 | Sri Lanka Turtle conservation Project | Sri Lanka Turtle conservation Project | 5 | N | Sinhalese |  |
| Meeting with the Principle and subject related teachers | Dugong & Sea Grass Awareness programme on Dugong & Sea grass | Nirmala matha Sinhala maha vidyalaya, Kalpitiya | 22. 09. 2016 | Sri Lanka Turtle conservation Project | Sri Lanka Turtle conservation Project | 4 | N | Sinhalese |  |
| Meeting with the Principle and subject related teachers | Awareness programme on Dugong | Romanu Katholika Sinhala Vidyalaya, Kurinchipitiya | 22. 09. 2016 | Sri Lanka Turtle conservation Project | Sri Lanka Turtle conservation Project | 4 | N | Sinhalese |  |
| Meeting with community leader | Project progress | Soththupitiya | 22. 09. 2016 | Sri Lanka Turtle conservation Project | Sri Lanka Turtle Conservation Project | 4 | N | Sinhalese |  |
| Meeting with sewing instructor | Sewing training programme progress | Serakkuliya | 15. 11. 2016 | Sri Lanka Turtle conservation Project | Sri Lanka Turtle Conservation Project | 3 | N | Sinhalese |  |
| Meeting with beneficiaries | Ornamental fish programme | Serakkuliya | 15.11.2016 | Sri Lanka Turtle Conservation Project | Sri Lanka Turtle Conservation Project | 4 | N | Sinhalese |  |
| Meeting with beneficiaries | Progress of Batik training programme | Kandakuliya | 16.11.2016 | Leader of Batik trainee group | Sri Lanka Turtle Conservation Project |  |  |  |  |
| Meeting with community leader | Palliwasathurei | Palliwasathurei | 16. 11. 2016 | Sri Lanka Turtle Conservation Project | Sri Lanka Turtle Conservation Project. | 3 | N | Sinhalese |  |
| Meeting with community leader | Project progress | Thirikkapallama | 22.11.2016 | Sri Lanka Turtle Conservation Project | Sri Lanka Turtle Conservation Project | 4 | N | Sinhalese |  |
| Meeting with beneficiaries | Project progress | Soththupitiya | 29.11.2016 | Community leader | Sri Lanka Turtle Conservation Project | 13 | N | Sinhalese |  |
| Meeting with community leader | Project progress | Palliwasathurei | 29.11.2016 | Sri Lanka Turtle Conservation Project | Sri Lanka Turtle Conservation Project | 4 | N | Sinhalese |  |
| Meeting with community leader | Project progress | Anawasala | 29.11.2016 | Sri Lanka Turtle Conservation Project | Sri Lanka Turtle Conservation Project | 3 | N | Sinhalese |  |
| Meeting with community leader | Project progress | Kandakuliya | 30.11.2016 | Sri Lanka Turtle Conservation Project | Sri Lanka Turtle Conservation Project | 3 | N | Sinhalese |  |

  - List(s) of meeting participants- following is the list of community leaders and beneficiaries that participated in meetings (same as the previous HYR).  In addition we have added, the names of other officials that SLTCP had meetings with.

| No. | Name of participant | Nationality |
| --- | --- | --- |
|  | W.J.Sanjeewa Fernando W.J.Jayalath W.Liyo Juniper Fernando W.Priman Ackvinas H.M.Dhanajaya Madumal W.Priyantha Janaka Fernando A.Anna Biyatris W.Pradeep Gayan Fernando H.Dhanasena Silva W. Jude Asitha Prasanga W.Roshan Nishantha W. Francis Jemuni Fernando E.Chaminda Rohita W.Patum Sanjeewa A.P.Jude Nishantha W.J.Mark Thisera W.Pavulu Tissera K.A.Pathum Shirantha A.K.M.Nalir W.Kingsly Priya Shantha W.Rohan Anthony M.Hanifa Jalil W.Cristopher Fernando Jasintha Tissera W.Roshan Manjula H.M.Ranjith W.Nadeeka Sandamali W.Sangeetha Priyadharshani W.Renuka Damayanthi K.Suris Nilantha W.Mary Margaret L.Priman Aquinas W.Roshini Shashikala A.L.Dilinika W.Kusumalatha C.Thushari K.M.Nilmini H.K.Kumuduni Kurera H.A.Champika K.A.Susantha Damayanthi W.Niranjala Samanlatha R.P.Pradeepa Shiromi M.A.Chandani Isurika Dulanjali UpekkaTamali Thanuja Sudarshani Nayomi Shashikala NadeeshaTecklanthi Menaka Wasanthi Mohani Iroshani W.Sajini Kaushalya R.Manjula Dilrukshi A.K.M.Nalir W.Jude Asitha Prasanga W.Kingsly Priyashantha W.NishanthaTissera M.M.Dhananjaya Nimal Vijilas Anzar Amitha Salman Nipasi Azir M.Karunawathi Mallika Kanthi Maheshwari Suseema Deepanjali Renu Piyaseeli Amitha Priyangani Susana Dirijet Shirani Randika Other officials: Mrs. Subhashini Nonis Nonis, Principal, Nagamaduwa Kanishta Vidyalaya, Vanathavillu Mr. Pradeep Aruna Shantha Vijayapura K. vidyalaya, Vanathavillu Mr. Nazeer, Principal, Nirmala matha Sinhala maha vidyalaya, Kalpitiya Mr. Nevious Perera, Principal, St. Sebastian Sinhala vidyalaya, Kandakuliya Mr. Dissanayake Principal, Romanu Katholika Sinhala Vidyalaya, Kurinchipitiyaa Mr. Wickramasinghe, Assistant Director, District Fisheries Office, Puttalam |  |

  - Documents, other printed materials, videos, and soft products

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication date |
| --- | --- | --- | --- | --- | --- | --- |
|  | Newsletter (English- online) | Turtle News | SLTCP | SLTCP |  | 25th Nov 2016 |
|  | Newsletter (English) | Turtle News | SLTCP | SLTCP |  | 20th Nov 2016 |
|  | Educational leaflets | Mangroves, Coral reefs, Marine turtles |  | Sri Lanka Turtle Conservation Project |  | August, 2016 |

| Name of Project Manager: | Name of Project Manager Supervisor: |
| --- | --- |
| Signature: | Date: | Signature: | Date: |

# Footnotes

Outputs and activities as described in the project proposal or in any updated project revision. Expand table as necessary.