The GEF Dugong and Seagrass Conservation Project

Project Progress Report - offline

| Reporting Period | From: | July 2016 | To: | December 2016 |
| --- | --- | --- | --- | --- |

- PROJECT GENERAL INFORMATION

| National Project Code & Title: | MG 1 - 1205 Building a model for long-term community-based conservation of seagrass-dependent biodiversity in Madagascar |
| --- | --- |

| Project Partner(s): | Blue Ventures Conservation |
| --- | --- |

| Location (country, region/ district and commune/ city/ village/ region etc.) | Madagascar, Barren Isles |
| --- | --- |
| Of which areas under protection (please indicate the name and size of protected areas or locally managed marine areas, if applicable) | Barren Isles LMMA |

| Project start date | 1 August 2015 | Project intended completion date | 30 September 2018 |
| --- | --- | --- | --- |

- PROJECT PROGRESS

  - Narrative of project progress during the past semester by Project Activity

1.2.1 Training LMMA management committee and community leaders in importance of seagrasses and seagrass dependent biodiversity. After completing the mapping and habitats assessment in the Barren Isles (BI) archipelago (see 1.2.2 and 1.2.3), we presented the data during a workshop (see 1.2.4 and supporting doc 1 and 1.2) and took the opportunity to present the importance of seagrass habitats for species, the interconnection that exists between the different marine habitats and therefore the importance for managing and protecting them. As Dugongs are rarely seen in the Barren Isles at the moment we have also been doing some work with communities around sea turtles, which are an important species in the Barren Isles, to raise awareness on seagrass habitats. Vezo fishers have been traditionally hunting and eating turtles for generations, but their fishing methods have intensified through the use of nets, leading to a population decline, despite the laws protecting them. A series of workshops were held where authorities reiterated the total ban on hunting, eating and selling them and we used the opportunity to tell a story about a fictitious village that experienced negative impacts from the disappearance of turtles, highlighting their role in the ecosystems and their vulnerability. We also facilitated a debate to identify community rules which they would be ready to enforce themselves. A positive impact of this strategy could be measured during a field visit, where the Vezo Miray Representative of one village said telling the story to their community raised awareness on turtles and seagrass. This process will be repeated with each community. 1.2.2 Training in dugong biology and participatory mapping of priority seagrass habitat areas Training was completed in the last quarter and the majority of the sites were mapped then too. The remaining three sites were surveyed in July (see supporting doc 2) (1.2.3). 1.2.3 Participatory assessment and filming of priority seagrass areas within LMMA From 24 to 29 July, our team completed the participatory assessment of seagrass and coral reefs and mapped the three remaining isles (four islands were done during April - see supporting doc 2- 4.4). Priority habitat areas were defined as areas with seagrass that were close to the islands and easy to maintain if communities later decide to implement permanent or temporary reserves. The participatory mapping and assessment included community meetings where the objectives and methodology were presented. 1.2.4 Analysis and dissemination of participatory assessment through community outreach tours, and meetings with Maintirano community and authorities The results of the participatory assessment and mapping of seven islands of the BI archipelago were presented during a workshop with Vezo Miray Representatives and local authorities. One aim of the workshop was for the authorities to validate a first draft of the management measures to be integrated in the MPA Management and Zoning Plan. It was a good opportunity to talk about habitat monitoring and management, that could be further implemented with the creation of permanent or temporary reserves in those areas. 1.3.1 Participatory zoning discussions of seagrass conservation areas within all LMMA communities The participatory habitat assessment and mapping contributed greatly to the wider discussions on identifying management measures in each village, including permanent and temporary reserves, as well as traditional fishing sites. All seven sites were included in those discussions, from which we are developing the zoning plan of the protected area (still in draft format but will be shared when finalised). From 2017 on, we’ll be able to delimit more clearly the areas that Vezo have already identified as reserves. We will also be able to clarify the delimitation of Nosy Mboro, the “noyau dur” (or permanent no-take zone) of the MPA, in a way that seagrass and coral reefs are integrated. 1.3.2 Community exchange to Velondriake LMMA to observe community experiences of gear restrictions, and permanent marine reserves We invited instead Roger, ex-President of the Velondriake fishers association (in the SW), to come to Maintirano in July, and do a community outreach tour, so that all the fisher communities in the BI MPA could benefit from his presentations and testimonials. He was able to explain the advantages of implementing temporary and permanent reserves, which at the time were still scary concepts for the fishers in our zone. He also described BV’s role in supporting the fisher association which manages their resources, silencing any false rumors and beliefs that were circulating about BV at the time, an ongoing frustration that many NGOs must overcome and why clear and transparent communication is key. The rumors were spread through fear of the unknown among local Vezo, or by migrants from the south who didn’t want to have resource management in the BI, for fear that it would include regulations with negative impacts on migratory fishers. The visit from Roger was useful and a key step towards restoring the trust with the communities we work with. We also organized a community exchange from the Barren Isles to Belo-sur-Mer, right after the MIHARI forum in August (the locally managed marine areas network of Madagascar), where we discussed marine management topics including mangrove temporary reserves and community-led surveillance. 1.3.3 Development of seagrass and dugong management plan incorporating permanent protected areas for priority seagrass areas within LMMA A first set of management measures have been identified in each village, were validated with the local authorities in August 2016 and will be integrated in the MPA management and zoning plan. Some of these management measures are to establish temporary or permanent reserves with important habitats such as seagrass beds included. Nosy Mboro is still seen as a no-take area, for which we still need to clarify the delimitation in a way that it includes seagrass and coral reefs areas. 2.1.1 Enforcement of LMMA management plan through collaboration with fisheries surveillance authorities to develop a community-led Monitoring Control and Surveillance (MCS) system for combating illegal fishing activities, including industrial fishing within the LMMA Last October a consultant helped design the MCS programme for the BI MPA. We started with community meetings in both the biggest villages to present further information about community-led surveillance and get their ideas and approval. A series of workshops were conducted to determine the structure of the surveillance body (number of agents per village), identify a list of priority infractions that community agents of surveillance would act on (infractions that will be formulated in the Dina and the community set of rules for resources management of the MPA), and equipment needed. Two PV were produced, signed by the local CSP Representative and approved by the Ministry of Fisheries. We have validated the general outline of the programme with each community in the MPA. From January onwards, we need to finalise the list of priority infractions and the best ways to intervene. This will involve discussions with each community, and consultations with the local government Fisheries authorities. 2.2.1 Develop educational/awareness raising campaign targeting destructive fisheries, and raising awareness of importance of seagrass ecosystems and permanent reserves. The participatory assessment and mapping of seagrass and coral reefs in the BI archipelago was completed in July, with a second mission in Nosy Abohazo, Manandra and Marify (see last half year report). This activity had two parts: 1) a community awareness raising session and 2) the participatory assessment. The community meeting aimed to explain the reasons for the habitat assessment and mapping, and the importance of these marine ecosystems for fish stocks. The participatory assessment involved some voluntary community members to assess the habitat health and identifying the species of seagrass and corals, as well as collecting GPS points for mapping the habitats. As a result, many fishers learnt about new aspects of the habitats’ importance as part of the wider marine ecosystems and are ready to preserve them. They also were eager to participate in the habitat assessments, and declared themselves ready for the next session. 2.2.4 Analysis and dissemination of results of integrated social survey (ISS). Data from the ISS conducted in October 2014 are currently being analyzed. As key results are identified (expected in early 2017) we will be able to develop focus group discussions with communities about relevant topics in order to evaluate the current local environmental knowledge, perception of problems and possible solutions and practical actions that they are ready to undertake. We’ll also work on some different ways to disseminate the results to different audiences including communities, and other stakeholders. 2.2.5 Implementation of seagrass and dugong awareness raising campaign, including community outreach tours (COT). Any activity regarding the development of the MPA technical plans, such as the management and zoning plan, requires us to share information about and raise awareness of the importance of marine habitats and key species. To date we did this before we undertook the participatory habitats assessment and mapping, when we discussed which regulations communities are ready to reinforce themselves and whenever we work with communities to identify management measures and temporary or permanent reserves.

  - Project implementation progress

We have only included activities scheduled in our workplan for this period. We will also include any other additional activities that have occurred outside of their originally scheduled period.

| Outputs & Activities | Expected completion date | Implementation status as of end of reporting period expressed in % | Describe any problems in delivery and any changes/mitigation action required. |
| --- | --- | --- | --- |
| Output 1.2 Capacity developed for community-based stewardship (conservation and monitoring of dugongs & seagrass) | N/A | NA |  |
| 1.2.1 Training LMMA management committee and community leaders in importance of seagrasses and seagrass dependent biodiversity | Dec 2016 | 100% | Although we have completed the main work on this, we realise this needs to be an ongoing activity, so we will continue to do training with mgmt committee and leaders as is necessary. |
| 1.2.2 Training in dugong biology and participatory mapping of priority seagrass habitat areas | Aug 2017 | 90% | We have completed the participatory mapping of priority seagrass habitats but when the final zoning is decided, further work on assessing those sites may be required. |
| 1.2.3 Participatory assessment and filming of priority seagrass areas within LMMA | Feb-Oct 2016 + Aug-Dec 2017 | 50% | First round complete. A new round of participatory assessment and filming will take place when we will implement permanent and temporary reserves with each community. |
| 1.2.4 Analysis and dissemination of participatory assessment through community outreach tours, and meetings with Maintirano community and authorities | Oct 2016 | 100% | Results of the participatory assessment have been presented. However, when further monitoring activities will take place with reserves implementation, we will still go on with analyzing and presenting the results to communities and local authorities. |
| Output 1.3 Integrated community management plans (conservation and monitoring of dugong and seagrass ecosystems) developed and piloted | NA | NA |  |
| 1.3.1 Participatory zoning discussions of seagrass conservation areas within all LMMA communities | July 2016 | 100% | Completed with the participatory mapping, but to be continued with formal delimitations of temporary and permanent reserves, as well as the no-take area |
| 1.3.2 Community exchange to Velondriake LMMA to observe community experiences of gear restrictions, and permanent marine reserves | Dec 2016 + Dec 2017 | 80% | Next year, we plan to organize an exchange visit focused on MCS in the North of Madagascar (dates to be confirmed). |
| 1.3.3 Development of seagrass and dugong management plan incorporating permanent protected areas for priority seagrass areas within LMMA | May 2017 | 80% | We already have an almost complete MPA management and zoning plan, where we need to add the delimitations of the temporary and permanent reserves, as well the no take zone. From May 2017: we should have the final zoning (including temporary or permanent seagrass areas). Then we'll finalize the implementation of the MCS programme and the management measures. |
| 1.3.4 Establishment of marine mammal hunting Dina within Barren Isles LMMA | July 2017 | 10% | The final Dina will be developed along the MCS programme. In fact only the management measures and the national and regional laws they agree to implement and reinforce will be formulated in the Dina. We’ll work on this during April - May and we’ll find out if they agree to add this in their Dina |
| Output 2:Output 2.1 Management and incentive mechanisms and tools for sustainable fisheries – pilots and capacity building (local community and government) | NA | NA | NA |
| 2.1.1 Enforcement of LMMA management plan through collaboration with fisheries surveillance authorities to develop a system of community-led Monitoring Control and Surveillance (MCS) system for combating illegal fishing activities, including industrial fishing within the LMMA | June 2018 | 50% | We have elaborated the first outline of the MCS programme for the BI MPA, which have been validated by the authorities at the regional and national levels. The second part of the MCS programme development will take place around July 2017, once we have completed all the required necessary steps. |
| 2.2.1 Develop educational/awareness raising campaign targeting destructive fisheries, and raising awareness of importance of seagrass ecosystems and permanent reserves | Dec 2016 | 100% | NA |
| 2.2.3 Baseline data collected on current awareness and attitudes to seagrass conservation, and dugong sightings, within integrated socioeconomic survey | April and July/August 2016 | 100% | NA |
| 2.2.4 Analysis and dissemination of results of integrated social survey | Nov 15 - Feb 16 + Jul-Nov 16 + Jan-Apr 18 | 10% | ISS data analysis will be completed in in 2017 |
| 2.2.5 Implementation of seagrass and dugong awareness raising campaign, including community outreach tours | March 2016 onwards | 80% | NA |

  - Risk and risk management

Please describe internal and external risks (examples included in brackets) that could affect successful implementation of project activities and the proposed risk mitigation measures.

| Risk group | Description | Risk level (Low/ Medium/ High) | Mitigation measures |
| --- | --- | --- | --- |
| Project Management (team capacity, internal communication, co-financing, budget, financial management, reporting, etc.) | NA |  |  |
| Socio-cultural issues (external communications, capacity of and work with stakeholders, cultural aspects) | Limited availability of fishers as they won't participate in long meetings or events during the peak season (April-Nov). | Low | Planning in advance and undertaking all activities with Vezo Miray, Chief of camp, Psdt Fokontany. Involving them in community mobilization. |
| Political risks (Political stability in country, political impacts on the project) | Low capacity and lack of political will of fisheries authorities to implement the project/LMMA and provide effective support (surveillance particularly) as this might encompass activities that some representatives might want to keep a low profile on (due to authorities involvement in illegal fishing activities). The dismissal of the CSP Executive Director, M. Tiana, by the Minister of Halieutic Resources and Fisheries last November might affect what BV has been building so far with M. Tiana concerning the integration of a community surveillance programme with a clear set of interventions in the struggle against illegal fishing activities, in partnership with the CSP. M. Tiana was known for his integrity and genuine will to act on illegal activities. His seat which is still vacant leaves many questions unanswered and space for doubts. Impact of illegal resource extraction within the MPA. The main risk is the MPA will be seen to lack legitimacy in the eye of stakeholders (particularly fishers) if this mining company is issued with an environmental permit undermining the regulations of the MPA. Additionally these mining activities will pose environmental risks to the MPA. | Medium High Medium | Identifying key partners and provide them with effective support to help deliver expected outcomes. Need to define a MCS program allowing communities to fill-in capacity gaps. (same as above) Communicating our concerns to the Ministries who will decide whether to issue permits. Encouraging fishing communities to voice their concerns. |
| Environmental risks (severe weather events/ disasters, natural causes negatively affecting project areas, habitats and species) | Flooding during the rainy season can restrict movement or reduce some local people’s ability to attend meetings. Bad weather including heavy rains during the season and strong wind, could restrict travel by boat to the island communities. | Low | Ensure transport options and planning done well in advance of meetings and that field missions are planned in accordance with the season and the weather forecast. |
| Other (please specify) |  |  |  |

- MONITORING AND EVALUATION

  - Please describe activities for monitoring and evaluation carried out during the reporting period.

Examples include: baseline data collection, stakeholder surveys, field surveys, steering committee meetings to assess project progress, peer review of documentation to ensure quality, mid-term review, etc.

Do not include routine project reporting.

We collected dugong sightings from LMMA management committees during the October 28th training session. We continue to gather informal feedback at the end of community meetings to try to improve the techniques and approaches we use to specific subjects. We didn’t have formal project monitoring and evaluation tools implemented during this reporting period. However, we constantly seek for feedback from communities, especially their representatives, as we work in the field and visit fairly regularly every village (about once a month). We try to develop activities that develop in a logical way, where most of fishers are able to follow and understand the whole process. We can assess their level of understanding and their readiness during meetings and informal talks. The VM Representatives are often our reference for evaluating if our methods are effective, and they also help us then clarify the message and the explanations to the wider communities. We have taken into account the reviewers comments and these have been answered in a separate document (also uploaded to dropbox).

- OTHER INFORMATION

  - Meetings

| Meeting type | Title | Venue | Dates | Convened by | Organised by | No. of participants | Report issued Y/N | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Community meeting | Consultation on creating a permanent reserve ; Presentation of S. Roger | Nosy Lava | 01/07 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | Y | French | 19/08 |
| 2. Community meeting | Management measures identification and validation; Presentation of S. Roger | Nosy Maroantaly | 02-03/07 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | Y | French | 19/08 |
| 3. Community meeting | Presentation of S. Roger | Ampandikoara | 04/07 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | Y | French | 19/08 |
| 4. Community meeting | Management measures identification and validation; Presentation of S. Roger | Beloba | 05/07 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | Y | French | 19/08 |
| 5. Community meeting | Presentation of S. Roger | Manombo | 06/07 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | Y | French | 19/08 |
| 6. Community meeting | Presentation of S. Roger | Nosy Marify | 07/07 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | Y | French | 19/08 |
| 7. Community meeting | Awareness raising about habitats and participatory mapping | Nosy Abohazo | 24-25/07 | Blue Ventures | Vezo Miray, Blue Ventures |  | Y | English | 02/08 |
| 8. Community meeting | Awareness raising about habitats and participatory mapping | Nosy Manandra | 26-27/07 | Blue Ventures | Vezo Miray, Blue Ventures |  | Y | English | 02/08 |
| 9. Community meeting | Awareness raising about habitats and participatory mapping | Nosy Marify | 28-29/07 | Blue Ventures | Vezo Miray, Blue Ventures |  | Y | English | 02/08 |
| 10. Workshop | Presentation of mapping results | Maintirano | 18/08 | Blue Ventures | Blue Ventures |  | Y | French | 29/08 |
| 11. Community meeting | Discussion on the MCS programme | Ambalahonko | 11/10 | Blue Ventures | Vezo Miray, Blue Ventures |  | N |  |  |
| 12.Community meeting | Discussion on the MCS programme | Ampasimandroro sector 1-2 | 12/10 | Blue Ventures | Vezo Miray, Blue Ventures |  | N |  |  |
| 13.Community meeting | Discussion on the MCS programme | Ampasimandroro sector 3 | 13/10 | Blue Ventures | Vezo Miray, Blue Ventures |  | N |  |  |
| 14. Workshop | Elaborating the general ouline of the MCS programme | Maintirano | 17-22/10 | Blue Ventures | Blue Ventures |  | Y | French | 02/11 |
| 15.Community meeting | Public validation of the general outline of the MCS programme | Nosy Manandra | 09-10/11 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | N |  |  |
| 16.Community meeting | Public validation of the general outline of the MCS programme | Nosy Maroantaly | 11/11 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | N |  |  |
| 17.Community meeting | Public validation of the general outline of the MCS programme | Nosy Lava | 12/11 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | N |  |  |
| 18.Community meeting | Public validation of the general outline of the MCS programme | Nosy Andrano - Mangily | 13/11 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | N |  |  |
| 19.Community meeting | Public validation of the general outline of the MCS programme | Ampandikoara | 18/11 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | N |  |  |
| 20.Community meeting | Public validation of the general outline of the MCS programme | Beloba | 19/11 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | N |  |  |
| 21.Community meeting | Public validation of the general outline of the MCS programme | Manombo | 20/11 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | N |  |  |
| 22.Community meeting | Public validation of the general outline of the MCS programme | Soahany | 23/11 | Vezo Miray, Blue Ventures | Vezo Miray, Blue Ventures |  | N |  |  |

  - List(s) of meeting participants

| No. | Name of participant | Nationality |
| --- | --- | --- |
| 1, 2, 3, 4, 5, 6, 10, 11, 12, 13, 14 | Cecile Fattebert, BV | Swiss |
| 7, 8, 9, 10 | Kevin Chambon, BV | French |
| 7, 8, 9, 10, 11, 12, 13, 14 | Jean-Berthieu Nomenjanahary, BV | Malagasy |
| 1, 2, 3, 4, 5, 6, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21 | Abdou Bin Julien Felix, BV | Malagasy |
| 1, 2, 3, 4, 5, 6, 10, 14, 22 | Toalidy, BV | Malagasy |
| 11, 12, 13, 14 | Charles Andrianaivojaona, Consultant BV | Malagasy |
| 10, 14 | Hery , DR-EEF Melaky | Malagasy |
| 10 | Gaetan Evariste, DR-RHP Melaky | Malagasy |
| 14 | Jantie, CSP Melaky | Malagasy |
| 1, 10, 14, 17 | Romule, VM Representative Nosy Lava | Malagasy |
| 1, 10, 14, 17 | Marie-Hélène, VM Representative Nosy Lava | Malagasy |
| 1, 10, 14, 17 | Kaposy, VM Representative Nosy Lava | Malagasy |
| 1, 17 | Fishers Nosy Lava | Malagasy |
| 2, 10, 14, 16 | Robustin, VM Representative Nosy Maroantaly | Malagasy |
| 2, 10, 14, 16 | Gervais, VM Representative Nosy Maroantaly | Malagasy |
| 2, 10, 14, 16 | Dada Fleur, VM Rep Nosy Maroantaly | Malagasy |
| 2, 16 | Fishers Nosy Maroantaly | Malagasy |
| 3, 10, 14, 19 | Zazah, VM Rep Ampandikoara | Malagasy |
| 3 10, 14, 19 | Bisou, VM Rep Ampandikoara | Malagasy |
| 3, 19 | Fishers Ampandikoara | Malagasy |
| 4, 10, 14, 20 | Lidon, VM Rep Beloba | Malagasy |
| 4, 10, 14, 20 | Fahita, VM Rep Beloba | Malagasy |
| 4, 20 | Fishers Beloba | Malagasy |
| 5, 10, 14, 21 | Tsevilimana, VM Rep Manombo | Malagasy |
| 5, 10, 14, 21 | Mahatsiaro, VM Rep Manombo | Malagasy |
| 5, 10, 14, 21 | Andreneha, VM Rep Manombo | Malagasy |
| 5, 10, 14, 21 | Tsaramisy, VM Rep Manombo | Malagasy |
| 5, 21 | Fishers Manombo | Malagasy |
| 6, 9, 10, 14 | Keita, VM Rep Nosy Marify | Malagasy |
| 6, 9, 10, 14 | Haja Aristide, VM Rep Nosy Marify | Malagasy |
| 6, 9, 10, 14 | Peliny, VM Rep Nosy Marify | Malagasy |
| 6, 9 | Fishers Nosy Marify | Malagasy |
| 7, 10, 14 | Covin, VM Rep Nosy Abohazo | Malagasy |
| 7, 10, 14 | Filgence,VM Rep Nosy Abohazo | Malagasy |
| 7, 10 | Fishers Nosy Abohazo | Malagasy |
| 8, 14, 15 | Fishers of Nosy Manandra | Malagasy |
| 10, 12, 14 | Boto Robert VM Rep Ampasimandroro | Malagasy |
| 10, 12, 14 | Kina, VM Rep Ampasimandroro | Malagasy |
| 10. 12, 14 | Benoît Bonald, VM Rep Ampasimandroro | Malagasy |
| 10, 12, 14 | Elisa, VM Rep Ampasimandroro | Malagasy |
| 12, 13, 14 | Fishers Ampasimandroro | Malagasy |
| 10, 11, 14 | Hervé, VM Rep Andranovoribe Namela | Malagasy |
| 10, 11, 14 | Paul, VM Rep Ambanin’ni Anglais Namela | Malagasy |
| 10, 11, 14 | Zakany Marcellin, VM Rep Ambalahonko Namela | Malagasy |
| 10, 11, 14 | Malama, VM Rep Ambalahonko Namela | Malagasy |
| 10, 11, 14 | Saba, VM Rep Ambalahonko Namela | Malagasy |
| 11, 14 | Fishers Namela | Malagasy |
| 10, 14, 18 | Jean-Baptiste Zamba, RepVM Nosy Andrano-Mangily | Malagasy |
| 10, 14, 18 | Tovo RepVM Nosy Andrano-Mangily | Malagasy |
| 18 | Fishers Nosy Andrano-Mangily | Malagasy |
| 10, 14, 22 | Zafisoa, VM Rep Soahany | Malagasy |
| 10, 14, 22 | Rufin, VM Rep Soahany | Malagasy |
| 10, 14, 22 | Naina, VM Rep Soahany | Malagasy |
| 10, 14, 22 | Kakany, VM Rep Soahany | Malagasy |
| 22 | Fishers Soahany | Malagasy |

  - Documents, other printed materials, videos, and soft products (such as CDs or websites)

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Powerpoint presentation | Community presentatin on mapping results (Cartographie participative des habitats marins de l’archipel des Îles Barren) | Kevin Chambon | NA | NA | NA |
| 1.2 | Report | Report on mission to present results ( Atelier formation des représentants Vezo Miray Nosy Barren, 17-18.08.2016: Rapport) | Cecile Fattebert | NA | NA | NA |
| 2 | Report | Mapping mission report | Jean Berthieu Nomenjanahary | NA | NA | NA |
| 3 | Excel | Mapping data global (results form mapping missions) | Kevin Chambon | NA | NA | NA |
| 4 | Maps | Habitats mapping the BI archipelago - 4 maps | Kevin Chambon | NA | NA | NA |
| 5 - 5.2 | Doc | Briefing documents about the mapping which include the method | Kevin Chambon |  |  |  |
| 6 | Pictures | Seagrass in the BI archipelago | Kevin Chambon | NA | NA | NA |
| 7 | PV | Minutes from the workshop series about the MCS programme development for the BI MPA (17-22.10.2016) | Charles Andrianaivojaona | NA | NA | NA |
| 7 | PV | Minutes from the workshop series about the MCS programme development for the BI MPA (22.10.2016 | Charles Andrianaivojaona | NA | NA | NA |
| 7 | Report | Atelier d’élaboration du programme MCS pour l’AP Îles Barren : Rapport | Cecile Fattebert | NA | NA | NA |

| Name of Project Manager: Cecile Fattebert | Name of Project Manager Supervisor: Frances Humbers |
| --- | --- |
| Signature: | Date: 10/01/2017 | Signature: | Date: 10/01/2017 |

# Footnotes

Briefly describe progress made during the previous six months highlighting major outcomes/benchmarks achieved during the period.

Information provided in “Quarterly Expenditure Report” should be in line with output/activity progress reported in this table.

Outputs and activities as described in the project proposal or in any updated project revision. Expand table as necessary.

Expand table as necessary

Meeting types: e.g. expert group meeting, project inception workshop, training workshop/seminar, partners consultation workshop, project Steering Committee meeting etc.

Expand table as necessary

Documents and printed material types: e.g. technical publication, meeting report, technical/substantive report, brochures, media releases, etc.