The GEF Dugong and Seagrass Conservation Project

Project Progress Report

| Reporting Period | From: | July 2016 | To: | December 2016 |
| --- | --- | --- | --- | --- |

- PROJECT GENERAL INFORMATION

| National Project Code & Title: | MG 2 - 2106: Fisher knowledge, awareness and behaviour change for the conservation of dugongs and seagrass using the Mihari network of Locally Managed Marine Areas in Madagascar. |
| --- | --- |

| Project Partner(s): | Blue Ventures Conservation |
| --- | --- |

| Location (country, region/ district and commune/ city/ village/ region etc.) | Madagascar |
| --- | --- |
| Of which areas under protection (please indicate the name and size of protected areas or locally managed marine areas, if applicable) | NA |

| Project start date | 1st August 2015 | Project intended completion date | 30th September 2018 |
| --- | --- | --- | --- |

- PROJECT PROGRESS

  - Narrative of project progress during the past semester by Project Activity

Some of the activities scheduled for this period are a little delayed due to limited staff capacity (previously only one full-time staff member). However, a technical assistant and a consultant were recruited in November 2016 to support MIHARI in the fulfillment of the Dugong and Seagrass Project. They started to identify priority sites from 10 December 2016 and have identified three potential sites in Ambanja, Ankazomborona and Analalava where the now expanded MIHARI team will continue education/awareness, participatory mapping training and Dina support at the start of 2017. 3.1.3. Methods and training materials identified and developed tailored to needs of community for participatory mapping. From 21 to 23 November, training was organized for the MIHARI team in Antananarivo with Ms Yvette Razafindrakoto, well known as a marine mammal expert in Madagascar, particularly dugongs. The MIHARI team received training on the biology of dugongs, the methodologies and tools for participatory mapping, the approaches to conduct community awareness and education on dugongs and general information about relevant criteria useful for site identification. This will allow us to deliver on the project more effectively as it allowed the team to identify the approaches and training tools to use, to develop the community participatory mapping activity and gave us an idea of the best sites to choose. 3.1.4 Training in participatory mapping of priority seagrass habitat areas at selected LMMA sites. Three priority sites have been identified for participatory seagrass mapping: Ankazomborona, Nosy Faly and Anjajavy. We will begin training community leaders in March 2017 from these sites. This will be based on the training that the MIHARI team received on how to conduct participatory seagrass mapping and combined with the methodologies that the national partners are using, based on Seagrass-Watch methodology. 3.1.5 Training in participatory mapping of priority seagrass habitat areas at Mihari forum 2016. Awareness on how this training will be conducted at the LMMA level was provided to around 70 people from NGOs and communities by C3 at the regional MIHARI forum during the Dugong education and awareness day on 8 July 2016 in Nosy Hara (see 2.2.5). 3.1.6 Participatory data collection Training on participatory mapping are planned from March, so, this activity will begin in April. 2.2.1 Selection of key LMMA sites for further community-based awareness work. Four priority sites have been selected in the north west of Madagascar: Nosy Faly (Ambanja), Ankazomborona (Ambilobe), Analalava and Anjajavy (both north of Mahajanga), through focus groups made by the MIHARI team from 10 to 16 December and 5 to 6 January for Anjajavy (see supporting docs - two reports from missions). More sites will be identified/ selected in January 2017 based on information about remaining Dugong hotspots in the northwest where national partners of the GEF Dugong and Seagrass Project are not yet working but where other MIHARI partners are involved. 2.2.2 Baseline data collected on current awareness. MIHARI organised some events where we collected information on community awareness of Dugongs: at the MIHARI regional forum in the northwest from 4 to 7 July 2016 in Ambanja; Dugong education and awareness day on 8 July 2016 in Nosy Hara; at the national days of fisheries and aquaculture from 29 September to 2 October 2016 and at the Dugong Festival organized by COSAP Sahamalaza in Nosy Berafia from 28 to 29 October 2016. During the site identification activities in Ambilobe, Ampasindava, Ambanja, Anjajavy and Analalava, the questionnaires also included some questions on community awareness regarding Dugongs. Five main findings emerged during those activities: Fishers can recognize Dugongs and seagrass among other species/ habitats and have interesting information about their biology and their traditional use and importance. Fishers are all able to identify Dugongs and seagrass hotspots in their village. All fishers the MIHARI team have met have seen Dugongs at least once. Communities are aware that the number of Dugongs have declining compared to the last decade and seeing them now is unbelievable Despite this, only half of the communities we met understood that they should change their behaviour when seeing Dugongs as they are now rare. The data collected during those activities will help the MIHARI team to define how the network will be used to raise awareness about Dugongs and deliver education activities in 2017 that are tailored to gaps in the communities’ existing knowledge. 2.2.3 Develop educational campaign/social marketing campaign. Based on the information we gathered during the baseline data collection sessions, the MIHARI team is now in the process of compiling the education tools we will use for the social marketing campaigns, by combining materials already being used by national partners and adapting them into the specific context or message we are trying to convey. These are expected to be completed by March 2017. 2.2.5. Environmental education and awareness delivered to participants of 2016 & 2017 regional and national Mihari fora. An education and awareness day was organised during the MIHARI Regional forum on 8 July in Nosy Hara – Diego. The event was co-organized with C3 and MNP Nosy Hara and attended by over 70 people (LMMA, Regional authorities and NGO in the Northwest). At the beginning of the event, some questions were asked to gain an understanding of participants’ current awareness on Dugongs and seagrass. Then, the three national partners, including MIHARI, C3 and COSAP Sahamalaza made presentations about their projects: MG2, MG3 and MG4. In addition to presentations, the junior ecoguard, a group of scholars from Diego supported by C3 provided some sketches about the importance of Dugongs and the threats. C3 also provided some training on how they engage communities in participatory mapping and seagrass watch. At the end of the education day, some games took place where a few questions were asked to the participants about what they learned from the day and where MIHARI gave prizes to all those able to correctly answer questions such as MIHARI t-shirts, caps and key chains. 1.1.1. Current LMMAs and hotspots identified in 3.1. assessed for priority sites for dugong and seagrass LMMAs. Based on the training provided to the MIHARI team in October 2016, the following 5 criteria were used to identify the priority sites: Historical data about Dugongs (eg: the last time when a Dugong was seen in the site) Availability of data about Dugong in the site Availability of data about seagrass in the site (mapping) Availability of information about threats of Dugongs Existence of supporting partners in the site Based on those criteria, five priority sites were selected: Nosy Faly supported by Blue Ventures, Ankazomborona supported by WWF, Ampasindava supported by Missouri Botanical Garden, Analalava supported by Opti-Pousse-Haie and Anjajavy supported by Anjajavy le lodge. 1.1.2. Dina from LMMAs within priority sites reviewed (and amended if necessary) to protect dugongs and seagrass. MIHARI is planning to provide financial and technical support to the community of Nosy Hara in the establishment of their Dina. Madagascar National Parks (MNP) works in the Park and MIHARI will provide additional support to integrate aspects of dugong conservation into the dina. Consultation is planned for January 2017. The Nosy Hara community would like to use a local convention that will allow them to decide the regulations and rules for use of the fishing zone within the MPA. They are convinced that the management plan they are using now is not sufficient to effectively manage the areas they use in the park. MIHARI is also planning to provide support in the elaboration of the Dina of some new sites where the network is starting to work, such as Anjajavy and Analalava. 1.1.3. Technical support provided to new LMMA site for seagrass and dugong established. The Dugong team is having a coordination meeting on 16 January to finalise the planning for the different levels of technical support that will be provided for each site selected. The supporting activities will then start from March 2017.

  - Project implementation progress

| Outputs & Activities | Expected completion date | Implementation status as of end of reporting period expressed in % | Describe any problems in delivery and any changes/mitigation action required. |
| --- | --- | --- | --- |
| Output 3.1 Critical knowledge gaps (dugongs and seagrass ecosystems) identified and surveys completed | NA | NA | NA |
| 3.1.1. Questionnaire sent to NGO partners to complete using community focus groups for preparation before national Mihari forum 2015. | December 2015 | 100% |  |
| 3.1.2 Organisation of dugong and seagrass information gathering at regional and national Mihari fora in 2016. | July 2016 | 100% |  |
| 3.1.3. Methods and training materials identified and developed tailored to needs of community for participatory mapping. | February 2017 | 60% | - A MOU with 2 national partners established which will allow the sharing of their participatory mapping methodology. - Organization of a 3 days training on Dugong and seagrass conservation methodology to the MIHARI team by a Dugong expert – and draft a guide on how to conduct the participatory mapping. |
| 3.1.4 Training in participatory mapping of priority seagrass habitat areas at selected LMMA sites. | March 2017 | 5% | The recruitment of additional team took more time than expected. MOU with the national partners took time |
| 3.1.5 Training in participatory mapping of priority seagrass habitat areas at Mihari forum 2016. | March 2017 | 0% | The process was outlined at the MIhari fora and training with community members will take place early in 2017. Identifying sites took longer than expected due to the lack of a team to work on it and the lack of proper methodology to select the priority sites and to elaborate the training tools. |
| 3.1.6 Participatory data collection | April 2017 | 0% | Site identification took more time than expected due to limited team members to work on it and the methodology to select the priority sites and to elaborate the training tools had not yet been decided. |
| Output 2.2 Awareness raising and social marketing programmes contributing to more sustainable practices (subsistence and small-scale artisanal fishers) in target areas | NA | NA | NA |
| 2.2.1 Selection of key LMMA sites for further community-based awareness work. | January 2017 | 90% |  |
| 2.2.2 Baseline data collected on current awareness. | January 2017 | 90% |  |
| 2.2.3 Develop educational campaign/social marketing campaign. | February 2017 | 80% |  |
| 2.2.7 Assessment of long-term sustainable financing mechanisms for LMMAs and MIHARI support | April 2017 | 40% |  |
| Output 1.1 Governance structures for community involvement in conservation and monitoring of dugong and seagrass ecosystems established or strengthened in target areas | NA | NA | NA |
| 1.1.1. Current LMMAs and hotspots identified in 3.1. assessed for priority sites for dugong and seagrass LMMAs. | December 2016 | 100% |  |
| 1.1.2. Dina from LMMAs within priority sites reviewed (and amended if necessary) to protect dugongs and seagrass. | Decembery 2017 | 40% |  |
| 1.1.3. Technical support provided to new LMMA site for seagrass and dugong established. | September 2018 | 30% |  |

  - Risk and risk management

Please describe internal and external risks (examples included in brackets) that could affect successful implementation of project activities and the proposed risk mitigation measures.

| Risk group | Description | Risk level (Low/ Medium/ High) | Mitigation measures |
| --- | --- | --- | --- |
| Project Management (team capacity, internal communication, co-financing, budget, financial management, reporting, etc.) | NA | NA |  |
| Socio-cultural issues (external communications, capacity of and work with stakeholders, cultural aspects) | NA | NA | NA |
| Political risks (Political stability in country, political impacts on the project) | NA | NA | NA |
| Environmental risks (severe weather events/ disasters, natural causes negatively affecting project areas, habitats and species) | NA | NA | NA |
| Other (please specify) | Potential sites are located in remote areas with weak access by transportation Potential sites are orphans (no NGO supporting them) – will be difficult for MIHARI (restricted team) to conduct the project there without the help of a supporting NGO Unrealistic expectations of the whole MIHARI partners into the project (a number of LMMAs are having issues in Dina creation but they are not Dugong hotspots, therefore MIHARI cannot support them via this project). Difficult to get up to date data about Dugongs from fishers | Medium Low | 1. Priority for those who are easier to access 2. Priority for the sites with a promising future with MIHARI 3. MIHARI will produce posters and guidance on Dina creation steps and tools – that will be shared with them 4. For each site, the team identified a focal point who will be able to identify the relevant fishers who will be able to provide updated info about Dugongs |

- MONITORING AND EVALUATION

  - Please describe activities for monitoring and evaluation carried out during the reporting period.

Examples include: baseline data collection, stakeholder surveys, field surveys, steering committee meetings to assess project progress, peer review of documentation to ensure quality, mid-term review, etc.

Do not include routine project reporting.

At the end of the dugong education day on 8 July in Nosy Hara, we gathered information feedback on how useful the information provided to them that day was. Some of them did not know about Dugong biology and that the NW was a Dugong hotspot but everyone was satisfied with the information we provided. A MIHARI database is being developed which contains information about MIHARI partners and LMMAs (contacts, dinas (local laws), types of closures, challenges, experiences, etc), the idea is that it allows MIHARI to track progress and the sharing of learning between LMMAs. The first draft has been presented to MIHARI partners in order gather comments, suggestions and opinion before starting the work to remodel the database. We have since created more structure in the database, and added more information fields to it. Work is currently in progress to create a user friendly questionnaire and glossary that can be used by partners to update and expand the information held in the database - using a web based system. The plan is to do an initial soft launch in March.

- OTHER INFORMATION

  - Meetings

| Meeting type | Title | Venue | Dates | Convened by | Organised by | No. of participants | Report issued Y/N | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Education workshop | Dugong education and awareness day | Nosy Hara-Diego | 8 July 2016 | MIHARI | MIHARI | 75 | Yes | French | 10 August 2016 |
| 2. Focus group | Focus group with fishers for the site identification | Ambanja, Ambilobe and Analalava | 08 – 14 December 2016 | MIHARI | MIHARI | 130 | Yes | French | 4 January 2017 |

  - List(s) of meeting participants

| N° | Name of Participants | Nationality | Organizations |
| --- | --- | --- | --- |
| 1 | Adrian Levrel | French | Blue Ventures |
| 2 | Ahmed Ben Youssouf | Malagasy | LMMA Community Member |
| 3 | Albert Tombo | Malagasy | LMMA Community Member |
| 4 | Amoza Baraka | Malagasy | LMMA Community Member |
| 5 | Angela Varisoa | Malagasy | LMMA Community Member |
| 6 | Antonjara Moussa | Malagasy | LMMA Community Member |
| 7 | Athouman Tomboravo | Malagasy | LMMA Community Member |
| 8 | Augustin Randrianasolo | Malagasy | LMMA Community Member |
| 9 | Augustine Tsara | Malagasy | LMMA Community Member |
| 10 | Bakarizafy Hervé | Malagasy | MNP Nosy Hara |
| 11 | Bernardin Raphael | Malagasy | LMMA Community Member |
| 12 | Bernardine Ramanamiary | Malagasy | DELC |
| 13 | Clément Mercia | Malagasy | LMMA Community Member |
| 14 | Dominique Voca | Malagasy | SAGE |
| 15 | Edmond Ramadany | Malagasy | LMMA Community Member |
| 16 | Emmanuel Jaoravoana | Malagasy | LMMA Community Member |
| 17 | Estephania | Malagasy | LMMA Community Member |
| 18 | Etienne Rakotonirina | Malagasy | LMMA Community Member |
| 19 | Eugène Matanjaka | Malagasy | LMMA Community Member |
| 20 | Fanony | Malagasy | LMMA Community Member |
| 21 | Félicien Pierre | Malagasy | LMMA Community Member |
| 22 | Félix Randrianasolo | Malagasy | LMMA Community Member |
| 23 | Fenonirina Rakotoarisoa | Malagasy | LMMA Community Member |
| 24 | Géneviève | Malagasy | LMMA Community Member |
| 25 | Georgette Rasoatsara | Malagasy | LMMA Community Member |
| 26 | Gisèle Soa | Malagasy | LMMA Community Member |
| 27 | Grégoire Masizara Famoeza | Malagasy | LMMA Community Member |
| 28 | Guy Célestin Rakotovao | Malagasy | LMMA Community Member |
| 29 | Hasimbola Razafimahefa | Malagasy | GIZ |
| 30 | Heritiana Rakotomalala | Malagasy | WWF |
| 31 | Houssen | Malagasy | LMMA Community Member |
| 32 | Hubert Rakotondrasoa | Malagasy | LMMA Community Member |
| 33 | Ifandeza Miseza | Malagasy | LMMA Community Member |
| 34 | Ignace Vandry | Malagasy | LMMA Community Member |
| 35 | Ihando Andrianjafy | Malagasy | DREEF BOENY |
| 36 | Isdine Andriamalaza | Malagasy | LMMA Community Member |
| 37 | Jaolisy Tolizara | Malagasy | LMMA Community Member |
| 38 | Jaomahazaka | Malagasy | LMMA Community Member |
| 39 | Jaoravo | Malagasy | LMMA Community Member |
| 40 | Jaosoa | Malagasy | LMMA Community Member |
| 41 | Jean Baptiste Zavatra | Malagasy | MNP Sahamalaza |
| 42 | Jery Léoness Raminosoa | Malagasy | Direction regionale du tourisme |
| 43 | Jinoro | Malagasy | LMMA Community Member |
| 44 | Jocelyn Eric Alson | Malagasy | LMMA Community Member |
| 45 | Justin Kinkou | Malagasy | LMMA Community Member |
| 46 | Lezava Guy Tiandraza | Malagasy | LMMA Community Member |
| 47 | Lidwia Rasoanandrasana | Malagasy | LMMA Community Member |
| 48 | Mamy Arthur | Malagasy | LMMA Community Member |
| 49 | Mamy Tiana Rakotonirina | Malagasy | GIZ |
| 50 | Maoulide Abdallah | Malagasy | LMMA Community Member |
| 51 | Marcelin Sanosy | Malagasy | LMMA Community Member |
| 52 | Michel Razafy | Malagasy | LMMA Community Member |
| 53 | Nantenaina Tahiry Andriamalala | Malagasy | PHE |
| 54 | Nicholas | Malagasy | LMMA Community Member |
| 55 | Noel Raymond Avilaza | Malagasy | LMMA Community Member |
| 56 | Ralison Voahangy Aimée | Malagasy | DREEF SOFIA |
| 57 | Raymond Isaia | Malagasy | COSAP Sahamalaza |
| 58 | Razafiarison | Malagasy | LMMA Community Member |
| 59 | Richard Adrien | Malagasy | LMMA Community Member |
| 60 | Rosine Hantasoa Kazy | Malagasy | CIRHP Nosy Be |
| 61 | Said Boana | Malagasy | LMMA Community Member |
| 62 | Saidou | Malagasy | LMMA Community Member |
| 63 | Santisy A.Andriamiravo | Malagasy | WCS |
| 64 | Solofo Andry Randriamanantena | Malagasy | LMMA Community Member |
| 65 | Sylvie Raharimalala | Malagasy | DRRHP Diana |
| 66 | Tahina Andranady Ralaifanasina | Malagasy | C3 |
| 67 | Tahiry Andrianjafimanana | Malagasy | C3 |
| 68 | Tinanty | Malagasy | LMMA Community Member |
| 69 | Tombohasy | Malagasy | LMMA Community Member |
| 70 | Tsiferana Rafaliarimanana | Malagasy | MIHARI |
| 71 | Vatosoa Rakotondrazafy | Malagasy | MIHARI |
| 72 | Velondraza | Malagasy | LMMA Community Member |
| 73 | Velonjara Philgence | Malagasy | LMMA Community Member |
| 74 | Yacinthe Razafimandimby | Malagasy | CI |
| 75 | Zeze Barthelemy | Malagasy | LMMA Community Member |
| 76 | Sebane Ben Said | Malagasy | Communauté Marotaolana |
| 77 | Levelo | Malagasy | Communauté Marotaolana |
| 78 | Antila | Malagasy | Communauté Marotaolana |
| 79 | Tsaramanana | Malagasy | Communauté Marotaolana |
| 80 | Eloi | Malagasy | Communauté Marotaolana |
| 81 | Paly Alimidy | Malagasy | Communauté Marotaolana |
| 82 | Sidiny | Malagasy | Communauté Marotaolana |
| 83 | Hadje | Malagasy | Communauté Marotaolana |
| 84 | Tsarahita | Malagasy | Communauté Marotaolana |
| 85 | Zokintonga | Malagasy | Communauté Marotaolana |
| 86 | Bertran | Malagasy | Communauté Marotaolana |
| 87 | Lemainty | Malagasy | Communauté Marotaolana |
| 88 | Désiré | Malagasy | Communauté Marotaolana |
| 89 | Patric | Malagasy | Communauté Marotaolana |
| 90 | Aliphane | Malagasy | Communauté Marotaolana |
| 91 | Fitariha | Malagasy | Communauté Fongony |
| 92 | Zilio | Malagasy | Communauté Fongony |
| 93 | Jocellin | Malagasy | Communauté Fongony |
| 94 | Tepera | Malagasy | Communauté Fongony |
| 95 | Dada | Malagasy | Communauté Fongony |
| 96 | Mbodiny | Malagasy | Communauté Fongony |
| 97 | Rastany | Malagasy | Communauté Fongony |
| 98 | Dodona | Malagasy | Communauté Fongony |
| 99 | Zafizara | Malagasy | Communauté Fongony |
| 100 | Ibrahim | Malagasy | Communauté Ambalahonko |
| 101 | Sily | Malagasy | Communauté Ambalahonko |
| 102 | Solo | Malagasy | Communauté Ambalahonko |
| 103 | Zezara | Malagasy | Communauté Ambalahonko |
| 104 | Velonozy | Malagasy | Communauté Ambalahonko |
| 105 | Flobert | Malagasy | Communauté Ambalahonko |
| 106 | Jean | Malagasy | Communauté Ambalahonko |
| 107 | Sameline | Malagasy | Communauté Ambalahonko |
| 108 | Sylvain | Malagasy | Communauté Nosy Lana |
| 109 | Aladine | Malagasy | Communauté Nosy Lana |
| 110 | Jolie | Malagasy | Communauté Nosy Lana |
| 111 | Fabie | Malagasy | Communauté Nosy Lana |
| 112 | Saosaony | Malagasy | Communauté Nosy Lana |
| 113 | Dominique | Malagasy | Communauté Nosy Lana |
| 114 | Lepere | Malagasy | Communauté Nosy Lana |
| 115 | Manjé | Malagasy | Communauté Nosy Lana |
| 116 | Arabo | Malagasy | Union des Fédérations des pêcheurs |
| 117 | Jean fernand | Malagasy | Fédérations des pêcheurs |
| 118 | Houssen | Malagasy | Communauté Ankazomborona |
| 119 | Christian | Malagasy | Fédérations des pêcheurs |
| 120 | Manafo | Malagasy | Fédérations des pêcheurs |
| 121 | Delor | Malagasy | Communauté Ankazomborona |
| 122 | Antida | Malagasy | Fédérations des pêcheurs |
| 123 | Mena | Malagasy | Fédérations des pêcheurs |
| 124 | Ahmed | Malagasy | Communauté Ankazomborona |
| 125 | Serany | Malagasy | Communauté Ankazomborona |
| 126 | Nourdine | Malagasy | Communauté Ankazomborona |
| 127 | Paul be | Malagasy | Communauté Ankazomborona |
| 128 | Jean louis | Malagasy | Fédérations des pêcheurs |
| 129 | Chriso | Malagasy | Fédérations des pêcheurs |
| 130 | Adany | Malagasy | Communauté Ankigny |
| 131 | Camardine | Malagasy | Communauté Ankigny |
| 132 | Jean chris | Malagasy | Communauté Ankigny |
| 133 | Jaovita | Malagasy | Fédérations des pêcheurs |
| 134 | Baban’i houssen | Malagasy | Communuaté Ankigny |
| 135 | Sebastien | Malagasy | Fédérations des pêcheurs |
| 136 | Mami | Malagasy | Fédérations des pêcheurs |
| 137 | Bonary | Malagasy | Communauté Antsahampano |
| 138 | Bera | Malagasy | Communauté Antsahampano |
| 139 | Atoumani | Malagasy | Communauté Antsahampano |
| 140 | Bekamisy arnaud | Malagasy | Communauté Antsahampano |
| 141 | Herman | Malagasy | Communauté Antsahampano |
| 142 | Dimbimanarina donald | Malagasy | Communauté Antsahampano |
| 143 | Deric | Malagasy | Communauté Antsahampano |
| 144 | Bera | Malagasy | Communauté Antsahampano |
| 145 | Jaosoa jean fridolin | Malagasy | Communauté Antsahampano |
| 146 | Jaotombo | Malagasy | Communauté Antsahampano |
| 147 | Felix | Malagasy | Communauté Antsahampano |
| 148 | Betombo | Malagasy | Communauté Antsahampano |
| 149 | Arona | Malagasy | Communauté Antsahampano |
| 150 | Nico | Malagasy | Communauté Antsahampano |
| 151 | Olivier | Malagasy | Communauté Antsahampano |
| 152 | Jacqueline | Malagasy | Communauté Ankigny |
| 153 | Jacquot | Malagasy | Communauté Ankigny |
| 154 | Tino | Malagasy | Communauté Ankigny |
| 155 | Tomboravo | Malagasy | Communauté Ankigny |
| 156 | Adanoro | Malagasy | Communauté Ankigny |
| 157 | Kamar | Malagasy | Communauté Ankigny |
| 158 | Sambo | Malagasy | Communauté Ankigny |
| 159 | Roméo | Malagasy | Communauté Ankigny |
| 160 | Anicet | Malagasy | Communauté Ankigny |
| 161 | Tombozafy | Malagasy | Communauté Ankigny |
| 162 | Georges jaosara | Malagasy | Communauté Ankigny |
| 163 | Pierrot | Malagasy | Communauté Nosy faly |
| 164 | Tonga | Malagasy | Communauté Nosy faly |
| 165 | Avizara | Malagasy | Communauté Nosy faly |
| 166 | Zafy | Malagasy | Communauté Nosy faly |
| 167 | Jean Dano | Malagasy | Communauté Nosy faly |
| 168 | Nico | Malagasy | Communauté Nosy faly |
| 169 | Francis | Malagasy | Communauté Nosy faly |
| 170 | Marcellia | Malagasy | Communauté Nosy faly |
| 171 | Edmon | Malagasy | Communauté Nosy faly |
| 172 | Jean jacques | Malagasy | Communauté Nosy faly |
| 173 | Jaovita | Malagasy | Communauté Nosy faly |
| 174 | Tsila | Malagasy | Communauté Nosy faly |
| 175 | Faralahy | Malagasy | Communauté Nosy faly |
| 176 | Joariziky | Malagasy | Communauté Nosy faly |
| 177 | Dino | Malagasy | Communauté Nosy faly |
| 178 | Ahmed salimo | Malagasy | Communauté Antsohimbondrona |
| 179 | Tombo | Malagasy | Communauté Antsohimbondrona |
| 180 | Kassimo | Malagasy | Communauté Antsohimbondrona |
| 181 | Franco | Malagasy | Communauté Antsohimbondrona |
| 182 | Kajy | Malagasy | Communauté Antsohimbondrona |
| 183 | Sabo | Malagasy | Communauté Antsohimbondrona |
| 184 | Roméo | Malagasy | Communauté Antsohimbondrona |
| 185 | Fatouma | Malagasy | Communauté Antsohimbondrona |
| 186 | Tino | Malagasy | Communauté Antsohimbondrona |
| 187 | Meva | Malagasy | Communauté Antsohimbondrona |
| 188 | Mananjara | Malagasy | Communauté Antsohimbondrona |
| 189 | Befanogny | Malagasy | Communauté Antsohimbondrona |
| 190 | Beanjara | Malagasy | Communauté Antsohimbondrona |
| 191 | Benefice | Malagasy | Communauté Antsohimbondrona |
| 192 | Ludo | Malagasy | Communauté Antsohimbondrona |
| 193 | Veve | Malagasy | Communauté Ampasindava |
| 194 | Jaotombo Sosten | Malagasy | Communauté Ampasindava |
| 195 | Totozafy eric | Malagasy | Communauté Ampasindava |
| 196 | Maharavo | Malagasy | Communauté Ampasindava |
| 197 | Berto | Malagasy | Communauté Ampasindava |
| 198 | Tsitondro | Malagasy | Communauté Ampasindava |
| 199 | Issouf | Malagasy | Communauté Ampasindava |
| 200 | Jean robert | Malagasy | Communauté Ampasindava |
| 201 | Toto | Malagasy | Communauté Ampasindava |
| 202 | mamodo | Malagasy | Communauté Ampasindava |
| 203 | Fenozandry clovis | Malagasy | Communauté Ampasindava |
| 204 | Tsimagneky | Malagasy | Communauté Ampasindava |
| 205 | Mevalaza frederic | Malagasy | Communauté Ampasindava |

  - Documents, other printed materials, videos, and soft products (such as CDs or websites)

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Meeting report | Dugong and seagrass education and awareness day | MIHARI Network | NA | NA | 13 Septembre 2016 |
| 2. | Online article | Communities leading seagrass and dugong conservation https://mihari-network.org/news/communities-leading-seagrass-dugong-conservation/ | MIHARI Network | NA | NA | January 2017 |
| 3 - 4 | Report | Priority site identification - mission reports where focus groups took place | MIHARI Network | NA | NA | January 2017 |
| 5 | Map | Priority site maps | MIHARI Network | NA | NA | January 2017 |
| 6 | Excel | Summary of priority sites | MIHARI Network | NA | NA | January 2017 |

| Name of Project Manager: Vatosoa Rakotondrazafy | Name of Project Manager Supervisor: NA |
| --- | --- |
| Signature: | Date: 10/1/17 | Signature: | Date: |

# Footnotes

Briefly describe progress made during the previous six months highlighting major outcomes/benchmarks achieved during the period.

Information provided in “Quarterly Expenditure Report” should be in line with output/activity progress reported in this table.

Outputs and activities as described in the project proposal or in any updated project revision. Expand table as necessary.

Expand table as necessary

Meeting types: e.g. expert group meeting, project inception workshop, training workshop/seminar, partners consultation workshop, project Steering Committee meeting etc.

Expand table as necessary

Documents and printed material types: e.g. technical publication, meeting report, technical/substantive report, brochures, media releases, etc.