D

The GEF Dugong and Seagrass Conservation Project

Project Progress Report

| Reporting Period | From: | 01 July 2016 | To: | 30December2016 |
| --- | --- | --- | --- | --- |

- PROJECT GENERAL INFORMATION

| National Project Code &Title: | MG 4 Integrated approaches to enhance the conservation dugongs and seagrass ecosystems in Sahamalaza areas |
| --- | --- |

| Project Partner(s): | COSAP Sahamalaza |
| --- | --- |

| Location (country, region/ district and commune/ city/ village/ region etc.) | Country:MADAGASCAR Region: SOFIA District: Analalava Commune: Ambolobozo |
| --- | --- |
| Of which areas under protection (please indicate the name and size of protected areas or locally managed marine areas, if applicable) | Sahamalaza marine and costal UNESCO Biosphere Reserve 153,200 Haof which 26,035 ha is Marine and Costal National Park |

| Project start date | 1/01/2015 | Project intended completion date | 31/08/2018 |
| --- | --- | --- | --- |

- PROJECT PROGRESS

  - Narrative of project progress during the past semester by Project Activity

This report covers the progress made on the activities planned during the period of July to December 2016. Output 1.1: governance structure for community involvement in conservation and monitoring of dugong and seagrass established or strengthened in target areas Activity 1.1.4: Local (e.g community/government/co-management/Fishing association) structures established and functioning The objective of MG4 project is to establish 10 governance structures during 2016; such structures allow the involvement of community members in the conservation and monitoring of dugongs and seagrass.In September, we organized two more community workshopsrespectively at Mahadera and Ambalabao fishing villages. These workshops had the same specific objectives as for the previous meetings: 1. To establish the community-based structure; 2. To prepare the local convention related to fishing regulation and protection of emblematic species 3. To collect baseline information on dugongs. The governance structures of Mahadera and Ambalabao were respectively named “Fitaramazava” and “VOI Ambalabao”.Elections of the members of the steering committees for both structures were done. The related report on the establishment of these governance structures is available in the Madagascar MG4 virtual repository and in the folder “Reports” under Reports & Deliverables/Year 2016/HYR Jul-Dec 2016/Supporting doc & Photos. Map summarizing the sites where governance structures were established is also available in the folder “Maps” under Reports & Deliverables/Year 2016/HYR Jul-Dec 2016/Supporting doc & Photos (MG4 folder). Output 1.2: capacity developed for the community-based stewardship (conservation and monitoring of dugong and seagrass Activity 1.2.1: Awareness and education campaigns Prior to the community workshop for establishing each governance structure in the fishing village of Mahadera and Ambalabao, the members of COSAP Sahamalaza Miaro dugongs raised the understanding of the fishing communities on dugongs and seagrass. It is worth noting that few participants had the knowledge of dugongs. The missionaries gave detailed information related to dugong including its biology and status. The lack of public awareness on the biodiversity has been proven as a key barrier in ensuring its protection. The lemur festival is one the annual outreach events organized in Sahamalaza Area for increasing awareness of the environment and to ensure its conservation. MG4 participated in this festival that was celebrated in September 2016 in Antafiabe village. We took advantage of this event to raise the publicunderstanding on dugongs and seagrass. Factsheets sent by the members of the PCT were exhibited during the poster session. Apart the administrative authorities, most of the visitors were pupils. They asked many questions related to dugong such as the size, lifespan, reproduction, number of calf. A report related to our participation in this event is available inthe folder “Reports” under Reports & Deliverables/Year 2016/HYR Jul-Dec 2016/Supporting doc & Photos (MG4 folder). For planning the celebration of the first edition of the dugong festival, Two community meetingswereheld at Berafia in September to discuss about the logistical aspects for it. Reporting related to the preparation of the festival was available in the folder “Reports” underReports & Deliverables/Year 2016/HYR Jul-Dec 2016/Supporting doc & Photos (MG4 folder). The principles of organizing a “Dugong Festival” were to reach large audiences and engage them in thinking about conservation and covered theme “Hasondrotrontsika miaraka ny fiarovana trozogno ndraiky ahi-dramasina agnatin’ny hôban’ny Sahamalaza“- Together, we enhance the conservation of dugong and seagrass in the coastal zone of Sahamalaza.” The first edition of dugong festival was a success, with more than 1,000 people attending, including high officials from SOFIA and DIANA Regions,other officers from the Regional Direction of Environment and Forest of SOFIA, Department of Fisheries of DIANA, NGOs, local private partners, migrant fishermen and local community. Special programsthat included poster session, film screenings and contests based on marine environment and dugong subjects were planned for raising public awareness. Additionally, the members of MG4 took advantage of the festival to conduct awareness program at the public elementary school of Berafia. Life history and illustration of dugong were presented to the pupils. A report related to the celebration of the first edition of the dugong festival is available in the folder “Reports” under Reports & Deliverables/Year 2016/HYR Jul-Dec 2016/Supporting doc & Photos (MG4 folder). 1.2.2: Training in dugong and seagrass based management At this stage of the project, we still collected baseline information and the management of dugong and seagrass is not yet planned. 1.2.3: Training in dugong and seagrass monitoring No training on dugong and seagrass was planned during the second half year period. However, we judged the importance of reviewing the monitoring protocol according to the results; this isfor the getting accurate information on dugongs inhabiting Sahamalaza area. We will plan training on dugong monitoring for the next period of reporting. Output 1.3 : Integrated coastal management 1.3.1: Baseline information gathering and consultations We continued to conduct interview surveys in Nosy Valiha and in several sites located along the eastern and western sides of Sahamalaza Peninsula for consolidating the information on dugongs and seagrass. A student from the University of Mahajanga was involved in the collection of supplement data using the CMS standardized dugong catch/by-catch questionnaires. We created a database related to the historical sightings of dugongs in Sahamalaza area from the 1980s to the 2010s. Additionally, maps illustrating respectively the survey sites visited during the data collection and the repartition of live dugongs observed during 2016 were developed. The updated database,historical dugong sighting database and maps arerespectively available in the folders “Databases” and “Maps” under Reports & Deliverables/Year 2016/HYR Jul-Dec 2016/Supporting doc & Photos (MG4 folder). 1.3.3: Pilot site management plan preparation “ In September, two new conservation community-based structures adopted their own local convention or “Dina” drafted in Malagasy; these conventions were adopted to regulate the fishing activities and to protect emblematic species including marine turtles. All signed local conventions adopted by the members of nine governance structures were compiled in one document that is available in the folder “Local conventions” under Reports & Deliverables/Year 2016/HYR Jul-Dec 2016/Supporting doc & Photos (MG4 folder). N.B: some local conventions are still waiting for the signatories of the Mayors. Output 2.1: Management and incentive mechanisms and tools for sustainable fisheries pilots and capacity building (local community and government) 2.1.3: Alternative income generation models developed and tested with communities (from coastal communities toolbox and others) In the past, a community-based management structure was established in Mahadera and it benefited funding for establishing alternative incentive programs for alleviating the fishing pressures. The impacts of the program have not yet evaluated since the end of the project. However, the participants in Mahadera identified the top three alternative livelihoods that are rice culture, vegetable culture and apiculture for alleviating the fishing pressures.As for Ambalabao, they proposed the fishing materials, well construction and poultry. Output 2.2: Awareness raising and social marketing programmes contributing to more sustainable practice (subsistence and small scale artisanal fisheries) in target areas 2.2.1: Awareness raised; social marketing pilot initiatives providing alternative finance From the last reporting period, we haven’tproduced thematic radio campaign for the public education as the owner of local radio station “Radio Andrea d’Antsohihy » has been in the process to fix it. Output 3.1: Critical knowledge gap (dugong and seagrass ecosystems) identified and surveys initiated/completed 3.1.1: Research/survey methodologies developed and tested The community members of Ambatolava, East of Berafia island, Ankasetra, West of Nosy Valiha and Ambatobe in Sahamalaza Bay reported to the managers of MG4 the results of their monitoring activities. A total of four events of mother/Calf Pair sightings were reported between June and October 2016 in the waters of Berafia. However, no sightings were reported by the other community members involved in the monitoring. The monitoring database is available in the folder “Databases” under Reports & Deliverables/Year 2016/HYR Jul-Dec 2016/Supporting doc & Photos (MG4 folder). The 20 existing community-based structures in COSAP participated in the protected area patrolling. They should monthly undertake 320 Person/Day of surveillance. During the 960 Person/Day have been realized. Activity 3.1.2: Training in R&M methods, collaborative/ participatory surveys The members of the governance structure from Berafia who have been in charge of managing the community-based marine protected area had a meeting with the first responsible of MIHARI Network (MG2).The training on participatory survey will depend on the planning of MG2.Additionally, the dugong festival was a nice opportunity to exchange information and experience among the members of the national partners from MG1, MG2, MG3, MG6 and MG4. Activity 3.3.2: Preparation and implementation of a Project Communication strategy and materials and national communications strategies Through the first edition of the dugong festival, the members of COSAP Miaro Dugong Sahamalaza adopted asone of communication strategiesthe courtesy meetings with the local administrative authorities and diverse technical services(the representatives of the local administrative authorities - the General Secretary of DIANA Region, representatives of the Senator and the first responsible of the diverse technical services at the following regional directions: Fisheries and marine resources, Environment and Forest, Local Education, Tourism, Communication). We undertook three expeditions of which two in major towns, situated at the northern side of Sahamalaza and belong to the coastal Region of DIANA(Ambanja and Antsiranana)and at Antsohihy in SOFIA Region. These meetings were the first opportunity for introducing the regional conservation effort on dugong and seagrass through the GEF project to these local administrative authorities and to engage them in our conservation effort. For the materials, banners with informative message on dugongs and seagrass were displayed at strategic locations: Ambanja, Maromandia and Berafia. We produced the traditional piece of textile and T-shirt to convey message on the protection of dugong. Media including radio and television stations was used to support communication. We worked closely with local radio stations for broadcasting news at the site level. Additionally the national Radio and Television stations were used to cover and broadcastnewsto large audience around Madagascar. We used as well the GEF Dugong and seagrass Project website and the PCT facebook for posting news from MG4.

  - Project implementation progress

| Outputs & Activities | Expected completion date | Implementation status as of end of reporting period expressed in % | Describe any problems in delivery and any changes/mitigation action required. |
| --- | --- | --- | --- |
| Output 1.1: Governance structures for community involvement in conservation and monitoring of dugong and seagrass ecosystems |  |  |  |
| Activity 1.1.4:Local (e.g community/government/co-management/Fishing association) structures established and functioning . | 31 Mars 2017 | 71% |  |
| Output 1.2 Capacity developed for community-based stewardship (conservation and monitoring of dugongs &seagrass) |  |  |  |
| Activity 1.2.1: Awareness/Education campaigns | 01 January 2016 to 31 May 2018 | 33% |  |
| Activity 1.2.2 Training in dugong and seagrass based management | 01 February – 31 March 2016/June –August 2017 | 0% | We still collected baseline information and the management of dugong and seagrass is not yet planned |
| Activity 1.2.3: Training in dugong and seagrass monitoring | 1 Mars – 30 April 2016/01 July-31 August 2017) | 21.24% | No training on dugong and seagrass was planned during the period June-December |
| Output 1.3 Integrated community management plans (conservation and monitoring of dugong and seagrass ecosystems) developed and piloted |  |  |  |
| Activity 1.3.1: Baseline information gathering and consultations | 30 December 2015 – 31 August 2016 | 79% |  |
| Activity 1.3.3Pilot site management plan preparation | 1 May-30 June 2016/June 2018 | 0% | The expected completion date of June 2016 referred to the update of the management plan of the park that was fulfilled. But referring to the results of the monitoring, the dugongs as well the seagrass are located at places outside the marine park delimitation but within the Biosphere Reserve. We plan to establish a local conservation plan of seagrass and dugongs that the expected completion date will be June 2018. |
| Output 2.1: Management and incentive mechanisms and tools for sustainable fisheries –pilots and capacity building (local community and government) |  |  |  |
| Activity 2.1.3: Alternative income generation models developed and tested with communities (from coastal communities toolbox and others) | 01 February - 30 April 2016/01 March-30 June 2017/01 January – 30 April 2018 | 40% |  |
| Output 2.2 Awareness raising and social marketing programmes contributing to more sustainable practices (subsistence and small-scale artisanal fishers) in target areas |  |  |  |
| 2.2.1: Awareness raised; social marketing pilot initiatives providing alternative finance | 01 February-31 May 2016/June 2017/Mars 2018 | 17% | The local radio station “Radio Andrea d’Antsohihy » has been in the process to fix and no thematic radio program was produced. |
| Output 3.1: Critical knowledge gaps (dugongs and seagrass ecosystems) identified and surveys initiated/ completed |  |  |  |
| Activity 3.1.1:Research/survey methodologies developed and tested | 01 April 2016- 31 May 2018 | 22% |  |
| Activity 3.1.2: Training in R&M methods, collaborative/ participatory surveys | Undetermined | 1% | In September, meeting with the MIHARI network (MG2) was done with the managers of the community-based marine protected area at Berafia.We changed the expected completion date which will be depending on the MG2 activity planning. |
| Activity 3.3.2: Preparation and implementation of a Project Communication strategy and materials and national communications strategies | 01 May 2016 – 30 June 2018 | 17% |  |

  - Risk and risk management

Please describe internal and external risks (examples included in brackets) that could affect successfulimplementation of project activities and the proposed risk mitigation measures.

| Risk group | Description | Risk level (Low/ Medium/ High) | Mitigation measures |
| --- | --- | --- | --- |
| Project Management (team capacity, internal communication, co-financing, budget, financial management, reporting, etc.) | -Co-financing: the MNP Sahamalaza faced logistical issues because of the momentary lost of their motorized boat. Team capacity We rely upon the staff of MNP for undertaking technical activities (GIS work, monitoring). This situation may hamper our activities when they were unavailable. | Medium | - For the co-financing: the project had to rent boat and pay for gas when undertaking surveys or visits at the sites. These were unexpected expenseswhich were high costs. - We will plan to collaborate with other national partner when needed. e |
| Socio-cultural issues (external communications, capacity of and work with stakeholders, cultural aspects) | - Educational level of the stakeholders is very low rendering difficult to communicate with them. This was already reported in the last report but it still remain a risk | Medium | - Using visual materials outreach |
| Political risks (Political stability in country, political impacts on the project) | - Political instability is still an issue in Madagascar and has negative impacts on behavior (lawlessness etc..) and economics (high level of poverty) of the local population . This was already reported in the last report but it still remain a risk | Medium | - Increasing efforts deployed on raising awareness involving local including traditional and regional authorities. - Identifying alternative on livelihoods to improve their incomes |
| Environmental risks (severe weather events/ disasters, natural causes negatively affecting project areas, habitats and species) |  |  |  |
| Other (please specify) |  |  |  |

- MONITORING AND EVALUATION

  - Please describe activities for monitoring and evaluation carried out during the reporting period.

Examples include: baseline data collection, stakeholder surveys, field surveys, steering committee meetings to assess project progress, peer review of documentation to ensure quality, mid-term review, etc.

Do not include routine project reporting.

PCT feedback Taking into account the feedback from PCT on the first half year report of 2016, a field expedition was planned inMay 2016by a team composed by representatives of the technical staff of the Park managers (MNP Sahamalaza), few members of COSAP and representatives of communities in the fishing villages to collect ground truth data on dugong repartition reported by the community. Mapping of the dugong repartitionthat was done by the GIS specialist of the MNP Sahamalaza still need to be refined (refer to “Maps” under Reports & Deliverables/Year 2016/HYR Jul-Dec 2016/Supporting doc & Photos). Regarding the seagrass, the available map of seagrass was developed by the GIS specialist of the MNP Sahamalaza. The seagrasses off Nosy Valiha are located within the marine park boundaries; the remaining seagrass habitats are located outside the marine park boundaries but belong to the Biosphere Reserve of Sahamalaza. The survey undertaken during the last half year period was the preliminary assessment of seagrass in Sahamalaza area. Therefore, the results that we got during the monitoring can be used as baseline data on seagrass in the marine park. It is not possible to estimate the trend of status of the seagrass in Sahamalaza area. Because of the non-availability of the MNP staff, we would not able to give the estimate sizes of dugong hotspot and seagrass area studied and assessed and their status. We will upload the data and inform the responsible if the information is available. MNP staff will return to work during the week of 9 January 2017. The protocol of the seagrass monitoring is available at the folder “Monitoring” under Reports & Deliverables/Year 2016/HYR Jan-June 2016/Supporting doc & Photos (MG4 folder). The results of the interview surveys using the CMS by-catch questionnaire conducted in 2010 and 2016 are available at at the folder “Database” under Reports & Deliverables/Year 2016/HYR Jan-June 2016/Supporting doc & Photos (MG4 folder). Monitoring surveys The members of the Local Committee involved in the dugong monitoring conducted monthly surveys between June and December in their respective sites (Berafia, Nosy Valiha and Ambatobe. They have to fill a template developed for the monitoring. They received training on the use of the Global Positioning System and recorded the coordinates of the sightings in the reports sent to the members of COSAP Sahamalaza Miaro Dugong. Interview survey A student from the University of Mahajanga undertookhe interview surveys using the same CMS standardized dugong catch/by-catch questionnaires (uploaded in July 2010) atsevenfishing villageslocated along the western side of Sahamalaza Peninsula. The surveys were conducted between 06and 22July 2016. The fishers interviewed were chosen haphazardly based on their availability during our visits to the respective villages. All of the data were entered to update the database. Mid-term review The first schedule of the mid-term review of the project was planned in November 2016 for Madagascar. Therefore, the members of MG4 project were prepared for the evaluation by getting supported documents needed as requested by the members of the PCT. We prepared executive summaries in English for all our key documents drafted in French and in our native language. Additionally, we realized the following preparation according to the notice sent by the members of the PCT: Printing of all supported documents to be available at hand; Preparing a project document including geographical coordinates of the pilot sites; Uploading all supportive documents in the virtual repository of the national project. Preparation of the 2nd EPSC meeting We prepared a summary of MG4 project progress for compiling the information from all project partners needed for the country presentation to be communicated during the EPSC meeting in Malaysia in November 2016.

- OTHER INFORMATION

  - Meetings

| Meeting type | Title | Venue | Dates | Convened by | Organised by | No. of participants | Report issued Y/N | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Community workshop at Mahadera | Establishing new governance structure and “dina”. | Mahadera village | 10/09/2016 | Local Administrative Authorities (Mayors, Chief of the Village) | COSAP | 57 | Y | Malagasy | 18/11/2016 |
| Community workshop at Ambalabao | Establishing new governance structure and “dina”. | Ambalabaovillage | 10/09/2016 | Administrative Authorities (Mayors, Chief of the Village) | COSAP | 28 | Y | Malagasy | 18/11/2016 |
| First meeting for local communities at Berafia | Preparation of the first outreach event “Dugong Festival” | Berafiavillage | 17/09/2016 | Administrative Authorities (Mayors, Chief of the Village) | COSAP | 128 | Y | Malagasy | 2/11/2016 |
| Second meeting for local communities at Berafia | Preparation of the first outreach event “Dugong Festival” | Berafia village | 18/10/2016 | Administrative Authorities (Mayors, Chief of the Village) | COSAP | 126 | Y | Malagasy | 2/1&/2016 |
| Local participation of community members in the festival | First edition of the dugong festival in Berafia | Berafia Village | 28 – 29/10/2016 | Administrative Authorities (Chiefs of Region and District, Mayors, Chief of the Villages) | COSAP | 167 | Y | Malagasy | 18/11/2016 |

  - List(s) of meeting participants

Meeting for establishing the governance structure of Mahadera on 10September 2016

| No. | Name of participant | Nationality |
| --- | --- | --- |
| 01 | Razafimamonjy Nestor | Madagascar |
| 02 | Honorine | Madagascar |
| 03 | Tongaravo | Madagascar |
| 04 | Tobozara | Madagascar |
| 05 | Rémi André | Madagascar |
| 06 | Mohamed | Madagascar |
| 07 | Joslin | Madagascar |
| 08 | Fetin’I Vahoaka | Madagascar |
| 09 | Androse | Madagascar |
| 10 | Fidele | Madagascar |
| 11 | Jaomamory Jean Claude | Madagascar |
| 12 | Tombozara | Madagascar |
| 13 | Tongazara | Madagascar |
| 14 | Jaotody | Madagascar |
| 15 | Theophile | Madagascar |
| 16 | Jaomanompo | Madagascar |
| 17 | Tongalaza | Madagascar |
| 18 | Marie | Madagascar |
| 19 | Raharimalala Marie Aline | Madagascar |
| 20 | Celine | Madagascar |
| 21 | Marisika | Madagascar |
| 22 | Nosy | Madagascar |
| 23 | Tianjara | Madagascar |
| 24 | Samalazara Lucie Malaka | Madagascar |
| 25 | Tongaravo | Madagascar |
| 26 | Avizara | Madagascar |
| 27 | Etienne | Madagascar |
| 28 | Jaomarisika | Madagascar |
| 29 | Abdou | Madagascar |
| 30 | Assimo | Madagascar |
| 31 | Franco | Madagascar |
| 32 | Jaoviloma | Madagascar |
| 33 | Nirina | Madagascar |
| 34 | Soaline | Madagascar |
| 35 | Jaotiana | Madagascar |
| 36 | Flavien | Madagascar |
| 37 | Narce Florent | Madagascar |
| 38 | Florence | Madagascar |
| 39 | Zafijery | Madagascar |
| 40 | Josiane | Madagascar |
| 41 | Solo Jean | Madagascar |
| 42 | Jaozandry | Madagascar |
| 43 | Justin | Madagascar |
| 44 | Jeannot David | Madagascar |
| 45 | Jean Noel | Madagascar |
| 46 | Tombozara Jules | Madagascar |
| 47 | Patrice | Madagascar |
| 48 | Christian | Madagascar |
| 49 | Rasta | Madagascar |
| 50 | Albert | Madagascar |
| 51 | Venance | Madagascar |
| 53 | Chamsdine | Madagascar |
| 54 | Gaston Norbert | Madagascar |
| 55 | Geda | Madagascar |
| 56 | Randrianarivelo Urbain Joeal | Madagascar |
| 57 | Isaia Raymond | Madagascar |

Meeting for establishing the governance structure of Ambalabao on 10September 2016

| No. | Name of participant | Nationality |
| --- | --- | --- |
| 01 | Dily Jaovola | Madagascar |
| 02 | Fidizara Nestor | Madagascar |
| 03 | Razanatsara Hortence | Madagascar |
| 04 | Johnson William | Madagascar |
| 05 | Akram | Madagascar |
| 06 | Betombo Robin | Madagascar |
| 07 | Robert | Madagascar |
| 08 | Flave | Madagascar |
| 09 | François | Madagascar |
| 10 | Live | Madagascar |
| 11 | Rabezara | Madagascar |
| 12 | Rapanoela Didi Léon | Madagascar |
| 13 | Robera | Madagascar |
| 14 | Narcis | Madagascar |
| 15 | Rasoamanosoka | Madagascar |
| 16 | Soa | Madagascar |
| 17 | Rasoanivo | Madagascar |
| 18 | Vonimasy | Madagascar |
| 19 | Zania | Madagascar |
| 20 | Mariane | Madagascar |
| 21 | Jenette | Madagascar |
| 22 | Manombo | Madagascar |
| 23 | Soamanidry | Madagascar |
| 24 | Diamary | Madagascar |
| 25 | Blandine | Madagascar |
| 26 | Olivier | Madagascar |
| 27 | Jao Marcel | Madagascar |
| 28 | Randria Norbert | Madagascar |

First meeting for preparing the first edition of the dugong festivalat Berafia on 17September 2016

| No. | Name of participant | Nationality |
| --- | --- | --- |
| 01 | Abdala | Madagascar |
| 02 | Rasilien | Madagascar |
| 03 | Andrianera | Madagascar |
| 04 | Labeny | Madagascar |
| 05 | Todiarivo | Madagascar |
| 06 | Hamba | Madagascar |
| 07 | Julienne | Madagascar |
| 08 | Marcelline | Madagascar |
| 09 | Soavina | Madagascar |
| 10 | Vongizara | Madagascar |
| 11 | Anteonjara | Madagascar |
| 12 | Celestine | Madagascar |
| 13 | Latifa | Madagascar |
| 14 | Adija | Madagascar |
| 15 | Landy | Madagascar |
| 16 | Salimonajimo | Madagascar |
| 17 | Pascal | Madagascar |
| 18 | Jacquelin | Madagascar |
| 19 | Tsiavic | Madagascar |
| 20 | Damien | Madagascar |
| 21 | Manohizara Clement | Madagascar |
| 22 | Djailane Bruno Abdou | Madagascar |
| 23 | Tolindraza Rom Georgino | Madagascar |
| 24 | Mahamoudou | Madagascar |
| 25 | Finjara | Madagascar |
| 26 | Marinosy | Madagascar |
| 27 | Marimina | Madagascar |
| 28 | Jacqueline | Madagascar |
| 29 | Tsontso | Madagascar |
| 30 | Safina | Madagascar |
| 31 | Mbotisoa | Madagascar |
| 32 | Claudine | Madagascar |
| 33 | Soamadamo | Madagascar |
| 34 | Angarena | Madagascar |
| 35 | Laurette | Madagascar |
| 36 | Moana Florine | Madagascar |
| 37 | Meline | Madagascar |
| 38 | Vitasoa | Madagascar |
| 39 | Moana Florine | Madagascar |
| 40 | Soatody | Madagascar |
| 41 | Jaosily | Madagascar |
| 42 | Anandra | Madagascar |
| 43 | Andre | Madagascar |
| 44 | Tsafitsaka Zara | Madagascar |
| 45 | Tombozara | Madagascar |
| 46 | Amiry | Madagascar |
| 47 | Tiazara | Madagascar |
| 48 | Tomboraza | Madagascar |
| 49 | James | Madagascar |
| 50 | Zily | Madagascar |
| 51 | Hada | Madagascar |
| 52 | Manompo | Madagascar |
| 53 | Jaosily | Madagascar |
| 54 | Makavita Bezily | Madagascar |
| 55 | Banono | Madagascar |
| 56 | Saotra | Madagascar |
| 57 | Zafitombo | Madagascar |
| 58 | Tsiantandra | Madagascar |
| 59 | Seizatiana | Madagascar |
| 60 | Zislin | Madagascar |
| 61 | Mananga | Madagascar |
| 62 | Amana | Madagascar |
| 63 | Bezara | Madagascar |
| 64 | Salimo | Madagascar |
| 65 | Randrianarison Jules | Madagascar |
| 66 | Michel | Madagascar |
| 67 | Luc | Madagascar |
| 68 | Veve | Madagascar |
| 69 | Rosy | Madagascar |
| 70 | Velo | Madagascar |
| 71 | Lio | Madagascar |
| 72 | Attomany Aly | Madagascar |
| 73 | Solovita | Madagascar |
| 74 | Jiabiry | Madagascar |
| 75 | Juldas Assan | Madagascar |
| 76 | Tianjara | Madagascar |
| 77 | Donne | Madagascar |
| 78 | Mac Simo | Madagascar |
| 79 | Marchel | Madagascar |
| 80 | Angeline | Madagascar |
| 81 | Zaitony | Madagascar |
| 82 | Robin | Madagascar |
| 83 | Beanjara Betombo | Madagascar |
| 84 | Souf | Madagascar |
| 85 | Misizara | Madagascar |
| 86 | Ampizara | Madagascar |
| 87 | Assany Houssen | Madagascar |
| 88 | Ali | Madagascar |
| 89 | Aboudou | Madagascar |
| 90 | Lusette | Madagascar |
| 91 | Sania | Madagascar |
| 92 | Jacline | Madagascar |
| 93 | Olizette | Madagascar |
| 94 | Nafisa | Madagascar |
| 95 | Roseline | Madagascar |
| 96 | Noeline | Madagascar |
| 97 | Laurance | Madagascar |
| 98 | Rabezafy Camille | Madagascar |
| 99 | Fidizara Nestor | Madagascar |
| 100 | Geda | Madagascar |
| 101 | Bienvenue Alexis | Madagascar |
| 102 | Tomboravo Attomany | Madagascar |
| 103 | Saidou | Madagascar |
| 104 | Tafara Ahiada Beny | Madagascar |
| 105 | Ravondaza Jean Narcisse | Madagascar |
| 106 | Radonarivelo Paulin | Madagascar |
| 107 | Hampy | Madagascar |
| 108 | Tiaraza | Madagascar |
| 109 | Tsiafindra | Madagascar |
| 110 | Bevoay Razaky | Madagascar |
| 111 | Faly Jean Robin | Madagascar |
| 112 | Sambizara Tsiafindra | Madagascar |
| 113 | Anzidane | Madagascar |
| 114 | Antoenjara | Madagascar |
| 115 | Faidaly Aboubakar | Madagascar |
| 116 | Ampizara | Madagascar |
| 117 | Attomany Ahidary | Madagascar |
| 118 | Solovelo Mahavita | Madagascar |
| 119 | Sidy | Madagascar |
| 120 | Ahidar | Madagascar |
| 121 | Aboudou | Madagascar |
| 122 | Jaosengy | Madagascar |
| 123 | Djinoro | Madagascar |
| 124 | Houssen | Madagascar |
| 125 | Hababe | Madagascar |
| 126 | Arson | Madagascar |
| 127 | Jaobe | Madagascar |
| 128 | Will | Madagascar |

Second meeting for preparing the first edition of the dugong festival at Berafia on 18October 2016

| No. | Name of participant | Nationality |
| --- | --- | --- |
| 01 | Rabezafy Camille | Madagascar |
| 02 | Fidizara Nestor | Madagascar |
| 03 | Geda | Madagascar |
| 04 | Manohizara Clement | Madagascar |
| 05 | Raharimalala Zita Fabiola | Madagascar |
| 06 | Tombolaza Jean René | Madagascar |
| 07 | Faidaly | Madagascar |
| 08 | Antoejanra | Madagascar |
| 09 | Attomany Ahidara | Madagascar |
| 10 | Paul Zara | Madagascar |
| 11 | Zafitombo | Madagascar |
| 12 | Tiaraza | Madagascar |
| 13 | Hadabe | Madagascar |
| 14 | Tombozafy | Madagascar |
| 15 | Bienvenue Alexis | Madagascar |
| 16 | Donné | Madagascar |
| 17 | Tianjara | Madagascar |
| 18 | Arsene Frederic | Madagascar |
| 19 | Richard | Madagascar |
| 20 | Moedine Solo | Madagascar |
| 21 | Abdoul Nordien | Madagascar |
| 22 | Pascal | Madagascar |
| 23 | Todiny | Madagascar |
| 24 | Felix | Madagascar |
| 25 | Dino | Madagascar |
| 26 | Fatima Soalehy | Madagascar |
| 27 | Vitzara | Madagascar |
| 28 | Luc | Madagascar |
| 29 | Tsaramanana Céverien | Madagascar |
| 30 | Claude | Madagascar |
| 31 | Zafy Bertin | Madagascar |
| 32 | Marcel | Madagascar |
| 33 | Angelo | Madagascar |
| 34 | Serge | Madagascar |
| 35 | Hamba Zandry | Madagascar |
| 36 | Arsene | Madagascar |
| 37 | Vitasoa | Madagascar |
| 38 | Valerine | Madagascar |
| 39 | Soazafy | Madagascar |
| 40 | Caroline | Madagascar |
| 41 | Laurette | Madagascar |
| 42 | Justine | Madagascar |
| 43 | Saufa | Madagascar |
| 44 | Abiba | Madagascar |
| 45 | Soamanarina Victorine | Madagascar |
| 46 | Zafinoro | Madagascar |
| 47 | Claudine | Madagascar |
| 48 | Siza | Madagascar |
| 49 | Lazany | Madagascar |
| 50 | Farida | Madagascar |
| 51 | Paso | Madagascar |
| 52 | Vero | Madagascar |
| 53 | Mbotizara | Madagascar |
| 54 | Peta | Madagascar |
| 55 | Rozeline | Madagascar |
| 56 | Florette | Madagascar |
| 57 | Amina | Madagascar |
| 58 | Vitasoa | Madagascar |
| 59 | Zafitombo Olivia | Madagascar |
| 60 | Finjara | Madagascar |
| 61 | Maromina | Madagascar |
| 62 | Torine | Madagascar |
| 63 | Zacline | Madagascar |
| 64 | Mbotisoa | Madagascar |
| 65 | Volahita | Madagascar |
| 66 | Marilaza | Madagascar |
| 67 | Angarena | Madagascar |
| 68 | Zanine | Madagascar |
| 69 | Rozaline | Madagascar |
| 70 | Agatte | Madagascar |
| 71 | Ivonne | Madagascar |
| 72 | Sesil | Madagascar |
| 73 | Masilaza | Madagascar |
| 74 | Zafinoro | Madagascar |
| 75 | Salima | Madagascar |
| 76 | Zarameva | Madagascar |
| 77 | Josephine | Madagascar |
| 78 | Tsotso | Madagascar |
| 79 | Marinjafy | Madagascar |
| 80 | Poety | Madagascar |
| 81 | Asiata | Madagascar |
| 82 | Ziline | Madagascar |
| 83 | Lazamary | Madagascar |
| 84 | Françoise | Madagascar |
| 85 | Noeline | Madagascar |
| 86 | Marisana Duela | Madagascar |
| 87 | Saida | Madagascar |
| 88 | Razay | Madagascar |
| 89 | Gline | Madagascar |
| 90 | Soaliza | Madagascar |
| 91 | Raissa | Madagascar |
| 92 | Norozara | Madagascar |
| 93 | Phipine | Madagascar |
| 94 | Ahidar | Madagascar |
| 95 | Tombo Assany | Madagascar |
| 96 | Tomboravo Atomany | Madagascar |
| 97 | Mahamoudou | Madagascar |
| 98 | Seizatiana | Madagascar |
| 99 | Tongazara | Madagascar |
| 100 | Jaosengy | Madagascar |
| 101 | Tombolaza | Madagascar |
| 102 | Soa | Madagascar |
| 103 | Saidou | Madagascar |
| 104 | Antoeny | Madagascar |
| 105 | Hada I | Madagascar |
| 106 | Andrianera | Madagascar |
| 107 | Ahmed | Madagascar |
| 108 | Tsiosa | Madagascar |
| 109 | Velondraza | Madagascar |
| 110 | Jaofasy | Madagascar |
| 111 | Jaohasy | Madagascar |
| 112 | René | Madagascar |
| 113 | Anjara | Madagascar |
| 114 | Tomboravo Atomany | Madagascar |
| 115 | Andre | Madagascar |
| 116 | Zarany | Madagascar |
| 117 | Richard | Madagascar |
| 118 | Henobelle | Madagascar |
| 119 | Jaosiny | Madagascar |
| 120 | Manajara | Madagascar |
| 121 | Anandra | Madagascar |
| 122 | Jaoraza | Madagascar |
| 123 | Bezara | Madagascar |
| 124 | Michel | Madagascar |
| 125 | Juslin | Madagascar |
| 126 | Djalanne Bruno Abdou | Madagascar |

Local community participating in the first edition of the dugong festival at Berafia on 28-29October 2016

| No. | Name of participant | Nationality |
| --- | --- | --- |
| 01 | Rabezafy Camille | Madagascar |
| 02 | Fidizara Nestor | Madagascar |
| 03 | Razanatsara Horthence | Madagascar |
| 04 | Gilbert | Madagascar |
| 05 | Léonida | Madagascar |
| 06 | Nosy | Madagascar |
| 07 | Zafimaro | Madagascar |
| 08 | Ramanirina Justine | Madagascar |
| 09 | Ravaomampionona Justine | Madagascar |
| 10 | Fiamina | Madagascar |
| 11 | Toalifa | Madagascar |
| 12 | Bao Zafihavana | Madagascar |
| 13 | Bevavy | Madagascar |
| 14 | Salima | Madagascar |
| 15 | Asmine | Madagascar |
| 16 | Ciline | Madagascar |
| 17 | Sanadera Eulodie | Madagascar |
| 18 | Rasoa Marie | Madagascar |
| 19 | Roseline | Madagascar |
| 20 | Gnetsany | Madagascar |
| 21 | Soazafy | Madagascar |
| 22 | Sandia | Madagascar |
| 23 | Adijà | Madagascar |
| 24 | Viaviny | Madagascar |
| 25 | Rasoa | Madagascar |
| 26 | Marie Claire | Madagascar |
| 27 | Sirazy | Madagascar |
| 28 | Dette | Madagascar |
| 29 | Fara | Madagascar |
| 30 | Sella | Madagascar |
| 31 | Soa | Madagascar |
| 32 | Soajery | Madagascar |
| 33 | Bemary | Madagascar |
| 34 | Tsarandro | Madagascar |
| 35 | Edwidge | Madagascar |
| 36 | Soazandry | Madagascar |
| 37 | Ravaonoro Roseline | Madagascar |
| 38 | Vanja Marie | Madagascar |
| 39 | Marindraza | Madagascar |
| 40 | Botra Jacquelin | Madagascar |
| 41 | Zafisoa Florine | Madagascar |
| 42 | Mahasosoko | Madagascar |
| 43 | Jaotombo Marcelline | Madagascar |
| 44 | Zakia | Madagascar |
| 45 | Tsaranarana | Madagascar |
| 46 | Mahadimby Nicolas | Madagascar |
| 47 | Rahatsimalandy Mahazaka | Madagascar |
| 48 | Zavatra Jean Baptiste | Madagascar |
| 49 | Rabemilarison Edmond | Madagascar |
| 50 | Rasolomiarina Friedel | Madagascar |
| 51 | Velondia Anatoli Altobeli | Madagascar |
| 52 | Jaosolo | Madagascar |
| 53 | Raherindray Raymond | Madagascar |
| 54 | Paranison Wald Edikoff | Madagascar |
| 55 | Victor Antonio | Madagascar |
| 56 | Randrianambinina | Madagascar |
| 57 | Ramantena Laingo Vivien | Madagascar |
| 58 | Mahavita Besily | Madagascar |
| 59 | Zaky | Madagascar |
| 60 | Zara Elysé | Madagascar |
| 61 | Euphrasie | Madagascar |
| 62 | Sabrina | Madagascar |
| 63 | Ernest | Madagascar |
| 64 | Tizara | Madagascar |
| 65 | Claude | Madagascar |
| 66 | Zafinoro Claudine | Madagascar |
| 67 | Isaia Raymond | Madagascar |
| 68 | Samalazara Lucie Malaka | Madagascar |
| 69 | Ramarozatovo Dina | Madagascar |
| 70 | Rasojarivelo Jean Bosco | Madagascar |
| 71 | Rakotondrazafy Vatosoa | Madagascar |
| 72 | Venance Damascene | Madagascar |
| 73 | Ratsimalandy Mahazaka | Madagascar |
| 74 | Jaosolo dit Jimmy | Madagascar |
| 75 | Fananara | Madagascar |
| 76 | Ginette | Madagascar |
| 77 | Tomboravo Atomany | Madagascar |
| 78 | Mahavitan’i Tombodily | Madagascar |
| 79 | Tsiatandra | Madagascar |
| 80 | Hamba Fidele | Madagascar |
| 81 | Saidou | Madagascar |
| 82 | A Olsen Banguie | Madagascar |
| 83 | Robi Herman | Madagascar |
| 84 | Polizara | Madagascar |
| 85 | Siamy | Madagascar |
| 86 | Aziza | Madagascar |
| 87 | Faidaly | Madagascar |
| 88 | Vony | Madagascar |
| 89 | Tombozafy Roger | Madagascar |
| 90 | Assany | Madagascar |
| 91 | Edson | Madagascar |
| 92 | Richard | Madagascar |
| 93 | Jaosengy | Madagascar |
| 94 | Richard | Madagascar |
| 95 | Vohavy | Madagascar |
| 96 | Tomboravo | Madagascar |
| 97 | Jaozandry | Madagascar |
| 98 | Eric | Madagascar |
| 99 | Léoquatre Mora | Madagascar |
| 100 | Stéphanie | Madagascar |
| 101 | Archille Elia | Madagascar |
| 102 | Phyrose | Madagascar |
| 103 | Folera | Madagascar |
| 104 | Zaramisy Jean Philbert | Madagascar |
| 105 | Randriamizaka Sherina | Madagascar |
| 106 | Anorontsany | Madagascar |
| 107 | Abdallah Rachid | Madagascar |
| 108 | Ampizara Odette | Madagascar |
| 109 | Randriamizaka Alina Anastha | Madagascar |
| 110 | Zozo | Madagascar |
| 111 | Soafeno | Madagascar |
| 112 | Zafitombo | Madagascar |
| 113 | Cnien | Madagascar |
| 114 | Mandigny | Madagascar |
| 115 | Vavitombo | Madagascar |
| 116 | Jaosenga | Madagascar |
| 117 | Clément | Madagascar |
| 118 | André | Madagascar |
| 119 | Mario | Madagascar |
| 120 | Viloma Laza | Madagascar |
| 121 | Beny | Madagascar |
| 122 | Horaza | Madagascar |
| 123 | Soanavony | Madagascar |
| 124 | Solo | Madagascar |
| 125 | Daule | Madagascar |
| 126 | Toutou | Madagascar |
| 127 | Théo | Madagascar |
| 128 | Tombo | Madagascar |
| 129 | Faby | Madagascar |
| 130 | Maurice | Madagascar |
| 131 | Tianjara | Madagascar |
| 132 | Adabe | Madagascar |
| 133 | Balà | Madagascar |
| 134 | Jaomarsel | Madagascar |
| 135 | Nordine | Madagascar |
| 136 | Zaid Aly | Madagascar |
| 137 | Mananjara Christian | Madagascar |
| 138 | Besiny | Madagascar |
| 139 | Erika | Madagascar |
| 140 | Hortensia | Madagascar |
| 141 | Azraf | Madagascar |
| 142 | Lôlô | Madagascar |
| 143 | Soazy | Madagascar |
| 144 | Afosoaky | Madagascar |
| 145 | Nassour Aly | Madagascar |
| 146 | Hambazandry | Madagascar |
| 147 | Sikina | Madagascar |
| 148 | Anicette | Madagascar |
| 149 | Fatoma | Madagascar |
| 150 | Safy | Madagascar |
| 151 | Maurela | Madagascar |
| 152 | Auguste | Madagascar |
| 153 | Amouzia | Madagascar |
| 154 | Tianjafy | Madagascar |
| 155 | Afdine | Madagascar |
| 156 | Chiamsdine | Madagascar |
| 157 | Claudio | Madagascar |
| 158 | Berto | Madagascar |
| 159 | Jaotody | Madagascar |
| 160 | Hamzah | Madagascar |
| 161 | Lamela | Madagascar |
| 162 | Adeline | Madagascar |
| 163 | Filao | Madagascar |
| 164 | Safimoana | Madagascar |
| 165 | Zara | Madagascar |
| 166 | Elise | Madagascar |
| 167 | Vonisolo | Madagascar |

  - Documents, other printed materials, videos, and soft products (such as CDs or websites)

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication date |
| --- | --- | --- | --- | --- | --- | --- |

# Footnotes

Briefly describe progress made during the previous six months highlighting major outcomes/benchmarks achieved during the period.

Information provided in “Quarterly Expenditure Report” should be in line with output/activity progress reported in this table.

Outputs and activities as described in the project proposal or in any updated project revision. Expand table as necessary.

Expand table as necessary

Meeting types: e.g. expert group meeting, project inception workshop, training workshop/seminar, partners consultation workshop, project Steering Committee meeting etc.

Expand table as necessary

Documents and printed material types: e.g. technical publication, meeting report, technical/substantive report, brochures, media releases, etc.