The GEF Dugong and Seagrass Conservation Project

Project Progress Report

| Reporting Period | From: | July / 2016 | To: | December / 2016 |
| --- | --- | --- | --- | --- |

- PROJECT GENERAL INFORMATION

| National Project Code & Title: | MY1-2111: Operationalizing the Malaysian National Plan of Action for Dugong in Pulau Sibu and Pulau Tinggi, Johor, Peninsular Malaysia |
| --- | --- |

| Project Partner(s): | Department of Marine Park Malaysia & Reef Check Malaysia |
| --- | --- |

| Location (country, region/ district and commune/ city/ village/ region etc.) | Pulau Sibu and Pulau Tinggi, Johor, Malaysia. |
| --- | --- |
| Of which areas under protection (please indicate the name and size of protected areas or locally managed marine areas, if applicable) | Pulau Sibu Marine Park, 4260 ha Pulau Tinggi Marine Park, 10,180 ha |

| Project start date | 1 Aug 2015 | Project intended completion date | 30 Sep 2018 |
| --- | --- | --- | --- |

- PROJECT PROGRESS

  - Narrative of project progress during the past semester by Project Activity

Project started almost a year behind schedule (Aug 2016) due to the legal issue on the contract facing one of the implementing partner, Department of Marine Park Malaysia which is a government agency. However, the issue is resolved by appointing third party NGO partner, (Reef Check Malaysia) and the project received a jump start with having a full time staff based on the project site (Pulau Sibu). Stocktaking process was immediately kicked off and some baseline data were collected and preliminary understanding of the community’s attitude. There is an issue of redundancy between federal and state government as both agencies have similar interest, objective and activities on the same project area which is in preparing the Management Plan of the Dugong Sanctuary. At the time of this report writing, a meeting between both agencies to resolve this issue is ongoing. Meanwhile the Department of Marine Park has taken initiative to fund a research study conducted by University Malaya to compile information from previous research study on the local communities demographic and marine resources surrounding Pulau Sibu and Pulau Tinggi, Johor. The results were partially contributing to a baseline information of this project. Despite the slow start, the project is believed to be able to catch up with the proposed timeline. However, pending to the meeting outcome between federal and state government discussion, it may be necessary to amend the proposed activities for this project to fit into the big picture.

  - Project implementation progress

| Outputs & Activities | Expected completion date | Implementation status as of end of reporting period expressed in % | Describe any problems in delivery and any changes/mitigation action required. |
| --- | --- | --- | --- |
| Output 1: Governance structures for community involvement in conservation and monitoring of dugong and seagrass ecosystems established or strengthened in target areas |  |  |  |
| Activity 1: Stocktaking: Community participation in project site | December 2017 | 30% |  |
| Activity 2: Stakeholder and community consultation and socialisation | December 2018 | 30% |  |
| Activity 3: Communication, education and awareness programme | September 2018 | 10% |  |
| Activity 4: Community Consultative Committee meetings | September 2018 | 10% |  |
| Activity 5: Training: Community involvement in consultative management of project sites | December 2017 | 0 |  |
| Output 2: Policy, planning and regulatory gaps reviewed (conservation of dugongs and seagrass ecosystems) and recommendations developed |  |  | Similar work is being conducted by the Johor State Government which will create redundancy. Currently discussion between state and federal government is ongoing. Changes in activity and timeline may be required, pending to the outcome of the meeting. |
| Activity 1: Data information and stocktaking-link to MY4 | December 2017 | 30% |  |
| Activity 2: Development of the management plan and proposal of dugong and seagrass sanctuary | July 2017 | 0% |  |
| Activity 3: Stakeholder and community consultation on Management Plan and proposed Dugong-Seagrass Sanctuary-Link to MY4 | July 2017 | 0% |  |
| Activity 4: Management Plan- Deliver | December 2017 | 0% |  |
| Activity 5: Management Plan Training | December 2018 | 0% |  |
| Activity 6: Completion of Proposal of Dugong-Seagrass Sanctuary | October 2017 | 0% |  |
| Activity 7: Submission of the Proposal of Dugong-Seagrass Sanctuary to NSC | December 2017 | 0% |  |
| Activity 8: Endorsement of Regulations on Fisheries Management for Dugong-Seagrass Sanctuary under Fisheries Act 1985 by National Steering Committee (NSC) | April 2018 | 0% |  |
| Activity 9: Monitoring and evaluation | December 2018 | 0% |  |
| Output 3: |  |  |  |
| Activity 4: |  |  |  |
| Activity 5: |  |  |  |
| Output 4: |  |  |  |
| Activity 6: |  |  |  |
| Activity 7: |  |  |  |

  - Risk and risk management

Please describe internal and external risks (examples included in brackets) that could affect successful implementation of project activities and the proposed risk mitigation measures.

| Risk group | Description | Risk level (Low/ Medium/ High) | Mitigation measures |
| --- | --- | --- | --- |
| Project Management (team capacity, internal communication, co-financing, budget, financial management, reporting, etc.) | The start of the project is delayed due to legal issue of the government agency receiving direct funding. This leads to two implementing partners creating a communication gap. | Low | The government agency implementing partner has appointed NGO as a third party to receive fund and to implement the programme of work together. The communication gap can be improved with consistent and scheduled updates. |
| Socio-cultural issues (external communications, capacity of and work with stakeholders, cultural aspects) | The local community culture of having the lack of trust on non-islanders makes the stocktaking process to be slightly longer than anticipated. | Medium | We have hired a full time staff to be based on the project site to blend in and understand the local stakeholders and community. |
| Political risks (Political stability in country, political impacts on the project) | Jurisdiction and interest overlap between federal and state government over the same project area. Both government agencies have similar objectives which caused some of the current programme of work to be modified. | High | Department of Marine Park as Federal government agency, have taken the initiative to meet and discuss possibility of co-management with the state government. |
| Environmental risks (severe weather events/ disasters, natural causes negatively affecting project areas, habitats and species) | Monsoonal season may be affecting the travel from mainland to island, which may affect the schedule of programme of work. | Low | Most programme of work will be planned and conducted during non-monsoon season. |
| Other (please specify) |  |  |  |

- MONITORING AND EVALUATION

  - Please describe activities for monitoring and evaluation carried out during the reporting period.

Examples include: baseline data collection, stakeholder surveys, field surveys, steering committee meetings to assess project progress, peer review of documentation to ensure quality, mid-term review, etc.

Do not include routine project reporting.

[INSERT TEXT HERE]

- OTHER INFORMATION

  - Meetings

| Meeting type | Title | Venue | Dates | Convened by | Organised by | No. of participants | Report issued Y/N | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Internal project partners meeting |  | Putrajaya | 1st July 2016 | Department of Marine Parks Malaysia (DMPM) | (DMPM) | 3 | N | English |  |
| National Project coordination Meeting | National Facilitation Meeting | Department of Fisheries office, Putrajaya | 4th October | Department of Fisheries (DoF) | Department of Fisheries (DoF) |  | N |  |  |
| Project Briefing to DMPM staff in Johor | Briefing on GEF Dugong-Seagrass Project-MY1 | Department of Marine Park Johor | 20th October | Department of Marine Park | Department of Marine Park | 15 | N | Bahasa |  |
| State technical meeting | Dugong Sanctuary Technical Committee Meeting | Kota Iskandar, Iskandar Puteri, Johor | 11th October 2016 | Johor State Government | Johor State Government |  | Y | Bahasa |  |
| National Project coordination Meeting | National Facilitation Meeting | Department of Fisheries office, Johor. | 25th October 2016 | Department of Fisheries (DoF) | Department of Fisheries (DoF) |  | N | Bahasa |  |
| Discussion With Project Coordinator Team | Discussion With Project Coordinator Team | Hotel Royale Chulan Damansara, Kuala Lumpur | 31 October | PCT | Department of Fisheries (DoF) | 10 | N | English |  |

  - List(s) of meeting participants

| No. | Name of participant | Nationality |
| --- | --- | --- |
| 1. | Syed Abdullah Syed Abdul Kadir | Malaysian |
| 2. | Abdul Muntalib Juli | Malaysian |
| 3. | Izarenah Md Repin | Malaysian |
| 4. | Julian Hyde | British |
| 5. | Lau Chai Ming (Edmund) | Malaysian |
| 6. | Nazirul Amin | Malaysian |
| 7. | Louisa Shobini Ponnampalam | Malaysian |
| 8. | Fairul Izmal | Malaysian |
| 9. | Nicolas Pilcher |  |
| 10. | Leela Rajamani | Malaysian |
| 11. | Sim Yee Kwang | Malaysian |

  - Documents, other printed materials, videos, and soft products (such as CDs or websites)

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication date |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Research Report | Status Report On The Marine Environment Of The Mersing Marine Park Islands, And Indicative Proposal For The Establishment Of A Marine Protected Area (MPA) Network | Dr. Jillian Ooi |  |  |  |
| 2. | Research Report | A Study Of Potential New Areas To Be Gazetted As State Of Johor Marine Parks | Assoc. Prof. Dr. Rosman bin Abdullah |  |  |  |

| Name of Project Manager: Julian Hyde | Name of Project Manager Supervisor: Abd Muntalib bin Juli |
| --- | --- |
| Signature: | Date: | Signature: | Date: |

# Footnotes

Briefly describe progress made during the previous six months highlighting major outcomes/benchmarks achieved during the period.

Information provided in “Quarterly Expenditure Report” should be in line with output/activity progress reported in this table.

Outputs and activities as described in the project proposal or in any updated project revision. Expand table as necessary.

Expand table as necessary

Meeting types: e.g. expert group meeting, project inception workshop, training workshop/seminar, partners consultation workshop, project Steering Committee meeting etc.

Expand table as necessary

Documents and printed material types: e.g. technical publication, meeting report, technical/substantive report, brochures, media releases, etc.