The GEF Dugong and Seagrass Conservation Project

Project Progress Report

| Reporting Period | From: | 1 July 2016 | To: | 31 December 2016 |
| --- | --- | --- | --- | --- |

- PROJECT GENERAL INFORMATION

| National Project Code & Title: | MY4-2114; A multi-pronged approach in overcoming knowledge barriers on the ecology and status of dugongs in Johor, Malaysia - Towards critical habitat protection |
| --- | --- |

| Project Partner(s): | The MareCet Research Organization |
| --- | --- |

| Location (country, region/ district and commune/ city/ village/ region etc.) | Country: Malaysia State: Johor Region: Sibu-Tinggi Archipelago, Johor east coast |
| --- | --- |
| Of which areas under protection (please indicate the name and size of protected areas or locally managed marine areas, if applicable) | Sultan Iskandar Marine Park, Johor east coast, Malaysia (765.65 km2) (a.k.a Tinggi Island Marine Park) |

| Project start date | 01 Jan 2015 (started earlier than GEF project due to conferment of Pew Fellowship to Louisa Ponnampalam) | Project intended completion date | Sep 2018 |
| --- | --- | --- | --- |

- PROJECT PROGRESS

  - Narrative of project progress during the past semester by Project Activity

Main challenges and achievements in bullet points Describe according to project activity (as per proposal), what has happened during this reporting period (results, plans) Main challenges: Unpredictable weather conditions during aerial surveys Getting appointments to meet with key community leaders Getting some interview respondents to be fully committed to the entire interview survey Achievements: Completion of aerial surveys (since 2014, when project started with funding from another source), the data of which are being sorted and prepped for detailed analyses**. In 2016, aerial surveys were conducted in April, August and October 2016; data from the latter two most recent surveys are being sorted at the moment Completion of two seagrass mapping surveys whereby we collected data on seagrass diversity, occurrences of dugong feeding trails, and boundaries of the seagrass meadows around the Sibu Archipelago** Completion of two seagrass mapping surveys and three seagrass sampling surveys whereby we collected initial data on the distribution and characteristics of dugong feeding trails and seagrass samples for analyses of nutrient composition (C, N, P, starch, fiber)** Completion of 271 interviews (152 of which are fishers) whereby we collected data and feedback from local community members on their perceptions and opinions of dugong and seagrass conservation plans for the Johor east coast islands and adjacent waters. More interviews with fishermen are scheduled for March 2017, after which the data will be analysed Interest and support of the Johor State authorities for dugong and seagrass conservation in Johor Plans moving forward for the delineation of a dugong and seagrass conservation area and the drafting of a management plan for said area – consultative sessions with local communities on the delineation and zoning within proposed dugong sanctuary were held in Nov 2016 and the next one with government agencies scheduled for Feb 2017 Completed an exhibition on dugongs and seagrass in August 2016 in conjunction with the Sultan of Johor’s annual 2016 Islands Expedition (GEF funds not used for this, but reported to show overall progress of MareCet’s efforts in dugong conservation) **Some of the initial results, figures and progress may be viewed in Appendices B - D of the previous half-yearly report from Aug 2016 (see folder “Misc supporting docs”, where this document has been included for ease of reference)

  - Project implementation progress

| Outputs & Activities | Expected completion date | Implementation status as of end of reporting period expressed in % | Describe any problems in delivery and any changes/mitigation action required. |
| --- | --- | --- | --- |
| Output 1.3 Integrated community management plans (conservation and monitoring of dugong and seagrass ecosystems) developed and piloted | 2018 | 30 | N/A |
| Activity 1.3.1 Discussions and meetings to establish a dugong and seagrass conservation steering committee group among the various stakeholders | Q2 2017 | 10 | Need better coordination among various agencies and stakeholders during discussions and MareCet to help steer this in the right direction |
| Activity 1.3.2 Discussions and meetings with govt agencies (e.g. Marine Department, Maritime Enforcement Agency) and local groups (e.g. villagers, boat and resort operators) to introduce and establish the concept of speed limit zone in high dugong areas | Q2 2017 | 20 | N/A |
| Activity 1.3.3 Speed limit zone adopted and demarcation buoys deployed | End 2017 | 2 | N/A |
| Output 3.1 Critical knowledge gaps (dugongs and seagrass ecosystems) identified and surveys initiated/ completed | End 2017 | 40 | N/A |
| Activity 3.1.1 Aerial surveys | End 2017 | 60 | N/A |
| Activity 3.1.2 Seagrass surveys | End 2017 | 40 | N/A |
| Activity 3.1.3 Contaminant studies | Q1 2018 | 30 | Analyses underway, and seeking additional funds for analyses |
| Activity 3.1.4 Socio-economic studies | End 2017 | 20 | N/A |
| Output 4.1 Policy, planning and regulatory gaps reviewed (conservation of dugongs and seagrass ecosystems) and recommendations developed | Q1 2017 | 40 | Need better coordination among various agencies and stakeholders during discussions and MareCet to help steer this in the right direction |
| Activity 4.1.1 Presentation of core research findings to relevant govt agencies | Twice a year | 50 | N/A |
| Activity 4.1.2 Roundtable discussions on MPA planning for dugong and seagrass | Mid-2017 | 35 | Need better coordination among various agencies and stakeholders during discussions and MareCet to help steer this in the right direction. |

  - Risk and risk management

Please describe internal and external risks (examples included in brackets) that could affect successful implementation of project activities and the proposed risk mitigation measures.

| Risk group | Description | Risk level (Low/ Medium/ High) | Mitigation measures |
| --- | --- | --- | --- |
| Project Management (team capacity, internal communication, co-financing, budget, financial management, reporting, etc.) | Team capacity | Low | To plan ahead and ensure enough project personnel available to conduct project activities |
| Socio-cultural issues (external communications, capacity of and work with stakeholders, cultural aspects) | Lack of cooperation among project partners, attempted sabotage and undermining of team’s efforts Reluctance of local community members and stakeholders to provide full cooperation during community consultative interviews | Medium – High Medium - High | Transparent reporting to the PCT and appropriate measures taken to look into such matters Ensure good communicators are present on the MPA/LMMA consultation team, both from the NGO and government sides |
| Political risks (Political stability in country, political impacts on the project) | Lack of political will for MPA/LMMA expansion planning | Medium | Ensure that key findings and consequences of not acting on conservation measures are communicated simplistically and often to the relevant government agencies; Inclusion of government agencies on both Federal and State levels to encourage active participation in the project |
| Environmental risks (severe weather events/ disasters, natural causes negatively affecting project areas, habitats and species) | Poor and erratic weather conditions | Medium - High | Check the best available weather forecast ahead of scheduled fieldwork periods; Allow for up to 3 days as a buffer to remain in the field to complete work in case work was hampered by poor weather |
| Other (please specify) | The rising costs of living and materials in Malaysia | Medium - High | Always look for the best offers and pricing ahead of time and where possible, negotiate suitable rates for equipment/ service which will remain constant throughout the duration of the project |

- MONITORING AND EVALUATION

  - Please describe activities for monitoring and evaluation carried out during the reporting period.

Examples include: baseline data collection, stakeholder surveys, field surveys, steering committee meetings to assess project progress, peer review of documentation to ensure quality, mid-term review, etc.

Do not include routine project reporting.

N/A

- OTHER INFORMATION

  - Meetings

| Meeting type | Title | Venue | Dates | Convened by | Organised by | No. of participants | Report issued Y/N | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MY DSCP partners meeting | Meeting to discuss compilation of MY country report for EPSC II meeting and streamlining of MY project activities | Department of Fisheries Malaysia, Putrajaya | 4 Oct 2016 | Tn Syed Abdullah (MY GEF DSCP National Focal Point) | Dept of Fisheries Malaysia | 10 | N | N/A |  |
| Expert group meeting | Meeting of the Technical Committee for the Johor Dugong Sanctuary | Johor National Parks Corporation HQ, Nusajaya, Johor | 11 Oct 2016 | YB Datuk Hj Ayub Rahmat (Johor EXCO for Health and Environment) | Johor National Parks Corporation | 24 | Y | Bahasa Malaysia | 11 Oct 2016 |
| MY DSCP partners meeting | Meeting to discuss compilation of MY country report for EPSC II meeting | Department of Fisheries Malaysia, Johor | 25 Oct 2016 | Tn Syed Abdullah (MY GEF DSCP National Focal Point) | Dept of Fisheries Malaysia | 9 | N | N/A |  |
| MY DSCP partners meeting with GEF DSCP PCT | Meeting to discuss progress of MY GEF DSCP projects and MTR expectations | Hotel Royal Chulan Damansara | 31 Oct 2016 | Maya Bankova (GEF DSCP PCT) | Dept of Fisheries Malaysia | 17 | N | N/A |  |
| Community consultative discussions | Interview surveys for the proposed dugong sanctuary – local stakeholders’ perceptions and knowledge awareness about dugongs and conservation | Various villages along the Johor east coast (Mersing to Tanjung Sedili), and on Sibu and Tinggi Islands | 6/10/16 – 8/11/16 | Lee Sok Fen (MY4 project member) | MareCet | 2 | N | N/A |  |
| MY DSCP partners fieldtrip with GEF DSCP PCT | Fieldtrip to Pulau Sibu and Pulau Tinggi for the PCT to visit Johor project sites | Pulau Sibu, Pulau Tinggi, Tanjung Leman, Mersing | 3 – 5/11/16 | Tn Syed Abdullah (MY GEF DSCP National Focal Point) | MareCet | 16 | Y | English | 10/11/16 |
| Community consultative discussions | Presentation of draft delineation of Johor dugong sanctuary | Pulau Sibu, Pulau Tinggi, Tanjung Leman, Mersing | 28 – 29/11/16 | MareCet | MareCet | 8 – 20 pax | N (draft delineation report to be submitted soon to the Johor National Parks Corporation) | N/A |  |

  - List(s) of meeting participants*

| No. | Name of participant | Nationality |
| --- | --- | --- |
| 1 | Datuk Hj Ayub Rahmat | Malaysia |
| 2 | Syed Abdullah Syed Abdul Kadir | Malaysia |
| 3 | Hj Shakib Hj Mohd Ali | Malaysia |
|  | Sukarno Wagiman | Malaysia |
| 4 | Fairul Izmal Jamal Hisne | Malaysia |
| 5 | Lee Sok Fen | Malaysia |
| 6 | Lili Tokiman | Malaysia |
| 7 | Leela Rajamani | Malaysia |
| 8 | Zamani Omar | Malaysia |
| 9 | James Bali | Malaysia |
| 10 | Ng Jol Ern | Malaysia |
| 11 | Julian Hyde | United Kingdom |
| 12 | Izarenah Mat Repin | Malaysia |
| 13 | Mohd Nizam Ismail | Malaysia |
| 14 | Abdul Muntalib Juli | Malaysia |
| 15 | Mohd Tamimi Ali | Malaysia |
| 16 | Toloy Keripin | Malaysia |
| 17 | Halid Salleh | Malaysia |
| 18 | Fishermen and local community members of Pulau Sibu, Pulau Tinggi, Tanjung Leman and Mersing | Malaysia |

* I do not have the participants list for each meeting as it was not made available, so I have listed the main attendees as I remember. This list also does not include the names of people who were at the community consultative meetings/interviews.

  - Documents, other printed materials, videos, and soft products (such as CDs or websites) (produced under the project)

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Newspaper article | The damsel of the sea | Lim Su Lin | Focus Malaysia | N/A | October 2014 |
| 2 | Short video | Ever wondered what dugongs eat? | MareCet | MareCet | N/A | September 2014 |
| 3 | Short video | Dugongs Eating, Swimming, and Serving as Seagrass "Mascots" ¦ One Minute Dive with Pew | The Pew Charitable Trusts | The Pew Charitable Trusts | N/A | 18 February 2015 |
| 4 | Short video | Dugongs in Johor – 7 Sep 2015 | MareCet | MareCet | N/A | September 2015 |
| 5 | Info flyer | Dugong Research and Conservation | MareCet | MareCet | N/A | October 2015 |
| 6 | Newsletter | Updates on dugong research and conservation | MareCet | MareCet | N/A | April 2016 |
| 7 | Poster | Mapping dugong habitat and understanding dugong feeding habits in the Johor east coast islands | Jillian Ooi, Louisa Ponnampalam, Heng Wei Khang | University Malaya | N/A | 22 April 2016 |
| 8 | Online photo album | Seagrass mapping & dugong feeding trails survey, June 2016 | MareCet | MareCet | N/A | June 2016 |
| 9 | Short video | Endangered dugongs of Johor | MareCet | MareCet | N/A | 15 December 2016 |
| 10 | Short video | A multi-pronged approach in overcoming knowledge barriers on the ecology and conservation needs of dugongs in Johor, Malaysia – Towards critical habitat protection | MareCet | MareCet | N/A | Not published yet (coming soon on social media) |

| Name of Project Manager: Louisa Shobhini Ponnampalam | Name of Project Manager Supervisor: N/A |
| --- | --- |
| Signature: | Date: 10 January 2017 | Signature: | Date: |

Appendix A

Some photos from activities conducted between July and December 2016

August and October 2016 – Aerial surveys

October 2016 – Seagrass surveys (mapping and feeding trails study)

November 2016 – Impromptu visit to the primary school on Sibu Island while we were in the area on seagrass and acoustic survey

October to November 2016 – Interviews with local communities on conservation perceptions and willingness to participate in conservation

# Footnotes

Briefly describe progress made during the previous six months highlighting major outcomes/benchmarks achieved during the period.

Information provided in “Quarterly Expenditure Report” should be in line with output/activity progress reported in this table.

Outputs and activities as described in the project proposal or in any updated project revision. Expand table as necessary.

Expand table as necessary

Meeting types: e.g. expert group meeting, project inception workshop, training workshop/seminar, partners consultation workshop, project Steering Committee meeting etc.

Expand table as necessary

Documents and printed material types: e.g. technical publication, meeting report, technical/substantive report, brochures, media releases, etc.