The GEF Dugong and Seagrass Conservation Project

Project Progress Report

| Reporting Period | From: | January / 2016 | To: | June / 2016 |
| --- | --- | --- | --- | --- |

- PROJECT GENERAL INFORMATION

| National Project Code & Title: | Project MZ2 – 2117 The distribution of dugongs in the coastal waters of Mozambique |
| --- | --- |

| Project Partner(s): | Associação para a conservação e protecção de dugongos e espécies de mamíferos marinhos Centre for Dolphin Studies Nelson Mandela Metropolitan University |
| --- | --- |

| Location (country, region/ district and commune/ city/ village/ region etc.) | Central Mozambique Coast |
| --- | --- |
| Of which areas under protection (please indicate the name and size of protected areas or locally managed marine areas, if applicable) | Bazaruto Archipelago National Park |

| Project start date | September 2015 | Project intended completion date | September 2018 |
| --- | --- | --- | --- |

- PROJECT PROGRESS

  - Narrative of project progress during the past semester by Project Activity

Output 1: Critical knowledge gaps (dugongs and seagrass ecosystems) identified and surveys initiated/ completed Activity 1.1: Surveys of potential dugong habitat (seagrass ecosystem identification) through remote sensing and surveys of beach-cast seagrass where water turbidity precludes remote sensing. Existing information on seagrasses of Central Mozambique coast, as well as satellite imagery has been compiled for future analysis. Logistics for fieldwork (seagrass sampling and mapping validation) are under preparation. A Canon G16 camera with an underwater housing was acquired and other sampling equipment (e.g. quadrats, containers, etc.) are being prepared. Activity 1.2: Questionnaire surveys and focal group meetings in coastal communities across the Mozambique coastline A hundred and sixty (160) questionnaire surveys were carried out in south of the Bazaruto archipelago (Massinga district) and North of the Bazaruto Archipelago (Govuro, Machanga, Buzi, Beira and Dondo). During the questionnaire surveys a number of focal group meetings were also carried out. Meetings with local NGOs ((EWT, WWF, Marine Megafauna Foundation – MMF, Centro Terra Viva – CTV, Ocean Revolution) that deal with marine conservation were carried out. The meetings served to inform them about our activities in the field, and promote cooperation among the organizations in order to facilitate work and avoid duplication of efforts. Activity 1.3: Acoustic monitoring of dugong presence (where water quality precludes aerial or boat surveys) Six acoustic loggers and eighteen batteries were acquired and imported to Mozambique. A meeting was carried out in Plettenberg Bay (South Africa), from the 5th to the 8th of February for project planning and training on the use of acoustic loggers. Eight participants attended this meeting. Permits to undertake the aerial survey and set the listening stations were obtained with local authorities. The first theoretical training for the aerial survey was undertaken in November, however because the weather prevented the aircraft to fly, the practical training and survey were postponed to January 2017.

Output 2: Good practice guideline for dugongs and seagrasses ecosystems conservation developed from project experience Activity 2.1: Review of both historic and recent information on dugong distribution and abundance across Mozambique waters Activity 2.2: Collate and compile the review information into a national knowledge base A baseline with past and current information on dugongs’ distribution and abundance in Mozambique coast is being collated for future analysis. Further, reports, conservation plans and legal framework are being compiled to serve as basis for analysis and development of a good practices guideline for dugongs and seagrasses conservation in Mozambique.

Output 3: Conservation-relevant information and guidance (dugongs and seagrasses ecosystems) collated and disseminated Activity 3.1: Identifying past and proposed activities that have contributed or are likely to contribute to changes in dugong conservation and knowledge and awareness thereof Activities proposed by the conservation plan proposed in 2009 were being reviewed taking into consideration results from the other activities of this project. The report was translated into Portuguese and shared with local stakeholders.

Output 4: Capacity for national and regional networking and contribution to global policy for effective dugong and seagrass conservation in the Indian and Pacific Ocean basins. Activity 4.1: Assessment of the historic and current status of dugongs across Mozambique waters For analysing the status of the dugong across Mozambique waters, a research is being conducted by a Mozambican PhD student, Alima Taju, registered at Nelson Mandela Metropolitan University in Port Elizabeth. Under her research she will assess dugongs’ abundance and distribution, study the genetic population structure and variability, and analyse impacts to the species and its habitats in Mozambique coast. The PhD proposal was prepared and presented to the university board in March.

  - Project implementation progress

| Outputs & Activities | Expected completion date | Implementation status as of end of reporting period expressed in % | Describe any problems in delivery and any changes/mitigation action required. |
| --- | --- | --- | --- |
| Output 1: Critical knowledge gaps (dugongs and seagrass ecosystems) identified and surveys initiated/ completed |
| Activity 1.1: Surveys of potential dugong habitat (seagrass ecosystem identification) through remote sensing and surveys of beach-cast seagrass where water turbidity precludes remote sensing | September 2018 | 15% |  |
| Activity 1.2: Questionnaire surveys and focal group meetings in coastal communities across the Mozambique coastline | September 2018 | 50% |  |
| Activity 1.3: Acoustic monitoring of dugong presence/absence (where water quality precludes aerial or boat surveys) | September 2018 | 5% | The costs to use a national aircraft was extremely high comparing to using a South African aircraft, thus in order to increase the sampling effort the second option was preferred. However, the processes to obtain permits to undertake the aerial survey with an international aircraft took longer than expected, but they were finally issued at the end of November 2016. Extreme weather events that are common during summer may pose a constraint to the planned schedule. |
| Output 2: Good practice guideline for dugongs and seagrasses ecosystems conservation developed from project experience |  |  |  |
| Activity 2.1: Review of both historic and recent information on dugong distribution and abundance across Mozambique waters | September 2018 | 50% |  |
| Activity 2.2: Collate and compile the review information into a national knowledge base | September 2018 | 30% |  |
| Activity 2.3: Assess and define historic and contemporary dugong distribution and seasonal (relative) abundance from reviewed data where possible, with the aim of identifying changes | September 2018 | 30% |  |
| Output 3: Conservation-relevant information and guidance (dugongs and seagrasses ecosystems) collated and disseminated |  |  |  |
| Activity 3.1: Identifying past and proposed activities that have contributed or are likely to contribute to changes in dugong conservation and knowledge and awareness thereof | September 2018 | 0% |  |
| Output 4: Capacity for national and regional networking and contribution to global policy for effective dugong and seagrass conservation in the Indian and Pacific Ocean basins. |  |  |  |
| Activity 4.1: Assessment of the historic status of dugongs across Mozambique waters | September 2018 | 50% |  |
| Activity 4.2: Assessment of current status of dugongs across Mozambique waters | September 2018 | 10% |  |

  - Risk and risk management

Please describe internal and external risks (examples included in brackets) that could affect successful implementation of project activities and the proposed risk mitigation measures.

| Risk group | Description | Risk level (Low/ Medium/ High) | Mitigation measures |
| --- | --- | --- | --- |
| Project Management (team capacity, internal communication, co-financing, budget, financial management, reporting, etc.) | Risk of theft of the acoustic loggers during the recording period | High | The acoustic loggers will be placed preferentially in places where fishing/boating activity is very reduced, and a satellite tracked will be attached to the loggers, so the equipment can be tracked in case of theft. Local authorities and communities are also being prevented the equipment will be in the water and shall not be taken. |
| Socio-cultural issues (external communications, capacity of and work with stakeholders, cultural aspects) |  |  |  |
| Political risks (Political stability in country, political impacts on the project) | Political instability in Central Mozambique may prevent traveling safely to sampling areas between the provinces of Inhambane/Sofala and Quelimane. | Medium | Precautions will be taken prior travels, and when possible aerial and boat transportation will be used to get to the sampling areas. |
| Environmental risks (severe weather events/ disasters, natural causes negatively affecting project areas, habitats and species) | Frequent storms during Summer (mainly from November to late February) can be a constraint to the aerial survey and passive acoustic monitoring. Heavy storms and cyclones can potentially drag the listening stations to other sites. | Medium | Aerial surveys will be avoided in when weather forecasts indicate an upcoming storm. Protected sites and clear waters will be preferred to set the listening stations during the summer. Murky waters will be assessed when the risks of storms are reduced. |
| Other (please specify) |  |  |  |

- MONITORING AND EVALUATION

  - Please describe activities for monitoring and evaluation carried out during the reporting period.

Examples include: baseline data collection, stakeholder surveys, field surveys, steering committee meetings to assess project progress, peer review of documentation to ensure quality, mid-term review, etc.

Do not include routine project reporting.

- OTHER INFORMATION

  - Meetings

| Meeting type | Title | Venue | Dates | Convened by | Organised by | No. of participants | Report issued Y/N | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

  - List(s) of meeting participants

| No. | Name of participant | Nationality |
| --- | --- | --- |

  - Documents, other printed materials, videos, and soft products (such as CDs or websites)

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication date |
| --- | --- | --- | --- | --- | --- | --- |

| Name of Project Manager: Almeida Guissamulo | Name of Project Manager Supervisor: Vic Cockcroft |
| --- | --- |
| Signature: | Date: | Signature: | Date: |

# Footnotes

Briefly describe progress made during the previous six months highlighting major outcomes/benchmarks achieved during the period.

Information provided in “Quarterly Expenditure Report” should be in line with output/activity progress reported in this table.

Outputs and activities as described in the project proposal or in any updated project revision. Expand table as necessary.

Expand table as necessary

Meeting types: e.g. expert group meeting, project inception workshop, training workshop/seminar, partners consultation workshop, project Steering Committee meeting etc.

Expand table as necessary

Documents and printed material types: e.g. technical publication, meeting report, technical/substantive report, brochures, media releases, etc.