The GEF Dugong and Seagrass Conservation Project

Project Progress Report

| Reporting Period | From: | July / 2016 | To: | December / 2016 |
| --- | --- | --- | --- | --- |

- PROJECT GENERAL INFORMATION

| National Project Code & Title: | SB5 Strengthening provincial and national capacity for project implementation in the Solomon Islands |
| --- | --- |

| Project Partner(s): | WorldFish |
| --- | --- |

| Location (country, region/ district and commune/ city/ village/ region etc.) | Solomon Islands |
| --- | --- |
| Of which areas under protection (please indicate the name and size of protected areas or locally managed marine areas, if applicable) | not applicable |

| Project start date | March 2016 | Project intended completion date | September 2018 |
| --- | --- | --- | --- |

- PROJECT PROGRESS

  - Narrative of project progress during the past semester by Project Activity

In the July to December 2016 period, there were four key activities that were carried out: 2nd NFC meeting. The key outcome of the meeting was the NFC call for more participation and/or information sharing on activities being implemented by the partners and providing recommendations to MFMR on prioritising regulations on ban on selling of dugong meat. Recommendations were also made to improve on the way partners provided updates by way of reporting template. The trip by the National Facilitator to attend the ESPC meeting in Kuala Lumpur, 1-2 Nov 2016. Chris as National Facilitator represented the Solomon Islands in place of Agnetha. At this meeting Chris shared Extra Ordinary meeting of the NFC for the development of the National Dugong and Seagrass Strategy. WorldFish convened this meeting to provide an outline of a Strategy and get feedback from the NFC on the outline itself, title and consultation process for this document. There was general consensus on the outline and discussions focused on a consultation process to ensure the Strategy was circulated. A draft report is available in the Dropbox file. 3rd NFC meeting. The third NFC meeting happened on December 12th 2016. This was moved to the end of the year due to commitments of partners in implementation of activities. The objective was to provide partner updates to the NFC and to relay information regarding the upcoming review. Draft report is pending. In October, a three day workshop from the 24-26 was held in Auki, Malaita Province. The workshop was an inception workshop for two WorldFish projects that is being implemented in Malaita Province by ADB and SwedBio. During this workshop, Delvene highlighted the work of the GEF Dugong and Seagrass Project in Lau Lagoon. A report is provided in Dropbox. *Two of WorldFish’s projects funded by the Asian Development Bank (ADB) and the Pacific Community (SPC) (the latter is mentioned in the HYP for SB3), are supportive of the Lau work. These projects focus on CBRM+ which includes threatened species. This has resulted in the attention for dugongs not only in Lau, but in Langalanga Lagoon near Auki. *CBRM+ is defined in the Solomon Islands National Plan of Action (SINPoA) for the Coral Triangle Initiative on Coral Reefs, Fisheries and Food Security (CTI-CFF) as Community-based Resource Management approaches covering climate change vulnerability and adaptation assessment, ecosystem approaches, food security, and management of key species and habitats and appropriate use of protected areas.

  - Project implementation progress

| Outputs & Activities | Expected completion date | Implementation status as of end of reporting period expressed in % | Describe any problems in delivery and any changes/mitigation action required. |
| --- | --- | --- | --- |
| Output 4.3 Capacity for national and regional networking and contribution to global policy for effective dugong and seagrass conservation in Indian and Pacific Ocean basins |  |  |  |
| Activity 4.3.3 Conduct four National Steering Committees per year | September 2018 | 100% completed for 2016 | By December 2016, three NFC meetings were held. A third meeting was planned for quarter three, however the NFC members agreed to combine the third and fourth meeting of the NFC to December 2016 instead. This was due to engagements of members of the NFC at that time. A recommendation is to reduce the number of NFC meetings to 3 per year. |
| Output 4.1 Policy, planning and regulatory gaps reviewed (conservation of dugongs and seagrass ecosystems) and recommendations developed |  |  |  |
| Activity 4.1.1 Develop the National Dugong and Seagrass Conservation Strategy | July 2018 | 5% complete. | In November 2016 the NFC convened for a meeting on the process for developing the National Dugong and Seagrass Conservation Strategy. This work is being led by Dr Johan Van der Ploeg. A timeline has been drafted for the development of the document for December 2017. An outline was presented for discussion. A summary meeting report is available in draft form. While a Dec 2017 might be tight, a clear implementation plan will need to be developed to ensure that tasks are checked. |

  - Risk and risk management

Please describe internal and external risks (examples included in brackets) that could affect successful implementation of project activities and the proposed risk mitigation measures.

| Risk group | Description | Risk level (Low/ Medium/ High) | Mitigation measures |
| --- | --- | --- | --- |
| Project Management (team capacity, internal communication, co-financing, budget, financial management, reporting, etc.) | Team capacity: a key staff exit will might mean delays in activities for 2017, particularly for quarter 1. Chrisanto Daokalia submitted his resignation from WorldFish in January 2017 and will end his tenure in mid-February 2017. WorldFish will advertise for a replacement person which will hopefully be recruited by March 2017. Financial reporting: WorldFish has been unable to submit its reports on time for 2016. Financial reporting delays may be a risk to project implementation | Low-Med Med-High | WorldFish will advertise a replacement position looking for a graduate preferably with working experience. Now that the arrangement for sitting at MECDM for two days a week has been finalised for Tuesdays and Thursdays, mentorship by govt will aide in bringing the person up to speed. Processes for field work and community contacts have already been established and so these will maintained Issue will need to be solved in January 2017 so that activities can proceed. Ensure communication with all team members |
| Socio-cultural issues (external communications, capacity of and work with stakeholders, cultural aspects) |  | Low |  |
| Political risks (Political stability in country, political impacts on the project) | None | Low | Promote and work in partnership with related Government line ministries rather than political figures to ensure neutral project stand. |
| Environmental risks (severe weather events/ disasters, natural causes negatively affecting project areas, habitats and species) | There is not much of a concern in terms of environmental risks | Low | Safety will be paramount in any field work. |
| Other (please specify) |  |  |  |

- MONITORING AND EVALUATION

  - Please describe activities for monitoring and evaluation carried out during the reporting period.

Examples include: baseline data collection, stakeholder surveys, field surveys, steering committee meetings to assess project progress, peer review of documentation to ensure quality, mid-term review, etc.

Do not include routine project reporting.

None for SB5 other than review at NFC meetings

- OTHER INFORMATION

  - Meetings

| Meeting type | Title | Venue | Dates | Convened by | Organised by | No. of participants | Report issued Y/N | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Steering Committee Meeting | 2nd meeting of the NFC | Ministry of Fisheries and Marine Resources (MFMR) Conference room, Honiara | 27 Jul 2016 | Chrisanto Daokalia | WorldFish, SICCP, MECDM, MFMR |  | Y | English | 12 Dec 2016 |
| Partners consultation workshop | Workshop on supporting community-based resource management and supplementary livelihoods in Malaita, Solomon Islands | Bahai Conference Room, Auki, Malaita Province | 24-26 October 2016 | Jan Van der Ploeg | WorldFish | 46 | Y | English | October 2016 |
| Project Steering Committee Meeting | EPSC Meeting, Kuala Lumpur | Royal Chulan Damansara Hotel, KL, Malaysia | 31 Oct-4 Nov 2016 | EPSC | EPSC |  | N |  |  |
| Project Steering Committee Meeting | Extra Ordinary NFC meeting for the National Dugong and Seagrass Conservation Strategy | WorldFish Office, Honiara | 18 Nov 2016 | Jan Van der Ploeg | WorldFish |  | In Draft Form | English |  |
| Project Steering Committee Meeting | 3rd Meeting of the NFC |  | 12 Dec 2016 | Chrisanto Daokalia | WorldFish |  | In Draft Form | English |  |

  - List(s) of meeting participants

2nd NFC meeting

| No. | Name of participant | Nationality/Organization |
| --- | --- | --- |
| 1 | Agnetha Vave Karamui | MECDM |
| 2 | Rosalie Masu | MFMR |
| 3 | Delvene Boso | WorldFish |
| 4 | Lysa Wini-Simeon | IUCN/MECDM |
| 5 | Duta Kauhiona | CI/MFMR |
| 6 | Corzzierrah Posala | SICCP |
| 7 | Chrisanto Daokalia | WorldFish |

Extra Ordinary Meeting, NFC

| No. | Name of participant | Nationality/Organization |
| --- | --- | --- |
| 1 | Agnetha Vave Karamui | MECDM |
| 2 | Rosalie Masu | MFMR |
| 3 | Delvene Boso | WorldFish |
| 4 | Lysa Wini-Simeon | IUCN/MECDM |
| 5 | Duta Kauhiona | CI/MFMR |
| 6 | Corzzierrah Posala | SICCP |
| 7 | Chrisanto Daokalia | WorldFish |

3rd NFC meeting, 12 December 2016

| No. | Name of participant | Nationality/Organization |
| --- | --- | --- |
| 1 | Agnetha Vave Karamui | MECDM |
| 2 | Rosalie Masu | MFMR |
| 3 | Delvene Boso | WorldFish |
| 4 | Lysa Wini-Simeon | IUCN/MECDM |
| 5 | Duta Kauhiona | CI/MFMR |
| 6 | Corzzierrah Posala | SICCP |
| 7 | Chrisanto Daokalia | WorldFish |

  - Documents, other printed materials, videos, and soft products (such as CDs or websites)

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication/Submission date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Meeting Report | 2nd National Facilitation Committee Meeting Minutes | WorldFish, MECDM |  |  | 12 Dec 2016 |
| 2 | Meeting Report | Extra Ordinary NFC meeting for the National Dugong and Seagrass Conservation Strategy | WorldFish |  |  | Still in draft form |
| 3 | Meeting Report | 3rd National Facilitation Committee Meeting Minutes | WorldFish |  |  | Still in draft form |
| 4 | Meeting Report | Workshop on supporting community-based resource management and supplementary livelihoods in Malaita, Solomon Islands | WorldFish |  |  | 23-Nov-2016 |

| Name of National Facilitator: Chrisanto Daokalia | Name of Project Manager: Delvene Boso |
| --- | --- |
| Signature: | Date: 17 January 2017 | Signature: | Date: 17 January 2017 |

# Footnotes

Briefly describe progress made during the previous six months highlighting major outcomes/benchmarks achieved during the period.

Information provided in “Quarterly Expenditure Report” should be in line with output/activity progress reported in this table.

Outputs and activities as described in the project proposal or in any updated project revision. Expand table as necessary.

Expand table as necessary

Meeting types: e.g. expert group meeting, project inception workshop, training workshop/seminar, partners consultation workshop, project Steering Committee meeting etc.

Expand table as necessary

Documents and printed material types: e.g. technical publication, meeting report, technical/substantive report, brochures, media releases, etc.