The GEF Dugong and Seagrass Conservation Project

Project Progress Report

| Reporting Period | From: | Month / Year Jul/2016 | To: | Month / Year Dec/ 2016 |
| --- | --- | --- | --- | --- |

- PROJECT GENERAL INFORMATION

| National Project Code & Title: | LK 5 - 2131 Ensuring seagrass ecosystem values are incorporated with coastal area planning in Sri Lanka |
| --- | --- |

| Project Partner(s): | NARA |
| --- | --- |

| Location (country, region/ district and commune/ city/ village/ region etc.) | Puttalam/Mannar/Jaffna |
| --- | --- |
| Of which areas under protection (please indicate the name and size of protected areas or locally managed marine areas, if applicable) | Bar Reef Marine Sanctuary; 306 km2 |

| Project start date | June 2015 | Project intended completion date | September2018 |
| --- | --- | --- | --- |

- PROJECT PROGRESS

Table 1

  - Narrative of project progress during the past semester by Project Activity

Pl see the annex

  - Project implementation progress

| Outputs & Activities | Expected completion date | Implementation status as of end of reporting period expressed in % | Describe any problems in delivery and any changes/mitigation action required. |
| --- | --- | --- | --- |
| Output 3.1: |  |  |  |
| Activity 1: plan the survey | July 2015 | 100% | The field work started in Nov 2015 after receiving the money and the should had to wait until the clearance obtained to proceed to field |
| Activity 2: Review of the existing collected data | March 2016 | 100% |  |
| Activity 3 :Preparation of Seagrass distribution maps in spatial scales | March 2018 | 24% |  |
| Activity 4:Ground truthing and monitoring | March 2018 | 24% | Conducting parallel with the field trips |
| Activity 5 : Continuous updating and validation of seagarass distribution maps by monitoring in temporal scale | March2018 | 10% |  |
| Activity 6: Identification of important habitats to be study in details | April 2016 | 50% | It needs to revised the time upto April 2017 |
| Activity 7:Conduct studies on ecological studies seagrasses in selected areas | March 2018 | 40% |  |
| Activity 8: Collate information on impact of fishing gears on seagrass destruction and seagrass associated fisheries | March 2018 | 30% |  |
| Activity 9: Collate information on other associated habitats such as mangroves and coral reefs as these ecosystems are interrelated. | March 2018 | 30% | Apart from coral reefs and mangrove habitats , fishery associated with the seagrass habitat as may documented |
| Activity 10: studies on water quality in selected areas | March 2018 | 40% |  |
| Activity11: Survey on illegal activities in selected areas | March 2018 | 30% |  |
| Output 3.2: |  |  |  |
| Activity 2: |  |  |  |
| Activity 3: |  |  |  |
| Output 3: |  |  |  |
| Activity 4: |  |  |  |
| Activity 5: |  |  |  |
| Output 4: |  |  |  |
| Activity 6: |  |  |  |
| Activity 7: |  |  |  |

  - Risk and risk management

Please describe internal and external risks (examples included in brackets) that could affect successful implementation of project activities and the proposed risk mitigation measures.

| Risk group | Description | Risk level (Low/ Medium/ High) | Mitigation measures |
| --- | --- | --- | --- |
| Project Management (team capacity, internal communication, co-financing, budget, financial management, reporting, etc.) | none |  |  |
| Socio-cultural issues (external communications, capacity of and work with stakeholders, cultural aspects) | Communication problems, Limited access to some of the sea areas due to security reasons | Low | Get necessary approvals |
| Political risks (Political stability in country, political impacts on the project) |  |  |  |
| Environmental risks (severe weather events/ disasters, natural causes negatively affecting project areas, habitats and species) | Monsoonal periods , severe floods during May 2016 | High | Avoid unfavourable seasons when conducting monitoring and ecological studies on seagrasses |
| Other (please specify) | Could not stick with time frame regarding some activities , activity 6 | Low | Readjust the time frame and complete work |

- MONITORING AND EVALUATION

  - Please describe activities for monitoring and evaluation carried out during the reporting period.

Examples include: baseline data collection, stakeholder surveys, field surveys, steering committee meetings to assess project progress, peer review of documentation to ensure quality, mid-term review, etc.

Do not include routine project reporting.

Baseline maps, Baseline data collection, field surveys, meetings,

- OTHER INFORMATION

  - Meetings

| Meeting type | Title | Venue | Dates | Convened by | Organised by | No. of participants | Report issued Y/N | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.National facilitating committee meeting | Discuss about the mid term review | Wild Life Dept | 10.10.16 | Wild Life dept. | Project team | 8 | N | English/Sinhala |  |
| 2.Expert group meeting | Discuss about the project activities | NARA | 16.11.16 | NARA management | NARA Management | 3 | N | English/Sinhala |  |
| 3.National facilitating committee meeting | Discuss about the progress & logistics | Wild Life Dept | 16.11.16 | Wild Life dept. | Wild Life Dept, Sri Lanka | 5 | N | English |  |

  - List(s) of meeting participants

| No. | Name of participant | Nationality |
| --- | --- | --- |
| 1 | 1. Dr. Lakshman Peiris – Assistant Director (Research and Training) 2. Mr. Channa Suraweera, Dept of Wild Life 3. Dr. Vasantha Pahalawaththaarachchi - NARA 4. Mr. PrasannaWeerakkody – ORCA 5. Mr. Sajith Subashana - ORCA 6. Mr. Ranil Nanayakkara - BEAR 7. Mr. Arjan Rajasuriya – 8.Mr.Thushan Kapurusingha -TCP | Sri Lankan |
| 2 | Dr. Palitha Kithsiri. Actg. Director General, Deputy Director General, NARA, Mr.A.B.A.K. Gunarathna, Director Monitoring and Evaluation, NARA; Dr.V.Pahalawattaaarachchi , GEF project coordinator; Dr. G. Dassanayake (Scientist, NARA) | Sri Lankan |
| 3 | 1. Dr. Lakshman Peiris – Assistant Director (Research and Training) 2. Dr. Gihan Dahanayake - NARA 3. Mr. PrasannaWeerakkody – ORCA 4. Mr. Sajith Subashana - 5. Mr. Arjan Rajasuriya – IUCN | Sri Lankan |

  - Documents, other printed materials, videos, and soft products (such as CDs or websites)

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Printed material | Poster on Seagrasses in Sri Lanka | V.Pahalawattaarachchi |  |  | Ongoing |

| Name of Project Manager.V Pahalawattaarachchi | Name of Project Manager Supervisor: |
| --- | --- |
| Signature: | Date: 10.01.17 | Signature: | Date: |

  - Annex:    2.1 Narrative of project progress during the past semester by Project Activity

Activity 3, 4 and 5: Preparation of Seagrass distribution maps in spatial scalesbased on the basal map (map 1 &2), Ground truthing and monitoring, Continuous updating and validation of seagarass distribution maps by monitoring in temporal scale. Mannar, Palk Bay and Palk straight locations of study and GPS readings were obtained

Upgrading and    Seagrass distribution map preparation is going on. Satellite images were purchased for the areas with clear water (non turbid) and shallow water  and  GIS method is being using for  the mapping of deep and turbid areas  ground truthing done in the study locations of gulf of

Activity 6: Identification of important habitats to be study in details

Spatial distribution patterns are still studying. It is clear that the sea grasses Halophila, Halodule and Cymodocea were found in the areas of Vedithathivu. Hence it is suggested to study details in Vedithathivu area.

Activity 7: Conduct studies on ecological studies seagrasses in selected areas

Seagrass ecological studies in Vedithalthivu (80km2)and Mannar South Bar (110km2) were conducted in the latter half of the year. In the study seagrass samples were collected in randomly placed   25cmx25cm quadrates for biomass studies and by placing 50cmx50cm quadrate for estimating % cover. The location of 8Km away from the shore Vedithathivu reef is located and corals found to be dead due to bleaching.  Halophila ovalis (photo-V1; 21-24 locations in the map) and Cymodocea rotundata (Photo V2; 21-24 locations in the map) was observed in low dense and patchy distribution around the deeper areas around the coral reefs. Caulerpa taxifolia (Photo V3) was observed distributed around the reef area over the seagrasses which is recorded as invasive in some reports.

The other areas studies were South Bar Mannar in which some dugong deaths recorded within last days. Sampling method was random quadrate method as there was no continous seagrass patches observed. It also recorded much blast fishing using dynamite. Hence the area should be marked as sensitive areas to be protected. Seaweeds/macro algae spp such as Caulerpa racemose, Caulerpa sertularioides/ Caulerpha taxifolia (Photo S1; to be confirmed), Halimida spp, could be seen distributed around the coral reef. Cymodacea serrulata densely grown (Photo S2) area was observed with 100% seagrass coverage.  Halophila ovalis and Syringodium isoetifolium (S3) observed patchy distribution wit patches   2’x4’ to 40’x50’.Slimy filamentous green algae (S4) was dominant in the are close to the shore (more than 60 km2; belt of no 10 in the map). This area beyond 3 Km away from the shore limited to conduct “Madel” fishery which has no seagrasses found in the bottom.

It has been recorded that, there is a major decrease in all marine species and a decline in fish biomass in areas where C. taxifolia has become a serious problem. In our studies, we have observed similar phenomena, but need further studies to confirm. Stomach content analysis of stranded dugongs also conducted and paper is in preparation

Activity 8: Collate information on impact of fishing gears on seagrass destruction and seagrass associated fisheries

During the baseline survey two main sites were observed with high number of bottom and submerged gill net operations in the Mannar district namely,Vankalei and Urumalei. Fishermen in these two sites mainly target crabs (Blue swimming crab (Portunuspelagicus)) and other benthic and demersal fish species (Rays (Bandedeagle ray (Aetomylaeusnichofii),Mottled eagle ray (Aetomylaeusmaculatus) Spotted eagle ray (Aetobatusnarinari), Guitar fish, Mullet (Liza sp., Mugil sp.,Valamugil sp.), Asian Sea bass (Latescalcarifer), Snappers). Also, fishermen operate seasonal gears which target specific fish species groups abundant within the area (eg: Squid jigs operation during the Cuttle fish and Squid abundance time period, “Habereli Del”- gill net which is targeted Needle fish during the peak abundance seasons

Main three type of fishing gears operated on sea grass beds of the selected two districts and which are gill nets, trammel nets, Fyke nets and Squid jig. Among the gill nets three type of nets are used for the fishing (classified accordingly material) including nylone nets, mono-filamentous or thangus nets and Multi monofilament nets. Five types of fishing gears were operated for fishing including Trammel nets, Fyke nets, Squid jig,Nylone gill nets, Mono-filamentous gill nets or Thangus nets and Multi monofilament gill nets specially in Jaffna district and three type of fishing gears including Trammel nets, Nylone gill nets andMulti monofilament gill nets were recorded in Mannar district respectively.

Sea grass abundance of the used gears for fishing were determined according to entangled amount  of sea grasses with each gears wile clearing gears (nets) and categorized to  five criteria’s as very high, high, medium, low and none. Among the observed fishing gears very high amount of sea grasses recorded from both Jaffna and Mannar districts for multi monofilament gill nets respectively. High sea grass amount also recorded from monofilament (Thangus)Gill netswhich were operated at Jaffna district. There are no feasibility to entangling sea grasses for  squid jig   gears which were operated at Jaffna district. The percentage of  sea grass abundance of selected sites of Jaffna and Mannar districts  with operated gears and rankings are illustrated as follows.

Activity 9: Collate information on other associated habitats such as mangroves and coral reefs as these ecosystems are interrelated.

Two coral reefs observed Vedithathivu and South Bar is damaged due to blast fishing. Corals in Vedithathivu found to be dead and covered with sediments. Seagrass area in Vedithalthivu was associated with a mangrove area while mangroves are not available at South Bar area, Mannar.

Activity 10: studies on water quality   in selected areas

Water quality analysis was conducted parallel to the ecological studies. Water salinity was around 33ppt and the water pH was around 8. Water turbidity was generally low and ranged from 0.77 NTU to 3.08 NTU.

Water salinity of the South Bar area was around 32ppt and the water is very clear or less turbid, 6-10m deep getting sufficient illumination to bottom plant photosynthesis

Activity11: Survey on illegal activities in selected areas

Most dangerous activity so far identified is blast fishing; it is very common in Mannar area (South Bar). Information were collected from the fisherman.

Dugong dugon observations in the north-western waters of Sri Lanka

According to the fishermen interviewed (40 fishermen), two fishermen have not observed Dugong for more than 10 years and one fishermen for more than 15 years. Also one fishermen observed around 2000 kg large Dugong before one year offshore area of Wankalei and another fishermen observed 300 kg one before 3 years within the Mannar area.

# Footnotes

Information provided in “Quarterly Expenditure Report” should be in line with output/activity progress reported in this table.

Outputs and activities as described in the project proposal or in any updated project revision. Expand table as necessary.

Expand table as necessary

Meeting types: e.g. expert group meeting, project inception workshop, training workshop/seminar, partners consultation workshop, project Steering Committee meeting etc.

Expand table as necessary

Documents and printed material types: e.g. technical publication, meeting report, technical/substantive report, brochures, media releases, etc.