The GEF Dugong and Seagrass Conservation Project

Project Progress Report

| Reporting Period | From: | July 2016 | To: | December 2016 |
| --- | --- | --- | --- | --- |

- PROJECT GENERAL INFORMATION

| National Project Code & Title: | LK 8 – 2134 National Facilitating Committee For GEF Dugong and Seagrass Conservation Project |
| --- | --- |

| Project Partner(s): | IUCN |
| --- | --- |

| Location (country, region/ district and commune/ city/ village/ region etc.) | Sri Lanka |
| --- | --- |
| Of which areas under protection (please indicate the name and size of protected areas or locally managed marine areas, if applicable) | Bar Reef Marine Sanctuary Wilpattu National Park Wankalai Sanctuary Adam’s Bridge Marine National Park |

| Project start date | June 2015 | Project intended completion date | September 2018 |
| --- | --- | --- | --- |

- PROJECT PROGRESS

  - Narrative of project progress during the past semester by Project Activity

National Facilitating Committee met 3 times to discuss project progresses and constrain. Discussed strategic approach to achieve project objectives. NF Participated to the EPSC meeting held in Malaysia. Training need assessment completed. National level awareness workshops were held in Puttalam, Jaffna, Killinochchi and Mannar Districts. Partners have been communicated on MTR and a programme for MTR is scheduled.

  - Project implementation progress

| Outputs & Activities | Expected completion date | Implementation status as of end of reporting period expressed in % | Describe any problems in delivery and any changes/mitigation action required. |
| --- | --- | --- | --- |
| Output 4.1 |  |  |  |
| Activity 1: Conduct policy reviews relevant to the conservation of dugongs, seagrasses, other sensitive ecosystems and the enviromment. Identify gaps and make recommendations | 30 Sep 2016 | 20% |  |
| Activity 2: Conduct a training needs assessment of national level capacity in monitoring and conservation of dugongs and seagrass ecosystems | 30 Apr 2016 | 100% |  |
| Activity 3: Based on activity 2 Conduct a training of trainees for government officials in relevant agencies and participants selected from the Community Conservation Groups | 30 Dec 2016 | 20% |  |
| Output 2: |  |  |  |
| Activity 1: Promote the conservation of dugongs and seagrass ecosystems among government organizations at national, regional and local levels and other stakeholders including private sector for CSR activities | Continue | 30% | National steering committee meetings and National level awareness |
| Activity 2: Preparation of strategic plan for the implementation of the dugong and seagrass conservation project | 30 Oct 2016 | 100% |  |
| Activity 3: Conduct regular NFC meetings every 3 months | 30 Dec 2016 | 100% |  |

  - Risk and risk management

Please describe internal and external risks (examples included in brackets) that could affect successful implementation of project activities and the proposed risk mitigation measures.

| Risk group | Description | Risk level (Low/ Medium/ High) | Mitigation measures |
| --- | --- | --- | --- |
| Project Management (team capacity, internal communication, co-financing, budget, financial management, reporting, etc.) | Integrated approach to achieve national project goals | Low | Regular meetings and discussions |
| Socio-cultural issues (external communications, capacity of and work with stakeholders, cultural aspects) | Communication to the different cultural groups | Low | Communicate through local community leaders |
| Political risks (Political stability in country, political impacts on the project) | Non |  |  |
| Environmental risks (severe weather events/ disasters, natural causes negatively affecting project areas, habitats and species) | Non |  |  |
| Other (please specify) |  |  |  |

- MONITORING AND EVALUATION

  - Please describe activities for monitoring and evaluation carried out during the reporting period.

Examples include: baseline data collection, stakeholder surveys, field surveys, steering committee meetings to assess project progress, peer review of documentation to ensure quality, mid-term review, etc.

Do not include routine project reporting.

Progress has been monitored and discussed in regularly at the national facilitating committee meetings

- OTHER INFORMATION

  - Meetings

| Meeting type | Title | Venue | Dates | Convened by | Organised by | No. of participants | Report issued Y/N | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Steering Committee | National Facilitating Committee | IUCN | 1-07-16 | IUCN | NF | 11 | Y | English |  |
|  | National Facilitating committee | DWC | 10-10-16 | Marine unit | Marine unit | 06 | Y | English |  |
|  | National Facilitating committee | DWC | 16-11-16 | Marine unit | Marine unit | 07 | Y | English |  |

  - List(s) of meeting participants

| No. | Name of participant | Nationality |
| --- | --- | --- |
|  | Dr. U.K.L. Peiris (National Facilitator) Mr. Thushan Kapurusinghe Mr. Tharanga Herath Mr. Prasanna Weerakkody Mr. H.M.D. Sajith Subashana Dr. V. Pahalawattaarachchi Dr. D.D.G.L. Dahanayaka Mr. Arjan Rajasuriya Ms. Shana Ranasinghe Ms. Matheesha Katuwawala Ms. Harini Nishshanka | Sri Lankan |
|  | Dr. U.K.L.Peiris Mr.Channa Suraweera Mr.Arjan Rajasuriya Mr. Prasanna Weerakkody Mr. H.M.D. Sajith Subhasinghe Mr. Thushan Kapurusinghe | Sri Lankan |
|  | Dr. U.K.L.Peiris Mr.Channa Suraweera Mr.Arjan Rajasuriya Mr. Prasanna Weerakkody Mr. H.M.D. Sajith Subhasinghe Mr. D.D.G.L.Dahanayake Mr. Asanka Gunawardana | Sri Lankan |

  - Documents, other printed materials, videos, and soft products (such as CDs or websites)

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Report | Monthly reports July to Dec 2016 | U.K.L.Peiris |  |  |  |
| 2 | Report | National facilitating Committee meeting | U.K.L.Peiris |  |  |  |
| 3 | Report | National Level Awareness | U.K.L.Peiris |  |  |  |
| 4 | Report | National Steering Committee | U.K.L.Peiris |  |  |  |
| 5 | Report | Training Need Assessment | U.K.L.Peiris |  |  |  |

| Name of Project Manager: | Name of Project Manager Supervisor: U.K.L.Peiris |
| --- | --- |
| Signature: | Date: | Signature: | Date: 09/01/2017 |

# Footnotes

Briefly describe progress made during the previous six months highlighting major outcomes/benchmarks achieved during the period.

Information provided in “Quarterly Expenditure Report” should be in line with output/activity progress reported in this table.

Outputs and activities as described in the project proposal or in any updated project revision. Expand table as necessary.

Expand table as necessary

Meeting types: e.g. expert group meeting, project inception workshop, training workshop/seminar, partners consultation workshop, project Steering Committee meeting etc.

Expand table as necessary

Documents and printed material types: e.g. technical publication, meeting report, technical/substantive report, brochures, media releases, etc.