The GEF Dugong and Seagrass Conservation Project

Project Progress Report

| Reporting Period | From: | July 2016 | To: | December 2016 |
| --- | --- | --- | --- | --- |

- PROJECT GENERAL INFORMATION

| National Project Code & Title: | MG3-2107 : Using incentivized Environmental Stewardship to conserve dugongs and seagrass habitat at an identified national hotspot |
| --- | --- |

| Project Partner(s): | Madagascar National Parks Nosy Hara, Direction Générale de l’Environnement Ministère de l’Environnement ,Ecologie,Mer et des Forets, Woman Association FIVEPANOHA (have listed top 3, there are many more as detailed in proposal) |
| --- | --- |

| Location (country, region/ district and commune/ city/ village/ region etc.) | Nosy Hara Marine Park, Diana region, northern Madagascar |
| --- | --- |
| Of which areas under protection (please indicate the name and size of protected areas or locally managed marine areas, if applicable) | Nosy Hara Marine Park 1831km² |

| Project start date | 1 September 2015 | Project intended completion date | 30 September 2018 |
| --- | --- | --- | --- |

- PROJECT PROGRESS

  - Narrative of project progress during the past semester by Project Activity

Given the slow start in the last quarter of 2015 the team have been incredibly busy in 2016 and already seen many successes in achieving their aims. In terms of governance structures the Local Park Management (CLP) committee is made up of representatives from each of the 21 communities across Nosy Hara Marine Park; some being very remote and difficult and expensive to access. Madagascar National Parks (MNP), which is responsible for convening the CLP meetings on a quarterly basis, has in the past been unable to convene all representatives at MNP's Park office in Ampasindava, meaning remote communities were omitted from planning and monitoring activities. C3 proposed division of the Park into 3 sub-regions and the separate assembly of communities in each of those areas at quarterly meetings. C3 then acts as a conduit of information between all communities and the Park authority and everyone has a say as well as more active involvement in Park management issues. We have a total of 20 active and committed CLP representatives (village presidents) and within those communities a further 326 community members attend these management meetings on a regular basis. Meetings have been held monthly in order to coordinate collection of data on illegal fisheries and dugong sightings. The update of the traditional dina on marine and coastal resource use has proven a complex affair and requires assistance from the MIHARI network as it needs expert legal advice to ensure this is done effectively and implemented effectively given the co-management of the Park both by national authorities and communities. Previous attempts by other NGOs and MNP have not yielded any progress on the issue so in June 2016 C3 signed a collaborative agreement with MIHARI to bring in their personnel to objectively assist in this component of our given their proven track record in other regions of Madagascar. Unfortunately MIHARI were unable to assist C3 in starting this activity but they have assured us they will start working on this from January 2017. They have signed an agreement to use our office space in Diego to facilitate attainment of this objective in a timely manner. C3 in completion of its responsibilities under the ToR shared promotional materials with MIHARI and sent staff and Junior Ecoguards to assist them with outreach events in Nosy Hara Marine Park and Sahamalaza. Our Programme Coordinator also volunteered her time to assist MIHARI in recruitment of personnel to coordination their dugong and seagrass outreach. Staff trained by C3 also ran a staff training session on dugong ecology and conservation for MIHARI in Antananarivo in November 2016. MIHARI will be using sections of the Junior Ecoguard Manual and Toolkit relating to dugongs and seagrass for their outreach in other communities. Our 40 Conservation Ambassadors from 21 communities have continued to be involved in monthly conservation activities including dugong incidental sighting reporting, illegal fisheries reporting, community outreach events, seagrass monitoring, CLP meetings and assistance with our incentives schemes (livelihoods, health and schools programmes). More Junior Ecoguards are to be recruited in the remote community of Andranofanjava. We have been waiting until the end of the wet season to coordinate this with community leaders. We're excited to announce that our Junior Ecoguard programme has expanded to a further 20 schools in the Diana region and delivery of toolkits has been completed in communities across northern Madagascar. We have received partial funding towards expanding the programme to 3 new provinces, expanding our reach even further in 2017. Support remains very strong from the Ministry of Education and their relevant offices in the region. The Toolkits have been produced in a sustainable manner with all materials sourced in Madagascar to ensure constant resupply easily and economically as required. We're happy to have had a total of 21 live dugongs reported since the project inception from 9 different locations and zero dugong mortalities, with most sightings from the north and west parts of the Park. Two of the sightings included a mother and calf pair and there was also one group of four dugongs spotted. We may have discovered a clear hotspot where dugongs are being seen on a very regular basis and our team is now engaging with the relevant fishers to spend time researching this area in more detail. Our incentives programme is running well with monthly fisheries monitoring being conducted at the three primary landing sites across the Park by 6 trained CAs. Interesting findings of rare or data-deficient species included Tawny nurse sharks, Grey Reef sharks, Honeycomb Stingrays and Grey Spotted Guitarfish. Reporting from our CAs has shown that no turtle poaching or harm to other marine megafauna has been observed but there have been accounts of some illegal fishing gear (e.g spear guns) being used. Annual seagrass monitoring was conducted at 4 sites as planned: Lalandaka, Vahilava, Ironono and Agnahibe. More marketing materials were produced for the womens ecotourism restaurant and tour companies in Diego are regularly bringing clients to eat there when visiting the Park. Unfortunately in September disaster struck the poultry farm with disease killing the chickens one-by-one until only 6 remained. Consultations have been made with agricultural specialists and the community about remedial actions. Recommendations included improvements in the housing and also additional vaccines. We are awaiting end of the wet season to take action in improving or relocation of the farm. Following the feasibility studies for new livelihoods, a goat farm was planned in Lalandaka (a dugong hotspot) and a duck farm in Andranomavo. In November training was carried out in enterprise management with CLPs an integral part of this process. The community of Andranomavo is currently constructing the housing for the duck farm as part of our collaborative agreement with them. We are awaiting completion before delivery of stock. Rather belatedly, following our feasibility study, MNP informed us of a fady for some community members in Lalandaka with regards to goat rearing which could compromise the enterprise’s success at that locality. We are therefore considering a second duck farm at the site but will need to conduct community meetings in early 2017 to introduce this alternative option. Monthly visits of a general practitioner and midwife began in June under formal collaboration with the Ministry of Health. Previously a monthly midwife visit was provided, based on community needs but later those same communities expressed desire for a visiting doctor who could assess and treat all community members. Uptake has been good with common problems such as gastro-intestinal illness, ear and genital infections, intestinal parasites, hypertension, routine pregnancy check-ups and febrile illnesses being treated. Construction of a desperately-needed new well to provide drinking water for the community in Ampasindava was completed in August 2016. Meetings with CISCO revealed the need for Maths, French, SVT and Malagasy books for classrooms and we are currently finalising a list and quotations. Books and furniture will be delivered to schools in January. A promotional film on our work in Nosy Hara Marine Park has been completed and will be disseminated in from January 2017. Cross-pollination of ideas from our highly successful community dugong conservation programme in the Philippines took place in September 2016 as well as staff capacity building, an internal audit and development of a Strategic Action Plan for 2016 – 2020. This helps lay out the roadmap for C3’s continued support to communities and endangered marine biodiversity in northern Madagascar. Since November 2016 implementation of our SAP began with a restructuring of our northern field office was to ensure greater efficiency in delivery of our programmes. Four major outreach events have taken place in Ampasindava village (awareness day with MIHARI network), Antananarivo (4 days outreach on fishery and aquaculture), Ambodirafia of Nosy Radama (Dugong Festival) and in Ankingameloka village. The Junior Ecoguards were a key focus at all these events, conducting their lively performances about dugongs, seagrasses, mangroves octopus and shark). We've teamed up with the famed clothes company of the Indian Ocean islands, 'Baobab clothing', to produce fundraising dugong t-shirts and informative posters for their shops across Madagascar, with a proportion of profits going to C3's dugong conservation work. We hope to distribute these products through the GEF Project’s online store soon.

  - Project implementation progress

| Outputs & Activities | Expected completion date | Implementation status as of end of reporting period expressed in % | Describe any problems in delivery and any changes/mitigation action required. |
| --- | --- | --- | --- |
| Output 1.1: Governance structures for community involvement in conservation and monitoring of dugong and seagrass ecosystems established or strengthened in target areas |  |  |  |
| Activity 1.1.1: Local Park Management committee meets monthly | September 2015 | 100% | In the first quarter we reviewed the system, it wasn't possible for all members of the CLP to meet monthly given the vast and remote areas we are dealing with. We then split into sub-regions and started a new more practical means of bringing members together; this is now in effect |
| Activity 1.1.2 Traditional 'dina' printed and discussed with all community leaders | March 2016 | 20% | We called upon the expertise of MIHARI in assisting with this and signed a formal working agreement in June 2016. They have been unable to allocate time to this so far but have promised to get started in January 2017 |
| Activity 1.1.3 Public awareness of the dina through outreach events | April 2016 | 0% | See above, will take place after 1.1.2 |
| Activity 1.1.4 Training of Conservation Ambassadors in implementing dina in their communities | April 2016 | 0% | As above |
| Output 1.2: Capacity developed for community-based stewardship (conservation and monitoring of dugongs & seagrass) |  |  |  |
| Activity 1.2.1: Training of Conservation Ambassadors & MNP rangers in incidental sighting report system | September 2015 | 100% | Everyone trained, but had to do it in regions given long distances between the communities and inaccessibility of some (access by sea only!) |
| Activity 1.2.2: Update database on dugong locations | September 2015 | 100% | This is fully functioning, with a review of the system completed in March 2016 |
| Activity 1.2.3 Seagrass watch monitoring at 4 key dugong sites | September 2015 | 100% | This was completed after the wet season due to weather constraints making fieldwork (and travel) hazardous |
| Activity 1.2.4 Recruitment & training of 20 new Conservation Ambassadors from across the park | October 2015 | 100% | As with recruitment in 1.2.1 this had to be done in various stages due to remoteness |
| Activity 1.2.5 : Recruitment & training of 30 new Junior Ecoguards from across the park | October 2015 | 100% | Since writing the proposal, some existing Junior Ecoguards had left their villages for work or further studies and also needed replacement in addition to the new recruits |
| Output 2.1: Management and incentive mechanisms and tools for sustainable fisheries – pilots and capacity building (local community and government) |  |  |  |
| Activity 2.1.1: Implementation of an illegal fisheries reporting system with incentive system | January 2016 | 100% | NA |
| Activity 2.1.2: Consultations with fishers about 2 new livelihood enterprises | April 2016 | 100% | NA |
| Activity 2.1.3 : Business plans written for 2 livelihood enterprises | May 2016 | 80% | Change of plan in one livelihood from goats to ducks (see above) and awaiting community completion of duck housing before delivery of stock in early 2016. |
| Activity 2.1.4 : Launch of 2 enterprises and monitoring | June 2016 | 0% | See point above |
| 2.1.5 : Planning & delivery of doctor's mobile clinic | January 2016 | 100% |  |
| 2.1.6 : Furniture and books procured | July 2016 | 100% | Completed with more books and furniture to distribute in January 2016 |
| Output 2.2: Awareness raising and social marketing programmes contributing to more sustainable practices (subsistence and small-scale artisanal fishers) in target areas |  |  |  |
| Activity 2.2.1: Evaluation of records on community infractions and conservation activities | January 2016 | 100% | Completed each quarter from January. |
| Output 3.1 : Critical knowledge gaps (dugongs and seagrass ecosystems) identified and surveys initiated/ completed |  |  |  |
| Activity 3.1.1 : Analysis of seagrass data from Park | July 2016 | 0% | Last monitoring in November 2016 so analysis pending |
| 3.1.2 : Analysis of dugong sighting data from Park | October 2016 | 100% | Completed end of the year |
| 3.1.3: Key informant intervierws with fishers | November 2016 | 0% | Has been postponed to April 2017, this will time with some bycatch surveys for another donor which will overlap a couple of sites and avoid duplication of effort and ensure fishers are only interviewed once. Also post-wet seasons sites will be more accessible for the team. |
| 3.1.4 : Preparation of status report on dugongs of Nosy Hara | April 2017 | 0% | This will be delayed due to data gathering in April 2017. |
| Output 3.3 : Conservation-relevant information and guidance (dugongs and seagrass ecosystems) collated and disseminated |  |  |  |
| 3.3.1 : Gathering footage for film on dugong & seagrass conservation in Malagasy communities | November 2016 | 100% | NA |
| 3.3.2 Editing film and adding narration | March 2017 | 100% | NA |
| 3.3.3 Final film produced | August 2017 | 0% |  |
| 3.3.4 Dissemination of film & status report | December 2017 | 0% | Due early in January 2017 |
| Output 4.2 Advocacy programmes and advocacy capacity for improved conservation management of dugongs and their seagrass ecosystems developed and implemented |  |  |  |
| 4.2.1 Annual plan for Junior Ecoguards outreach events | January 2016 | 100% | NA |
| 4.2.2 Outreach events (theatre, film, debate & coastal field trips) in each village of the Park | October 2015 | 100% | NA |

  - Risk and risk management

Please describe internal and external risks (examples included in brackets) that could affect successful implementation of project activities and the proposed risk mitigation measures.

| Risk group | Description | Risk level (Low/ Medium/ High) | Mitigation measures |
| --- | --- | --- | --- |
| Project Management (team capacity, internal communication, co-financing, budget, financial management, reporting, etc.) | In a small team staff are stretched in terms of time to commit to all their responsibilities and may not be prioritising effectively Cash flow is sometimes an issue when funds have to be transferred from the UK to Madagascar, delays have been incurred due to the bank Financial security is an issue for a small NGO | Medium | 1.) An external evaluation conducted in September 2016 has helped define our strategic directions and institutional capacity needs for 2016 – 2020 2) We have requested 6 months budget in advance from GEF and our bank has assured us that transfer delay issues will be addressed. 3) a financial sustainability plan is part of the SAP and is being implemented by staff at our head office in Tana |
| Socio-cultural issues (external communications, capacity of and work with stakeholders, cultural aspects) | Spread of our outreach materials across Madagascar means they must be translated from the local dialect into other regional dialects as required Promotional film is a great way to spread awareness of C3 across a wider area including other provinces in the north | Medium | MIHARI network to fund the required translation and dissemination of outreach tools we have developed The film is in Malagasy with English subtitles as the primary aim is to reach local populations |
| Political risks (Political stability in country, political impacts on the project) | Changeover of Ministry staff after resignation of Prime Minister in April 2016 Beboarimisa Ralava appointed the new Minister of the Environment, Ecology, Sea and Forestry | High | Despite challenges of working with government we maintain good relations and are pivotal in providing guidance and information in marine biodiversity conservation. Our staff are always included in relevant meetings, workshops and committees. |
| Environmental risks (severe weather events/ disasters, natural causes negatively affecting project areas, habitats and species) | Cyclone and torrential rains in northern Madagascar | High | 1) For the safety of our staff and community volunteers many field activities are postponed until end of the wet season |
| Other (please specify) | Lack of coordination with other partners at the national level & low awareness of what other projects are doing | High | Our staff have spent a lot of time voluntarily assisting the MIHARI network with various administrative, technical, outreach and planning activities as part of our TOR. From January 2017 MIHARI will be reciprocating by delivery of the dina component of our project. They have also been offered office space in Diego which they will take up from January 2016. |

- MONITORING AND EVALUATION

  - Please describe activities for monitoring and evaluation carried out during the reporting period.

Examples include: baseline data collection, stakeholder surveys, field surveys, steering committee meetings to assess project progress, peer review of documentation to ensure quality, mid-term review, etc.

Do not include routine project reporting.

Monitoring and evaluation was conducted monthly by visits to the communities to assess : -livelihood enterprises balance sheets and stock as well as any problems/concerns -dugong sightings collected by CLP members and CAs - any illegal activities observed in the Park -fisheries data from landing site monitoring Review of the programme’s overall institutional capacity, financial management systems and drafting of a strategic action plan took place in September 2016 by an external staff member from the C3 network.

- OTHER INFORMATION

  - Meetings

| Meeting type | Title | Venue | Dates | Convened by | Organised by | No. of participants | Report issued Y/N | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Community Park Management representatives meeting | Monthly meeting with CLP in Lalandaka | Lalandaka | 26th july 2016 | C3 | RANDRIANJAFIMANANA Nambinintsoa Tahiry, Senior Programme Officer RALAIFANASINA Andrianady Tahina, Programme Officer Database | 07 | Y | Malagasy |  |
| Community Park Management representatives meeting | Monthly meeting with CLP in Anjiamaloto | Anjiamaloto | 23rd August 2016 | C3 | RALAIFANASINA Andrianady Tahina, Programme Officer | 01 | Y | Malagasy |  |
| Community Park Management representatives meeting | Monthly meeting with CLP in Ampasindava | Ampasindava | 23rd November | C3 | Lalarisoa Rakotoarimino, PC, Mihary Ramiandrisoa, SPO, Anwar Salimo, PO Anatoli Velondia, PO | 09 | Y | Malagasy |  |
| Community Park Management representatives meeting | Community consultation about goat farm in Lalandaka/ CLP meeting | Lalandaka | 25th November | C3 | Anwar Salimo, PO Anatoli Velondia, PO | 13 | Y | Malagasy |  |
| Community Park Management representatives meeting |  |  |  | C3 |  |  |  |  |  |
| Community Park Management representatives meeting | Monthly meeting with CLP in Andranomavo | Andranomavo | 17th December 2016 | C3 | Mihary Ramiandrisoa, SPO Patrice, Student | 09 | Y | Malagasy |  |
| Community consultation | FIVEPANOHA Consultation about poultry farm and restaurant | Ampasindava | 23rd November | C3 | Lalarisoa Rakotoarimino, PC, Mihary Ramiandrisoa, SPO,Anwar Salimo, PO Anatoli Velondia, PO | 14 | Y | Malagasy |  |
| Internal planning meeting | C3 staff quarterly meeting on GEF plans | C3 Diego field office |  | C3 | Lalarisoa Rakotoarimino, PC | 4 | Y | Malagasy |  |
| NGO GEF partner meeting |  | SEMER office Antananarivo |  |  |  |  | Y |  |  |
| COSAP meeting |  |  |  | COSAP |  | 1 | Y |  |  |

  - List(s) of meeting participants

| No. | Name of participant | Nationality |
| --- | --- | --- |
|  | RANDRIANJAFIMANANA Nambinintsoa Tahiry, Senior Programme Officer RALAIFANASINA Andrianady Tahina, Programme Officer Database JAOZANDRY, CLP President BERAVO, CLP Eloah Joseph, Conservation Ambassador Moussa Bakar, Conservation Ambassador VOASAOTRA André, Conservation Ambassador JAOTIANA DAMA Passo, Conservation Ambassador BEANJARA, Conservation Ambassador | Malagasy |
|  | RALAIFANASINA Andrianady Tahina, Programme Officer JACQUI Adama, Conservation Ambassador | Malagasy |
|  | Lalarisoa Rakotoarimino, PC Mihary Ramiandrisoa, SPO Anwar Salimo, PO Anatoli Velondia, PO Women from FIVEPANOHA | Malagasy |
|  | Lalarisoa Rakotoarimino, PC Mihary Ramiandrisoa, SPO Anwar Salimo, PO Anatoli Velondia, PO CLP members from Andranomavo: Zaramasy & Rajoel Manjaka Hova CLP from Akingameloka: Mahatoly be & Randria CLP from Bobatolagna: Memena & Pierre Felicien CLP from Ampasindava: Charlie Rakotonirina, Fatoma Therese & Samy William | Malagasy |
|  | Anwar Salimo, PO Anatoli Velondia, PO 13 CLP President of the Lalandaka village | Malagasy |
|  | Mihary Ramiandrisoa, SPO Patrice, Student CLPs from Andranomavo : Razafy Rajoel; Beanjara Jean; Damo, Zaramasy; Tombohasy, 0341627403 CLPs of Ambararata : Betombo Tomboanjara Aymar, 0349761887 Marcel Mila Fasimila Be Peter | Malagasy |

  - Documents, other printed materials, videos, and soft products (such as CDs or websites)

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Film | C3 community outreach film |  | C3 |  | November 2016 |
| 2 | Postcard | Dugong postcard |  | C3 |  | July 2017 |
| 3 | Brochure | Womens ecotourism restaurant promotional brochure |  | C3 |  | August 2016 |
| 4 | Report | Feasibility report and business plan for two livelihood |  | C3 |  | August 2016, reviewed November 2016 |
| 5 | System | Fisher identification and registration system |  | C3 |  | July 2016 |
| 6 | Press release | http://latribune.cyber-diego.com/societe/2097-ong-c3-prendre-en-main-la-protection-de-l-environnement.html |  | La Tribune de Diego |  | 9th August 2016 |
| 7 | Press release | http://us9.campaign-archive2.com/?u=4a97b0ee2d7c527ef4fe39cee&id=bd39123011 |  | PHE network newsletter |  | September 2016 |
| 8 | Press release | http://www.newsmada.com/2016/12/05/dugong-nosy-hara-suivi-continu-de-la-population/ |  | News Mada |  | 05 December 2016 |

| Name of Project Manager: Lalarisoa Rakotoarimino | Name of Project Manager Supervisor: Patricia Z. R Davis |
| --- | --- |
|  | Date:8 July 2016 | Signature: | Date: 10 January 2017 |

# Footnotes

Briefly describe progress made during the previous six months highlighting major outcomes/benchmarks achieved during the period.

Information provided in “Quarterly Expenditure Report” should be in line with output/activity progress reported in this table.

Outputs and activities as described in the project proposal or in any updated project revision. Expand table as necessary.

Expand table as necessary

Meeting types: e.g. expert group meeting, project inception workshop, training workshop/seminar, partners consultation workshop, project Steering Committee meeting etc.

Expand table as necessary

Documents and printed material types: e.g. technical publication, meeting report, technical/substantive report, brochures, media releases, etc.