The GEF Dugong and Seagrass Conservation Project

Project Progress Report

| Reporting Period | From: | July 2016 | To: December 2016 |  |
| --- | --- | --- | --- | --- |

- PROJECT GENERAL INFORMATION

| National Project Code & Title: | MY2 Establishment of National Facilitating Committee and Technical Working Group for Conserving Dugongs and Their Habitats Through Involvement of Various Stakeholders |
| --- | --- |

| Project Partner(s): | SYED ABDULLAH BIN SYED ABDUL KADIR TURTLE AND MARINE RESEACH CENTER, DEPARTMENT OF FISHERIES MALAYSIA |
| --- | --- |

| Location (country, region/ district and commune/ city/ village/ region etc.) | Country: Malaysia District: Kuala Lumpur, Johor Bahru, Mersing, |
| --- | --- |
| Of which areas under protection (please indicate the name and size of protected areas or locally managed marine areas, if applicable) |  |

| Project start date | October 2016 | Project intended completion date |  |
| --- | --- | --- | --- |

- PROJECT PROGRESS

  - Narrative of project progress during the past semester by Project Activity

From July to December 2016 four meetings had successful be conducted. These meetings are (i) Meeting For Coordinating the Project Activities of MY1, MY3 and MY4 on 4 October 2016, Putrajaya, (ii) Second Meeting on National Facilitating Team 25 October 2016, Johor Bahru and (iii) Meeting to Review the Progress of Malaysia Project Dugong GEF 5 With Project Coordinator Team (PCT) on 31 October 2016, Kuala Lumpir and (iv) Organise Discussion With Local Communities at Sibu and Tinggi Islands together with the PCT on 3 -5 November 2016.

  - Project implementation progress

| Outputs & Activities | Expected completion date | Implementation status as of end of reporting period expressed in % | Describe any problems in delivery and any changes/mitigation action required. |
| --- | --- | --- | --- |
| Output 4.1 Policy, planning and regulatory gaps reviewed (conservation of dugongs and seagrass ecosystems) and recommendations developed |  |  |  |
| Activity 1: Second Meeting on National Facilitating Team 25 October 2016, Johor Bahru Second Meeting on National Facilitating Team, 25 October 2016, Johor Bahru | April 2018 | 25 % | No problem on establishment of the National Facilitating Team. The cooperation among the project partners very is excellent |
| Activity 2: Organise Discussion With Local Communities at Sibu and Tinggi Islands together with the PCT on 3 – 5 November 2016, | April 2018 | 25 % | Very good response from the local stakeholders to work together for conserving dugong and their habitats |
| Avtivity 3: Meeting For Coordinating the Project Activities of MY1, MY3 and MY4 on 4 October 2016, Putrajaya |  |  | MY2 Project Partner are responsible to facilitate the meeting. This is an extra schedule of MY2 Project activiites. This is an extra schedule to make sure that the project activities of MY1 , MY 2 and MY3 are well collaborate since some of the activities are overlapped |
| Activity 4: Meeting to Review the Progress of Malaysia Project Dugong GEF 5 With Project Coordinator Team (PCT) on 31 October 2016, Kuala Lumpur |  |  | This in an extra schedule pf MY2 Project activities to take the opportunity on the present of PCT in Malaysia during 2 EPSC Meeting in Malaysia The meeting was organised with present of PCT in order to provide technical advices on the implementation of project activities in Malaysia |
| Output 2: |  |  |  |
| Activity 2: |  |  |  |
| Activity 3: |  |  |  |
| Output 3: |  |  |  |
| Activity 4: |  |  |  |
| Activity 5: |  |  |  |
| Output 4: |  |  |  |
| Activity 6: |  |  |  |
| Activity 7: |  |  |  |

  - Risk and risk management

Please describe internal and external risks (examples included in brackets) that could affect successful implementation of project activities and the proposed risk mitigation measures.

| Risk group | Description | Risk level (Low/ Medium/ High) | Mitigation measures |
| --- | --- | --- | --- |
| Project Management (team capacity, internal communication, co-financing, budget, financial management, reporting, etc.) | The project activities started quite late due to the administration obstacle for signing the Funding Agreement | Medium | The Funding Agreement had already signed and now the project running smoothly |
| Socio-cultural issues (external communications, capacity of and work with stakeholders, cultural aspects) | Active participation from local state holders for establishment the Technical Working Group at Sibu/Tinggi Islands and Lawas is still low. | Medium | Regular dialogs and consultations will local stake holders will be conducted |
| Political risks (Political stability in country, political impacts on the project) | Need fully support from the Local Politician Leadar on establishment of Technical Working Group at Sibu/Tinggi Island and Lawas | Medium | Continuously meeting, discuss and convince the local Politician Leader will be carried out. |
| Environmental risks (severe weather events/ disasters, natural causes negatively affecting project areas, habitats and species) | No risk for MY2 Project |  |  |
| Other (please specify) |  |  |  |

- MONITORING AND EVALUATION

  - Please describe activities for monitoring and evaluation carried out during the reporting period.

Examples include: baseline data collection, stakeholder surveys, field surveys, steering committee meetings to assess project progress, peer review of documentation to ensure quality, mid-term review, etc.

Do not include routine project reporting.

Conducted Second Meeting on National Facilitating Team 25 October 2016, Johor Bahru and conducted the Meeting to Review the Progress of Malaysia Project Dugong GEF 5 With Project Coordinator Team (PCT) on 31 October 2016, Kuala Lumpir

- OTHER INFORMATION

  - Meetings

| Meeting type | Title | Venue | Dates | Convened by | Organised by | No. of participants | Report issued Y/N | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coordinating Project Activities | 1 Meeting For Coordinating the Project Activities of MY1, MY3 and MY4 on 4 October 2016, Putrajaya | Putrajaya | 4 October 2016 | National Focal Point | National Focal Point | 12 | yes | Malay | 10 October 2016 |
| National Facilitating Team | 2. Second Meeting on National Facilitating Team 25 October 2016, Johor Bahru | Johor Bahru | 25 October 2016 | National Focal Point | National Focal Point | 9 | yes | Malay | 7 November 2016 |
| Review Project Progress | 3. Meeting to Review the Progress of Malaysia Project Dugong GEF 5 With Project Coordinator Team (PCT) on 31 October 2016, Kuala Lumpur | Kuala Lumpur | 31 October 2016 | National Focal Point | PCT | 10 | No (But every Project Partner take note on the advised and suggestion given by PCT) |  |  |
| Stake holder Consultation | 4. Organise Discussion With Local Communities at Sibu and Tinggi Islands together with the PCT on 3 & 4 November 2016. | Sibu Island & Tinggi Island | 3 – 5 November 2016 | National Focal Point | National Focal Point | ‘ 14 | No (But every Project Partner take note on the advised and suggestion given by PCT) |  |  |

  - List(s) of meeting participants

| No. | Name of participant | Nationality |
| --- | --- | --- |
| 1 | Syed Abdullah, Mohd Tamimi, Dr Louisa Ponampalan, Dr Leela Rajamani, Julian Hyde, Edmund Lau, Abu Muntalib, Izarenah Md Repin, Dr Nicolas Picher, Mohd Noor, Hemalatha, Fairuz Izmal | Malaysia |
| 2 | Syed Abdullah, Dr Louisa Ponampalan, Fairuz Izmal, Dr Leela Rajamani, Edmund Lau, Abu Muntalib, Izarenah Md Repin, James Bali and Toloy Keriping | Malaysia |
| 3 | Syed Abdullah, Mohd Tamimi, Dr Louisa Ponampalan, Fairuz Izmal, Dr Leela Rajamani, Edmund Lau, Abu Muntalib, Izarenah Md Repin, James Bali and Toloy Keriping | Malaysia |
| 4 | Syed Abdullah, Mohd Tamimi, Dr Louisa Ponampalan, Dr Leela Rajamani, Edmund Lau, Abu Muntalib, Izarenah Md Repin, James Bali, Toloy Keriping. Yuniza, Maya Bankova, Donna Kwan, Duthler Kirk and Nicolas Pilcher | Malaysia and PCT from Abu Dhabi (UAE) |

  - Documents, other printed materials, videos, and soft products (such as CDs or websites)

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication date |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | NONE |  |  |  |  |

| Name of Project Manager: SYED ABDULLAJ BIN SYED ABDUL KADIR | Name of Project Manager Supervisor: |
| --- | --- |
| Signature: | Date: 1O January 2017 | Signature: | Date: |

# Footnotes

Briefly describe progress made during the previous six months highlighting major outcomes/benchmarks achieved during the period.

Information provided in “Quarterly Expenditure Report” should be in line with output/activity progress reported in this table.

Outputs and activities as described in the project proposal or in any updated project revision. Expand table as necessary.

Expand table as necessary

Meeting types: e.g. expert group meeting, project inception workshop, training workshop/seminar, partners consultation workshop, project Steering Committee meeting etc.

Expand table as necessary

Documents and printed material types: e.g. technical publication, meeting report, technical/substantive report, brochures, media releases, etc.