The GEF Dugong and Seagrass Conservation Project

Project Progress Report

| Reporting Period | From: | July / 2016 | To: | December / 2016 |
| --- | --- | --- | --- | --- |

- PROJECT GENERAL INFORMATION

| National Project Code & Title: | (MY 3) Community understanding of dugong and seagrass resources in Johor, Malaysia |
| --- | --- |

| Project Partner(s): | University Sains Malaysia |
| --- | --- |

| Location (country, region/ district and commune/ city/ village/ region etc.) | Pulau Tinggi and Pulau Sibu |
| --- | --- |
| Of which areas under protection (please indicate the name and size of protected areas or locally managed marine areas, if applicable) | Pulau Tinggi Marine Park |

| Project start date | November 2015 | Project intended completion date | September 2018 |
| --- | --- | --- | --- |

- PROJECT PROGRESS

  - Narrative of project progress during the past semester by Project Activity

Since July 2016, I have been working on refining the document on best practices and guidelines for dugong and seagrass conservation. The document was also further reviewed by the progress report reviewers and all comments have been taken into account I received further reviews from one partner and one more technical adviser for the project. These points have been taken into account although some of the comments do not represent a clear understanding of the purpose of the best practice guidelines and its uses. The current draft document is now ready to be presented to the Fisheries Department and the presentation due on January 17, 2017. A PowerPoint slide has also been prepared for it. (I will attach it to this document). In September 2016, the printing of the posters (both Malay and English), A4 stickers and T-shirts were completed. From September 28 to October 2016, and initiation trip was conducted to visit the relevant community members in Pulau Sibu and Pulau Tinggi as well as resort members on these two islands to discuss the upcoming activities and reasons for the project. We discussed the upcoming education programme and their involvement in management initiatives. The villagers of Kg Duku in Pulau Sibu, Rimba resort, Coconut Village resort, Sea Gypsy Resort, Sari Pacifica resort, Twinbeach resort were consulted and informed about the upcoming project. Similarly, the villagers of Kg Pasir Panjang were consulted as well as the existing TAD resort on Pulau Tinggi. Meeting with Kampung Duku village head-although the village head had acknowledged our presence as well as the project. It is unclear, the level in of involvement of the village head in the project as well as the people in his village. We will continue to initiate dialogue and involve him and others in activities in the coming visit. Rimba resort – the resort manager and staff were very interested in the community management of dugong is and also talked about their own conservation with turtles and their plans with opening a turtle sanctuary and hatchery. I have been providing assistance to them in terms of getting expertise from James Cook University and starting a Facebook messenger group with associates from James Cook University. It is hoped this initiation will encourage them to participate in dugong conservation. Waste materials are disposed of using boats whereby solid waste is carried in trash bags and sent to the municipality garbage bins in Tanjung Leman. Sea Gypsy resort – after discussions with Sea Gypsy Resort manager and co-workers, it appears that they are very interested in the project and in the sustainable means of living and already having a sustainable compost and waste management in place. They have an incinerator.

Coconut Village resort – after discussions with the resident dive master he seemed sceptical about the research activities on dugongs going on the island and wished that he could have an explanation of the current research. He was also sceptical about how the research was going on and what people were doing on boats around the island. However he was very keen on the idea of seagrass transplantation although I said that was not the usual means of starting seagrass conservation as well as dugong management. We will continue discussions with him and his colleagues in the future to see what steps he will take in the management of the resources. Sari Pacifica resort – we could not meet up with the general manager or the operations manager at this point in time and we will go back and try again as he was not on the island. Twinbeach resort – they acknowledged our presence and our project but they did not give too many comments about their participation and are waiting to see what the next steps are. Kumpung Tanjung Balang – we met up with the village head of this kumpung and stated the purpose of our visit. We also asked him to host our English teaching and interpretation of the dugong storybook session at his homestay, Tok Mok chalet. He readily agreed to host this session and invite members of the community to come.He supports our conservation work but it is yet to be known the extent of management initiatives he will contribute. TAD marine resort – the operations manager of the resort was approached and we conveyed our intentions of the project. He asked us to contact the main office in Kuala Lumpur and speak to the relevant owner of the resort. We are now trying to fix up an appointment to see him in February, 2017. Education programme (Part 1) at Pulau Tinggi The village head arranged for the inhabitants of Kg. Tanjung Balang to come to the Tok Mok chalet where the program was conducted. Approximately 8 to 10 people came every day from 5 PM to 7 PM from the 24th to 27th October, 2016. The program was an interpretation of the dugong storybook while learning English. People represented included mothers, children and boat men. The program was well received by the participants as flashcards and role-playing was used to interpret the storybook. They were also asked to read passages in the book and interpret what they meant. We had a colouring session to produce posters in English. However few fishermen attended. We compensated for this by going from house to house distributing and explaining the posters and A4 stickers to the fishermen and their families as well as providing T-shirts where possible.

Distribution of education materials The posters, A4 stickers and T-shirts were distributed and explained to almost all inhabitants of the island including those of Kg. Tanjung Balang, Kg. Pasir Panjang, and TAD resort. They were received with great interest and some already understood the contents from previous programmes and knew many things about the dugongs. (Please consult with video that was produced in conjunction with the mid-term review) On October 22, 2016 we set up Facebook page named “Community Management of Dugong and Seagrass in Malaysia” as a means to convey the activities conducted on the project. In November 2016, a part-time project officer was hired to assist with project activities and Administration. Her name is Ong Ke Shin is currently a PhD student at University Sains Malaysia conducting research on community involvement in alternative livelihoods such as tourism. Recently also in November 2016, the Head of the Agro Bio and Environment cluster, Volunteer Secretariat, Universiti Malaya Mr. Muhd Hafiz bin Mohd Amin approached me to ask to volunteer for activities relating to MY3. His group will be available to help us in April 2017.

  - Project implementation progress

| Outputs & Activities interested | Expected completion date | Implementation status as of end of reporting period expressed in % | Describe any problems in delivery and any changes/mitigation action required. |
| --- | --- | --- | --- |
| Output 1: Further refinement of the draft guideline on best practice | End of 2018 | 50% |  |
| Activity 1: Further review by four reviewers of the half yearly report and one partner of the MY project | Early November 2016 | 100% |  |
| Activity 2: Prepared PowerPoint presentation for fisheries department to review | December 2016 | 95% |  |
| Output 2: Production of posters, A4 stickers and T-shirts | 22 /10/2016 | 100% |  |
| Activity 3: Printing of posters and A4 stickers | 22 /10/2016 | 100% |  |
| Activity 4: Sewing of T-shirts | 22 /10/2016 | 100% |  |
| Output 3: Communities understand better the reasons for the implementation for the project as well as the purpose of their involvement | 2/10/2016 | 100% |  |
| Activity 5: Meet key members of the local community such as village head and other members to introduce the project and ask for their involvement in it | 2/10/2016 | 100% |  |
| Activity 6: Meet resort managers and other resort workers to introduce the project and ask for their involvement in it | 2/10/2016 | 100% |  |
| Output 4: Education programme conducted (Part 1) Pulau Tinggi | 28/10/2016 | 100% |  |
| Activity 7: Introduce the environmental dugong story book and teaching English terms in it to inhabitants of Kg Tanjung Balang, Kg Pasir Panjang and TAD Marine Resort (Explain the story) | 28/10/2016 | 100% |  |
| Activity 8: Distribution and explanation of posters and A4 stickers in Pulau Tinggi | 28/10/2016 | 100% |  |
| Activity 9: Distribution of T-shirts to all inhabitants of Pulau Tinggi | 28/10/2016 | 100% |  |

  - Risk and risk management

Please describe internal and external risks (examples included in brackets) that could affect successful implementation of project activities and the proposed risk mitigation measures.

| Risk group | Description | Risk level (Low/ Medium/ High) | Mitigation measures |
| --- | --- | --- | --- |
| Project Management (team capacity, internal communication, co-financing, budget, financial management, reporting, etc.) | There is a lack of coordination and sharing of information between partners especially MY4 which is pertinent to the smooth running of the project as a whole. The attendance for national type administrative meetings needs to be reduced as this is taking away finances needed for fieldwork. These meetings require travel from Penang to Johor Baru and Kuala Lumpur and are costly. | Medium Medium | Better communication Skype meetings. National meetings to be held at USM as a fairer means of cost sharing |
| Socio-cultural issues (external communications, capacity of and work with stakeholders, cultural aspects) |  |  |  |
| Political risks (Political stability in country, political impacts on the project) |  |  |  |
| Environmental risks (severe weather events/ disasters, natural causes negatively affecting project areas, habitats and species) |  |  |  |
| Other (please specify) |  |  |  |

- MONITORING AND EVALUATION

  - Please describe activities for monitoring and evaluation carried out during the reporting period.

Examples include: baseline data collection, stakeholder surveys, field surveys, steering committee meetings to assess project progress, peer review of documentation to ensure quality, mid-term review, etc.

Do not include routine project reporting.

In terms of progress, we have advanced to engage with the communities two times in Sept and Oct, 2016 and it is following the work plan as scheduled. The training of best practice could not be done in 2016 as we were waiting for approvals from Fisheries Department Malaysia in order to present it to the community. These approvals are needed because some of the best practices guidelines might affect the implementation of the Fisheries Act 1985. A meeting has been scheduled to present this guideline to Fisheries Department Malaysia on January 17, 2017 for approval and also review and comment. We have also addressed and taken into account all comments by reviewers.

- OTHER INFORMATION

  - Meetings

| Meeting type | Title | Venue | Dates | Convened by | Organised by | No. of participants | Report issued Y/N | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Internal meeting | Preparatory meeting for printing of educational material and ordering of tablet | USM | 24/8/2016 | Leela Rajamani | Leela Rajamani | 3 | N | English | 24/8/2016 |
| Partner and focal point consultation meeting | Meeting for coordination of project activities GEF 5 for project MY1, MY3, MY4. | Fisheries Department Malaysia Putrajaya | 4/10/2016 | Syed Abdullah | Syed Abdullah | 7 | N | English | 4/10/2016 |
| Internal meeting | Discussion of upcoming trip and activities (24-28th Oct 2016) | USM | 20/10/2016 | Leela Rajamani | Leela Rajamani | 4 | N | English | 20/10/2016 |
| Project coordinator meeting between partners focal point and agencies | National meeting for facilitating team | State Fisheries Department Johor | 25/10/2016 | Syed Abdullah | Syed Abdullah | 11 | N | Malay | 25/10/2016 |
| Project coordinator meeting GEF dugong project | Discussion with project coordinator team project | Hotel Royale Chulan Kuala Lumpur | 31/10/2016 | Syed Abdullah | Syed Abdullah | 14 | N | English | 31/10/2016 |
| Internal meeting | Project coordination meeting MY3 | USM | 22/11/2016 | Leela Rajamani | Leela Rajamani | 5 | N | English | 22/11/2016 |
| Internal meeting | Project activities meeting for January 2017 | USM | 27/12/2016 | Leela Rajamani | Leela Rajamani | 4 | N | English | 27/12/2016 |

  - List(s) of meeting participants

| No. | Name of participant | Nationality |
| --- | --- | --- |
| 1 | Wan Mustaffa bin Wan Din | Malaysian |
|  | Sim Yee Kwang | Malaysian |
|  | Leela Rajamani | Malaysian |
| 2 | Edmund Lau Chai Ming | Malaysian |
|  | Fairul Izmal | Malaysian |
|  | Louisa S.Ponnampalam | Malaysian |
|  | Nicolas Pilcher | British |
|  | Julian Hyde | Malaysian |
|  | Leela Rajamani | Malaysian |
|  | Syed Abdullah bin Syed Abdul Kadir | Malaysian |
| 3 | Wan Mustaffa bin Wan Din | Malaysian |
|  | Sim Yee Kwang | Malaysian |
|  | Leela Rajamani | Malaysian |
|  | Rosita Victor | Malaysian |
| 4 | Abdul Muntalib | Malaysian |
|  | Izarenah bt Mh Repin | Malaysian |
|  | Louisa S.Ponnampalam | Malaysian |
|  | Leela Rajamani | Malaysian |
|  | Syed Abdullah bin Syed Abdul Kadir | Malaysian |
|  | Edmund Lau Chai Ming | Malaysian |
|  | Ng Jol Ern | Malaysian |
|  | James Bali | Malaysian |
| 5 | Maya Bankova-Todorova | Bulgarian |
|  | Mariam | Egyptian |
|  | Kirk | American |
|  | Donna Kwan | Australian |
|  | Abdul Muntalib | Malaysian |
|  | Izarenah bt Mh Repin | Malaysian |
|  | Louisa S.Ponnampalam | Malaysian |
|  | Leela Rajamani | Malaysian |
|  | Syed Abdullah bin Syed Abdul Kadir | Malaysian |
|  | Edmund Lau Chai Ming | Malaysian |
|  | Ng Jol Ern | Malaysian |
|  | James Bali | Malaysian |
|  | Julian Hyde | British |
| 6 | Wan Mustaffa bin Wan Din | Malaysian |
|  | Sim Yee Kwang | Malaysian |
|  | Leela Rajamani | Malaysian |
|  | Norizan Esa | Malaysian |
|  | Ong Ke Shin | Malaysian |
| 7 | Sim Yee Kwang | Malaysian |
|  | Leela Rajamani | Malaysian |
|  | Nurul Farhana Low bt. Abdullah | Malaysian |
|  | Ong Ke Shin | Malaysian |

  - Documents, other printed materials, videos, and soft products (such as CDs or websites)

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Poster | Dugong Education Poster (English) | Leela Rajamani |  |  | October 2016 |
| 2 | Poster | Dugong Education Poster (Malay) | Leela Rajamani |  |  | October 2016 |
| 3 | A4 Stickers | A4 Sticker Best Practice and Boats (English) | Leela Rajamani |  |  | October 2016 |
| 4 | A4 Stickers | A4 Sticker Best Practice and Boats (Malay) | Leela Rajamani |  |  | October 2016 |
| 5 | Facebook page | Community Management of Dugong and Seagrass in Malaysia Facebook address : https://www.facebook.com/Community-Management-of-Dugong-and-Seagrass-in-Malaysia1691388057846078/?ref=aymt_homepage_panel | Leela Rajamani |  |  | 22nd October 2016 |

| Name of Project Manager: | Name of Project Manager Supervisor: |
| --- | --- |
| Signature: | Date: | Signature: | Date: |

# Footnotes

Briefly describe progress made during the previous six months highlighting major outcomes/benchmarks achieved during the period.

Information provided in “Quarterly Expenditure Report” should be in line with output/activity progress reported in this table.

Outputs and activities as described in the project proposal or in any updated project revision. Expand table as necessary.

Expand table as necessary

Meeting types: e.g. expert group meeting, project inception workshop, training workshop/seminar, partners consultation workshop, project Steering Committee meeting etc.

Expand table as necessary

Documents and printed material types: e.g. technical publication, meeting report, technical/substantive report, brochures, media releases, etc.