The GEF Dugong and Seagrass Conservation Project

Project Progress Report

| Reporting Period | From: | June / 2016 | To: | December / 2016 |
| --- | --- | --- | --- | --- |

- PROJECT GENERAL INFORMATION

| National Project Code & Title: | MY 5 – 2115 Overcoming the Knowledge gaps and involvement of Local Community to support the Establishment of a Marine Protected Area (MPA) for Conservation of Dugong and Seagrass in Bay of Brunei, Lawas, Sarawak, Malaysian Borneo |
| --- | --- |

| Project Partner(s): | 1. Assoc. Prof. Dr. Saifullah Arifin Jaaman, (Universiti Malaysia Terengganu) - Co-researcher in dugong studies 2. Dr. Leela Rajamani, (Universiti Sains Malaysia) - Co-researcher in public awareness programme |
| --- | --- |

| Location (country, region/ district and commune/ city/ village/ region etc.) | Malaysia, Sarawak, Limbang Division, Lawas |
| --- | --- |
| Of which areas under protection (please indicate the name and size of protected areas or locally managed marine areas, if applicable) | -Not applicable - |

| Project start date | 30 September 2015 | Project intended completion date | 30 September 2018 |
| --- | --- | --- | --- |

- PROJECT PROGRESS

  - Narrative of project progress during the past semester by Project Activity

  - Project implementation progress

| Outputs & Activities | Expected completion date | Implementation status as of end of reporting period expressed in % | Describe any problems in delivery and any changes/mitigation action required. |
| --- | --- | --- | --- |
| Output 1: 1.1 - Governance structures for community involvement in conservation and monitoring of dugong and seagrass ecosystems established or strengthened in target areas |  |  |  |
| Activity 1: 1.1.1 Conducting community based awareness activities for local communities through Honorary Wildlife Program - 75 local communities trained and appointed as Honorary Wildlife Ranger in 2016 & 2017 | Aug 2017 | 0% | The program was postponed from Aug 2016 to Jan 2017 due to requests from target participants (fishermen, village heads). The request was made by villages as Aug ( South West Monsoon, dry season) is the fishing season for the participants, by conducting the program during North East monsoon (off fishing season), the fishermen can make themselves maximum participation and attendance to the program. |
| Activity 1: 1.1.2 Conducting community awareness activities to school children through Nature ‘n U program – 90 students for 2016 & 2017 | Sept 2017 | 100% | Program completed ahead of planned schedule with a total of 93 secondary school students from four schools in Lawas area participated. |
| Activity 1: 1.1.3 Development of Sarawak State Cabinet Paper for the gazettement of Lawas National Park for protection of dugong and seagrass | June 2017 | 0% | Pending data collection |
| Output 2: (Not applicable for MY5 – 2115) |  |  |  |
| Activity 2: |  |  |  |
| Activity 3: |  |  |  |
| Output 3: 3.1 Critical knowledge gaps (dugongs and seagrass ecosystems) identified and surveys initiated/ completed |  |  |  |
| Activity 3: 3.1.1 Overcoming the knowledge gaps of dugongs in the Brunei bay specifically related to their distribution, abundance, behaviour and movement using unmanned aerial surveillance (UAS) systems or drones | Sept 2018 | 30% | Drone surveys initiated successfully: Subsequent surveys were conducted July, June, August. June survey recorded 2 sightings of dugong, July sighting was one pod of Irrawaddy dolphin, August surveys recorded 6 sightings of dugong. |
| Activity 3: 3.3.3 Determine the High Conservation Area of dugongs in Lawas by observing the spatial and temporal feeding trail patterns on seagrass beds | Aug 2018 | 10% | Identified field research assistant will commence field work in July 2016 |
| Output 4: Output 4.2 Advocacy programmes and advocacy capacity for improved conservation management of dugongs and their seagrass ecosystems developed and implemented |  |  |  |
| Activity 4: 4.2.2 Strategic discussion and advocacy effort to stakeholders e.g. state government agencies, federal agencies, NGOs and Institution of Higher Learning and private sectors to review/formulate dugong related policies and legislations. | May 2017 | 0% | Preliminary discussion with stakeholders is in early stages. |

  - Risk and risk management

Please describe internal and external risks (examples included in brackets) that could affect successful implementation of project activities and the proposed risk mitigation measures.

| Risk group | Description | Risk level (Low/ Medium/ High) | Mitigation measures |
| --- | --- | --- | --- |
| Project Management (team capacity, internal communication, co-financing, budget, financial management, reporting, etc.) | Difficulty in obtaining approval for staffs to participate in this project due work priorities in their respective work stations. | Medium | Train more staffs in survey techniques and in community programs to ensure competent staff available for project implementation when required. |
| Socio-cultural issues (external communications, capacity of and work with stakeholders, cultural aspects) | Suitable time to carry out community programs which maximize number of participants | Low | Multiple series of community programs (Nature and You & Honorary Wildlife Ranger) from 2016 to 2018 to be conducted in one occasion, but meet the projected number of participant involved |
| Political risks (Political stability in country, political impacts on the project) | Pre-planned schedule delay due to requests from political figures | Medium | Prepare the planned program early to avoid unnecessary delays |
| Environmental risks (severe weather events/ disasters, natural causes negatively affecting project areas, habitats and species) | Drone surveys can only be conducted during favourable and safe weather condition | High | Constant weather updates, pre-flight plan to fully utilize dry monsoon season (March to Oct, annually) Utilize available technology (weather forecast apps, UAV flight apps, etc) to ensure safe flying of drones. |
| Other (please specify) |  |  |  |

- MONITORING AND EVALUATION

  - Please describe activities for monitoring and evaluation carried out during the reporting period.

Examples include: baseline data collection, stakeholder surveys, field surveys, steering committee meetings to assess project progress, peer review of documentation to ensure quality, mid-term review, etc.

Do not include routine project reporting.

| No. | Project activities | Timeline |
| --- | --- | --- |
|  |  | From | To |
| 1 | Develop material, module, and planning for Honorary Wildlife Ranger |  |  |
| 2 | Drone Dugong survey in Kuala Lawas | June | Aug |
| 3 | Seagrass mapping via drone planning and trial | June | July |

- OTHER INFORMATION

  - Meetings

| Meeting type | Title | Venue | Dates | Convened by | Organised by | No. of participants | Report issued Y/N | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coordination meeting | Project coordination and local participation meetings with Miri Regional Office Staff | Miri, Sarawak, Malaysia | 24-Jan-16 | Project Manager | SFC | 20 | N | Bahasa Malaysia |  |
| Workshop | BootCamp on QGIS & R | Kuala Lumpur, Malaysia | 6 - 10 Mar 16 | Biodiversity Conservation Society of Sarawak (BCSS) | BCSS | 20 | N | English |  |
| Training | Drone (UAS) flight, maintenance and mission training | Sandakan, Sabah, Malaysia | 13 – 20 Mar 16 | Hornbill Surveys | SFC | 4 | N | English |  |
| Training/Workshop | Health Assessment for Endangered Marine Species | Trang, Thailand | 23-30 June 16 | Dept. of Marine and Coastal Resources Thailand | Phuket Marine Biodiversity Centre | 25 | N | English |  |
| Meeting | GEF Dugong and Seagrass National Coordination Meeting | Putrajaya, Malaysia | 30 Apr 16 | National Coordinator | Dept of Fisheries Malaysia | 10 | N | Bahasa Malaysia |  |

  - List(s) of meeting participants

| No. | Name of participant | Nationality |
| --- | --- | --- |

  - Documents, other printed materials, videos, and soft products (such as CDs or websites)

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication date |
| --- | --- | --- | --- | --- | --- | --- |

| Name of Project Manager: JAMES ANAK BALI | Name of Project Manager Supervisor: OSWALD BRAKEN TISEN |
| --- | --- |
| Signature: | Date: | Signature: | Date: |

# Footnotes

Briefly describe progress made during the previous six months highlighting major outcomes/benchmarks achieved during the period.

Information provided in “Quarterly Expenditure Report” should be in line with output/activity progress reported in this table.

Outputs and activities as described in the project proposal or in any updated project revision. Expand table as necessary.

Expand table as necessary

Meeting types: e.g. expert group meeting, project inception workshop, training workshop/seminar, partners consultation workshop, project Steering Committee meeting etc.

Expand table as necessary

Documents and printed material types: e.g. technical publication, meeting report, technical/substantive report, brochures, media releases, etc.