The GEF Dugong and Seagrass Conservation Project

National Facilitating Committee (MZ6)

Half Yearly Report

| Reporting Period: | From: | July 2016 | To: | December 2016 |
| --- | --- | --- | --- | --- |

I. Introduction

The National Facilitating Committee for the GEF Dugong and Seagrass Conservation Project (MZ6) is implemented by the Ministry of Land, Environment and Rural Development/ National  Directorate of the Environment. The MZ6 with duration from 01 May 2016 to 30 September 2018, has the budget of $80,858.86.

MZ6 seeks to build an informed and effective National Facilitating Committee (NFC) to provide country-level oversight of Project activities in order to ensure that dugong and seagrass conservation considerations are integrated within relevant national-level environmental policy, planning and regulatory frameworks.

Specifically, in this report period, the following outputs were carried out:

- Establish a National Facilitating Committee to provide national oversight of Project activities.

- Identify gaps in legislation and policy instruments and devise recommendations for their improvement to assist the management of seagrass ecosystems and dugong conservation.

- Develop collaboration with Fishing Associations and other relevant stakeholders to promote best practices that reduce damage to seagrass habitats.

- Audío-visual material to be advertised in the media.

II. Development

II.1 - First meeting of project partners

The first meeting of project partners on conservation of dugongs and Seagrass directed by the National Director of the Environment, Ms. Ivete Maibaze was held between on 10 August 2016, in the Conference Room of the National Directorate of the Environment,.

The objectives of the meeting were the following:

- Official launching of Mozambique’s projects;

- Familiarization of the partners with respect to all projects, so that its implementation is as a common programme;

- Harmonization of common activities, such as communications and legal aspects to ensure the efficient use of resources;

- Organize the National Facilitation Committee meetings, where they make parts representatives of the partners present and relevant national institutions linked to conservation of dugongs and seagrass.

Were present at the meeting, the following institutions:

- National Directorate of the Environment/Environmental Management Department (Marine and Coastal Environment)

- Museum of Natural History/Association for the Conservation of Dugongs (Dugongs.org)

- EWT and

- Blue Ventures.

II.2 - Field Trip to Vilankulo and Inhassoro

Within the framework of the implementation of the MZ6 project activities, a joint technical team of technicians of the National Directorate of the Environment (Division of Coastal Management), Provincial Directorate of Land, Environment and Rural Development of Inhambane (Department of Environmental Management), District Services of Infrastructure and Planning-SDPI (Inhassoro and Vilankulo), Provincial Directorate of Sea, inland waters and fisheries (Vilankulo and Inhassoro delegations), University of Eduardo Mondlane - UEM (Department of Biological Sciences-DCB)/Museum of Natural History-MHN), went to the districts of Vilankulo and Inhassoro, between 28 September to 02 October 2016.

This field trip is under the component of creating and strengthening the foundations of governance structures for the involvement of the community in the conservation and monitoring of dugongs and seagrass ecosystems.

GENERAL OBJECTIVE

With this mission, it was intended to listen to the communities to identify gaps policies, planning and regulations concerning to the conservation of dugongs and seagrass ecosystems.

RESULTS

In line with the questionnaire used and in the meetings held in the field, it was possible to gather information and data about the current state of conservation of seagrass and dugongs, as well as, the perception about how fishermen deal with both the seagrass, dugongs, tourism, and local authorities.

The results of the field work have been compiled in separate annex, structurally based on the following points:

- Types of fishing gear;

- Fishing Areas;

- Trends in levels of income;

- Closed season;

- Management of fishing activity;

- Relationship/conflicts between artisanal, semi-industrial and industrial fishing:

- Knowledge of dugongs and other species; and

- Fishermen's Organization.

In parallel to the compilation of data and information collected on the ground, were recorded photographic images and footage of short videos that will later be the subject of analysis and publication in the medias.

In parallel to the district institutions, the following Fisheries Communities Consuls (CCP) and Fisheries Association and Trading Association have been involved:

Fisheries Communities Consuls

| # | District | Name do CCP | Localization | Legal Status | Year of creation | Legalization year |
| --- | --- | --- | --- | --- | --- | --- |
|  | Vilankulo | Macunhe | Bulande | No | 2003 |  |
|  |  | Guitine | Guitine | Yes | 2003 | 14/07/2008 |
|  |  | Chingonguene | Chingonguene | Yes | 2003 | 02/03/2010 |
|  |  | Marape | Marape | Yes | 2003 | 08/03/2010 |
|  |  | Mabandene | Mabandene | Yes | 2005 | 05/12/2007 |
|  |  | Mundego | Mundego | Yes | 2005 | 07/12/2007 |
|  |  | Mangalice | Mangalice | No | 2008 |  |
|  |  | Chichocane | Chichocane | No | 2010 | 16/08/2011 |
|  | Inhassoro | Petane 1 | Petane 1 | Yes | 2004 | 05/12/2007 |
|  |  | Tsondzo | Tsondzo | Yes | 2004 | 05/12/2007 |
|  |  | Fequete | Fequete | Yes | 2005 | 24/07/2006 |
|  |  | Mucocuene | Mucocuene | Yes | 2005 | 24/07/2006 |
|  |  | Nhagondzo | Nhagondzo | Yes | 2007 | 14/07/2008 |
|  |  | Vuca | Vuca | No | 2009 |  |
|  |  | Bazaruto | Sitone | No | 2012 |  |

Fisheries and Trading Associations

| # | Localization/ District | Name of Association | Main Activity | Year of creation | Legal Status | Members |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | H | M | Total |
|  | Vilankulo | Pescadores de Vilankulo (APV) | Fishery | 1996 | Yes | 37 | 2 | 39 |
|  |  | Pescadores Artesanais de Mangalice (APAMA) | Fishery | 2007 | Yes | 13 | 4 | 17 |
|  | Sub-total 1 |  | Fishery |  | Yes | 50 | 6 | 56 |
|  | Inhassoro | Pescadores de Inhassoro (API) | Fishery | 1998 | Yes | 49 | 4 | 53 |
|  |  | Moçambicana dos pescadores de Inhassoro (AMOPI) | Fishery | 2001 | Yes | 25 | 5 | 30 |
|  |  | Pescadores de Arquipélago de Bazaruto (APABA) | Fishery | 2005 | Yes | 20 | 0 | 20 |
|  |  | Comercialização de Pescado de Graças a Deus de Inhassoro (ACOPEGI) | Trading /Fishery | 2008 | Yes | 0 | 5 | 5 |
|  |  | Comercialização de Pescado de Inhassoro (ACOPEI) | Trading / Fishery | 2008 | No | 5 | 5 | 10 |
|  | Sub-total 2 |  |  |  |  | 99 | 19 | 118 |
|  | TOTAL |  |  |  |  | 149 | 25 | 174 |

II.3 - The Second Partners Meeting

The Second Partners Meeting, directed by Ms. Guilhermina Amurane (Head of Environmental Management Department), took place on 14-October-2016, on Chiuta Guest House.

Have participated at the meeting, the following institutions representatives:

- National Directorate of the Environment/Environmental Management Department (Marine and Coastal Environment);

- Museum of Natural History/Association for the Conservation of Dugongs (Dugongs.org),

- EWT, and

- Blue Ventures.

The agenda points of the meeting were the following:

- Preparation of the first meeting of the National Facilitation Committee of 10/17/16 day; and

- Short presentation of the projects (duration, budget, objectives, expected results, balance sheet and plan/2017).

II.4 - The First National facilitation Committee Meeting

Directed by National Environmental Director, Ms. Ivete Maibaze, on 17 October 2016, in the Conference Room of the National Directorate of the environment, took place the first Meeting of the National facilitation Committee of project on conservation of dugongs and Seagrass.

The objectives of the meeting were the following:

- The creation of a National Facilitation Committee (CNF) which will make the supervisory function at the country level of the project activities in order to ensure that the considerations of conservation of dugongs and seagrass are integrated at the national environmental planning and regulatory framework level; and

- Assess the relevance of the sectors proposed for members of the Facilitation Committee.

Were present at the meeting, representatives from the following institutions:

- National Directorate of environment (DINAB)/Department of the Environmental Management (DGA)/Division of marine and coastal environment environment (RAMC);

- National conservation areas Administration (FAA);

- Museum of Natural history;

- National Fisheries Research Institute (IIP);

- National Board of fisheries (ADNAP);

- National Institute of Fisheries and Aquaculture Development (IDEPA);

- Ministry of Transport and Communication;

- national Institute of the Marine (INAMAR);

- World Wildlife Fund (WWF)-Mozambique;

- Association for the Conservation of dugongs (Dugong. Org);

- The Endangered Wildlife Trust (EWT); and

- Blue Ventures Conservation.

Were absent the representatives of:

- International Union of conservation of nature (IUCN); and

- Centro Terra Viva (CTV).

The meeting had as agenda, the following:

- Presentation of a video about the life of dugongs;

- Presentation of the general project;

- Short presentation of the projects (duration, budget, objectives, expected results, balance sheet and plan/2017); and

- Definition of role of different institutions.

Elaborated by:

Anselmo César Gaspar

(Project Manager)

# Text boxes

PROTECTING DUGONGS

CONSERVING SEAGRASS

CHANGE FOR COMMUNITIES