The GEF Dugong and Seagrass Conservation Project

Project Progress Report

| Reporting Period | From: | July / 2016 | To: | Dec / 2016 |
| --- | --- | --- | --- | --- |

- PROJECT GENERAL INFORMATION

| National Project Code & Title: | SB3 – 2124 Mapping critical seagrass fisheries habitats in Lau Lagoon, Solomon Islands |
| --- | --- |

| Project Partner(s): | WorldFish |
| --- | --- |

| Location (country, region/ district and commune/ city/ village/ region etc.) | Lau Lagoon – Malaita Province, Solomon Islands |
| --- | --- |
| Of which areas under protection (please indicate the name and size of protected areas or locally managed marine areas, if applicable) | Fumamato’o LMMA (100 ha) |

| Project start date | March 2016 | Project intended completion date | 30 September 2018 |
| --- | --- | --- | --- |

- PROJECT PROGRESS

  - Narrative of project progress during the past semester by Project Activity

August 2016: Participatory Mapping of Critical Seagrass Fisheries Habitats in Lau Lagoon A field trip was conducted from 28th July to the 13th of August 2016 to conduct the Participatory Mapping of Critical Seagrass Fisheries Habitats in Lau Lagoon. Team members consisted of WorldFish staff and a representative from the Ministry of Environment, Climate Change, Disaster Management and Meteorology (MECDM). The aims of the trip were to Conduct participatory mapping activities workshops with five communities in the Lau Lagoon on seagrass and their perceptions and valuation of seagrass. Collect indigenous stories from locals on seagrass and dugong folklore. Carry out the CMS dugong survey Confirm dugong sittings During the workshop, information on dugongs and seagrass was solicited through Focus Group Discussion (FGD), Pebble Distribution Method (PDM). In addition the team administered a quantitative questionnaire with men and women. In the FGD people were asked to identify and features of importance on a detailed map of the lagoon. This information will be used to develop a map for Lau lagoon, which focuses on the importance of seagrass habitats to the livelihood of people in the Lau Lagoon. The participatory resource map is currently being digitized by the Ministry of Environment, Climate Change, and Disaster Management (MECDM) GIS division. The draft map will be taken out into the field on the next field trip to Lau Lagoon for community review. During the workshops the team also gave a presentation on dugong and seagrass ecology and conservation. This generated much interest and questions, on how to protect key marine resources and species and on the role of the government and customary authorities (see field report) September 2016: MFMR Inshore Fisheries Regulations Workshop #2 WorldFish attended a stakeholders meeting convened by MFMR to discuss the development of the inshore fisheries regulations. Following on from the 2nd NFC meeting in July, recommendations suggested at that time were relayed to MFMR. November 2016: Youth at Work Intern and Mentoring Program, Cross training Staffs from WorldFish were invited by the Secretariat of the Pacific Community (SPC) to give a talk on Community Based Resource Management to more than 200 youths undergoing internship training with the Youth at Work Program of SPC in Honiara. This was seen as an opportunity for an awareness session with the interns and so this incorporated an awareness talk on dugongs and seagrass. November 29 – Dec 1: CBRM Training for Malaita Youth A three-day CBRM training was held in Auki, Malaita for 32 youth representing 10 Malaita communities in November. While this work is not captured directly under the SB3 project, staff took the opportunity to share information on dugongs and seagrass and so we have tagged the activity and its costs as in-kind. A report is provided

  - Project implementation progress

| Outputs & Activities | Expected completion date | Implementation status as of end of reporting period expressed in % | Describe any problems in delivery and any changes/mitigation action required. |
| --- | --- | --- | --- |
| Output 3.1 Critical knowledge gaps (dugongs and seagrass ecosystems) identified and surveys initiated/ completed |  |  |  |
| Activity 3.1.1 Planning meeting with Honiara stakeholders | March 2016 | 100% complete | Combined with First NFC meeting |
| Activity 3.1.2 Conduct a workshop in North Malaita and Lau Lagoon communities on the project | May 2016 | 100% complete | No difficulties in delivery, the major outcome from this activity was community input to the mapping exercise and awareness that the activity would happen. |
| Activity 3.1.3 Planning and capacity development with WorldFish research staff in preparation for participatory seagrass mapping | July 2016 | 100% complete | No difficulties in delivery. Trip schedule changed from July to August 2016 |
| Activity 3.1.4 Conduct 4 mapping workshops in communities (1 day each) | July 2016 | 100% complete | No difficulties in delivery. Conducted 5 mapping workshops in 5 communities. Expected completion dates changed from July to August 2016 |
| Activity 3.1.9 Collect information during mapping exercises | July 2016 | 50% complete | Stories were collected in the August mapping trip however further efforts for more collection of stories will need to be collected. |
| Activity 3.1.10. Liaise with SICCP to collect stories from Western Province sites | April 2017 | 30% complete | Discussions are currently taking place with SICCP. |
| Activity 3.1.11 Compilation of stories and information | September 2017 | 20% complete | WorldFish team is in the process of compiling and editing the stories collected in Lau Lagoon |
| output 4.1 Policy, planning and regulatory gaps reviewed (conservation of dugongs and seagrass ecosystems) and recommendations developed |  |  |  |
| 4.1.1 Policy brief developed to inform improved policy for management and development of lagoonal seagrass ecosystems | July 2018 | 20% complete | No problems in delivery. We are in regular contact with the MECDM and MFMR. |
| 4.1.2 Presentation of provincial government | September 2018 | 0% complete | We are in regular contact with provincial government |

  - Risk and risk management

Please describe internal and external risks (examples included in brackets) that could affect successful implementation of project activities and the proposed risk mitigation measures.

| Risk group | Description | Risk level (Low/ Medium/ High) | Mitigation measures |
| --- | --- | --- | --- |
| Project Management (team capacity, internal communication, co-financing, budget, financial management, reporting, etc.) | Financial reporting delays may be a risk to project implementation. Maintaining key staff is challenging: few qualified and experienced people to conduct scien-based conservation work in Lau Lagoon | Med-High | Issue will need to be solved in January 2017 so that activities can proceed as planned for 2017. Ensure communication with all team members, including PCT |
| Socio-cultural issues (external communications, capacity of and work with stakeholders, cultural aspects) | Misconceptions of communities of the mapping work and involvement of communities may provide a risk to field work. (An issue where communities relayed their grievances with the involvement of certain community individuals during mapping workshops) | Low | Explain to communities at every field work and through community contacts of the intention of the mapping work and that staff and the project are neutral in any community disputes. Make sure that there are no promises made, to avoid unrealistic expectations. |
| Political risks (Political stability in country, political impacts on the project) | None |  |  |
| Environmental risks (severe weather events/ disasters, natural causes negatively affecting project areas, habitats and species) | weather events posing a delay issue at time of field trips | low | Safety will always be paramount and delays may happen in such events especially during field trips. |
| Other (please specify) |  |  |  |

- MONITORING AND EVALUATION

  - Please describe activities for monitoring and evaluation carried out during the reporting period.

Examples include: baseline data collection, stakeholder surveys, field surveys, steering committee meetings to assess project progress, peer review of documentation to ensure quality, mid-term review, etc.

Do not include routine project reporting.

The participatory planning method document underwent review by the technical advisors (Dr. McKenzie). Draft maps developed from initial data collected will be presented to the communities in 2017 for validation and review as more information is gathered.

- OTHER INFORMATION

  - Meetings

| Meeting type | Title | Venue | Dates | Convened by | Organised by | No. of participants | Report issued Y/N | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project workshop | Participatory Mapping of Critical Seagrass Fisheries Habitats in Lau Lagoon | Lau lagoon, Malaita Province | 28th July to 13th August 2016 | WorldFish and Ministry of Environment, Climate Change, and Disaster Management (MECDM) | WorldFish and MECDM | 122 | In Progress | English |  |
| Training workshop/seminar | Community Based Resource Management (CBRM) and Dugong and Seagrass Conservation Program | National Auditorium, Honiara | 9th November 2016 | WorldFish | Secretariat of the Pacific Community (SPC) Youth at Work | 227 | N |  |  |
| Training workshop/seminar | Community based Resource Management (CBRM), Fish Aggregating Device Construction Training and Dugong and Seagrass Conservation Information Dissemination. | Auki, Malaita Province | 22nd – 24th November 2016 | WorldFish | WorldFish | 32 | N |  |  |

  - List(s) of meeting participants

1. Participatory Mapping of Critical Seagrass Fisheries Habitats in Lau Lagoon Attendance

| No. | Name of participant | Nationality |
| --- | --- | --- |
|  | Tauba Community |  |
| 1 | John Kaia | Solomon Islander |
| 2 | Samson Kaia | Solomon Islander |
| 3 | Steve Oru | Solomon Islander |
| 4 | Christina Faisi | Solomon Islander |
| 5 | Benadeta Failo | Solomon Islander |
| 6 | Steward John | Solomon Islander |
| 7 | Daniel Siale | Solomon Islander |
| 8 | John Safe | Solomon Islander |
| 9 | Joseph Alafa | Solomon Islander |
| 10 | Lawrence Wara | Solomon Islander |
| 11 | Gabriel Wasike | Solomon Islander |
| 12 | Eddie Kaia | Solomon Islander |
| 13 | Abraham Eke | Solomon Islander |
| 14 | Patrick Williams | Solomon Islander |
| 15 | David Obeti | Solomon Islander |
| 16 | Rofeni Kalisto | Solomon Islander |
| 17 | Jack Sepo | Solomon Islander |
| 18 | Abraham Talix | Solomon Islander |
|  | Fumatoo Community |  |
| 1 | Egigeo Kwarafi | Solomon Islander |
| 2 | Thomas Waitele | Solomon Islander |
| 3 | Robert Donga | Solomon Islander |
| 4 | Samuel Sale | Solomon Islander |
| 5 | Alick Ben | Solomon Islander |
| 6 | Casper Sale | Solomon Islander |
| 7 | Andrew Ega | Solomon Islander |
| 8 | Ileen Dede | Solomon Islander |
| 9 | Kwakena Heny | Solomon Islander |
| 10 | Eva | Solomon Islander |
| 11 | Kaelonga | Solomon Islander |
| 12 | Aumooi Veronica | Solomon Islander |
| 13 | Gabby Boga | Solomon Islander |
| 14 | Ada Kwarafi | Solomon Islander |
| 15 | Ethel Toata | Solomon Islander |
|  | Takwa Community |  |
| 1 | Noelyn Ngalena | Solomon Islander |
| 2 | Michaella Iuna | Solomon Islander |
| 3 | Mary Rita | Solomon Islander |
| 4 | Marisela Kosi | Solomon Islander |
| 5 | Justina Ruth | Solomon Islander |
| 6 | Madlyn Ngosa | Solomon Islander |
| 7 | Gladis Dora | Solomon Islander |
| 8 | Samson S. | Solomon Islander |
| 9 | George Konairara | Solomon Islander |
| 10 | Banisi Harry | Solomon Islander |
| 11 | Clement Sale | Solomon Islander |
| 12 | Harry Eke | Solomon Islander |
| 13 | Samo Ben | Solomon Islander |
| 14 | Lawrence Tuita | Solomon Islander |
| 15 | Joseph Aruiwafu | Solomon Islander |
| 16 | Luciano Fadaua | Solomon Islander |
| 17 | Joseph kiko | Solomon Islander |
| 18 | John Abakai | Solomon Islander |
| 19 | John Ben | Solomon Islander |
| 20 | Banisi Iroi | Solomon Islander |
| 21 | Harry Iroi | Solomon Islander |
| 22 | Bennie Luda | Solomon Islander |
| 23 | Bino L. | Solomon Islander |
| 24 | Jerry Susui | Solomon Islander |
| 25 | Brown Tolido | Solomon Islander |
| 26 | Melly Rofeta | Solomon Islander |
| 27 | Peter Harry | Solomon Islander |
| 28 | Peter Suimae | Solomon Islander |
| 29 | Alick Kwisufu | Solomon Islander |
|  | Hatodea Community |  |
| 1 | Rose Una | Solomon Islander |
| 2 | Abora Gabby | Solomon Islander |
| 3 | Gladis Sale | Solomon Islander |
| 4 | Rose Laeni | Solomon Islander |
| 5 | Mirrriam Reeves | Solomon Islander |
| 6 | Ilyn Gela | Solomon Islander |
| 7 | Masiala Gabby | Solomon Islander |
| 8 | Oso Malamu | Solomon Islander |
| 9 | Una Maenu | Solomon Islander |
| 10 | Maria Sia | Solomon Islander |
| 11 | Paulin Hendry | Solomon Islander |
| 12 | Aduwane Saeman | Solomon Islander |
| 13 | Lucia Norman | Solomon Islander |
| 14 | Annet Stanley | Solomon Islander |
| 15 | Daga David | Solomon Islander |
| 16 | Elizabeth Abora | Solomon Islander |
| 17 | Fedo MAekol | Solomon Islander |
| 18 | Tony Diau | Solomon Islander |
| 19 | Gabby Kilifa | Solomon Islander |
| 20 | Tony Sale | Solomon Islander |
| 21 | Sale James | Solomon Islander |
| 22 | David Molia | Solomon Islander |
| 23 | Simon Aduwane | Solomon Islander |
| 24 | James Aika | Solomon Islander |
| 25 | B. Maito | Solomon Islander |
| 26 | Jorita Reeves Tagini | Solomon Islander |
| 27 | Norman Defe | Solomon Islander |
| 28 | Gabby Manisari | Solomon Islander |
| 29 | Ratu Gabby | Solomon Islander |
| 30 | Fred Charles | Solomon Islander |
| 31 | Stanley Kebe | Solomon Islander |
| 32 | Gela Paulmary | Solomon Islander |
| 33 | Bugas Moses | Solomon Islander |
|  | Foueda Community |  |
| 1 | Elzah | Solomon Islander |
| 2 | Jenny | Solomon Islander |
| 3 | Rachel Dede | Solomon Islander |
| 4 | Tadoe Sale | Solomon Islander |
| 5 | Noelyn John | Solomon Islander |
| 6 | Mwevalyn Billy | Solomon Islander |
| 7 | Salome Belo | Solomon Islander |
| 8 | Samani Buga | Solomon Islander |
| 9 | Fredrick Bata | Solomon Islander |
| 10 | Milton | Solomon Islander |
| 11 | Jack Harry | Solomon Islander |
| 12 | Kabolo Malefo | Solomon Islander |
| 13 | Sade kwaisufu | Solomon Islander |
| 14 | John Ratu | Solomon Islander |
| 15 | Tuita U. | Solomon Islander |
| 16 | Samo U. | Solomon Islander |
| 17 | Sale B. | Solomon Islander |
| 18 | Tome Luda | Solomon Islander |
| 19 | Luke Tisa | Solomon Islander |
| 20 | David Tuita | Solomon Islander |
| 21 | Abel Satu | Solomon Islander |
| 22 | Waiwai Bata | Solomon Islander |
| 23 | Dede Samani | Solomon Islander |
| 24 | Jerrial Oeta Lui | Solomon Islander |
| 25 | Chris Satu | Solomon Islander |
| 26 | John Bou | Solomon Islander |
| 27 | Tome Seni | Solomon Islander |

Youth at Work internship and mentoring cross training Attendance

| No. | Name of participant | Nationality |
| --- | --- | --- |
| 1 | 227 participants | Solomon Islanders |

CBRM and FAD training Attendance

| No. | Name of participant | Nationality |
| --- | --- | --- |
| 1 | 32 participants | Solomon Islanders |

  - Documents, other printed materials, videos, and soft products (such as CDs or websites)

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication date |
| --- | --- | --- | --- | --- | --- | --- |
|  | N/A |  |  |  |  |  |

| Name of Project Manager: | Name of Project Manager Supervisor: |
| --- | --- |
| Signature: | Date: 17/01/2017 | Signature: | Date: 17-January-2017 |

# Footnotes

Briefly describe progress made during the previous six months highlighting major outcomes/benchmarks achieved during the period.

Information provided in “Quarterly Expenditure Report” should be in line with output/activity progress reported in this table.

Outputs and activities as described in the project proposal or in any updated project revision. Expand table as necessary.

Expand table as necessary

Meeting types: e.g. expert group meeting, project inception workshop, training workshop/seminar, partners consultation workshop, project Steering Committee meeting etc.

Expand table as necessary

Documents and printed material types: e.g. technical publication, meeting report, technical/substantive report, brochures, media releases, etc.