The GEF Dugong and Seagrass Conservation Project

Project Progress Report

| Reporting Period | From: | July 2016 | To: | December 2016 |
| --- | --- | --- | --- | --- |

- PROJECT GENERAL INFORMATION

| National Project Code & Title: | TL1-2135 - Identification of priority sites for conservation of dugongs and seagrasses in Timor-Leste |
| --- | --- |

| Project Partner(s): | Ministry of Agriculture and Fisheries, Ministry of Commerce, Industry, and Environment, & Blue Ventures |
| --- | --- |

| Location (country, region/ district and commune/ city/ village/ region etc.) | Timor-Leste |
| --- | --- |
| Of which areas under protection (please indicate the name and size of protected areas or locally managed marine areas, if applicable) | Nino Konis Santana National Park |

| Project start date | 1 July 2015 | Project intended completion date | 30 September 2018 |
| --- | --- | --- | --- |

- PROJECT PROGRESS

  - Narrative of project progress during the past semester by Project Activity

Output 1.2 Capacity developed for community-based stewardship (conservation and monitoring of dugongs & seagrass) 1.2.1 Key communities identified from survey data Two potential sites for dugong and its seagrass habitat conservation has been identified and discussed among each of those communities of Com (Lautem) and Vila (Atauro Island) 1.2.2 Community entry and socialisation of the dugong and seagrass project to aid selection of pilot community Public awareness and an environmental education campaign on seagrass, turtles and cetaceans in the community and through schools and an Audio visual (TVE) have been conducted. Sites included Dili, Atauro Island, and Oecussi. Output 3.1: Critical knowledge gaps (dugongs and seagrass ecosystems) identified and surveys initiated/ completed Activity 3.1.4: Community based dugong and seagrass survey implemented Survey questionnaire has been translated into Tetum and provided to the survey team members including Blue Ventures, MAF, and UNITAL a private university in Timor-Leste which has an environment program (Currently the National University is not conducting environmental programs). The UNITAL students were selected based on their home municipality. Seven students will implement the survey in their own coastal municipalities. This supports the communities by having survey implementers who speak the local languages. Added to Atauro Island and Lautem district, this will give 9 out of 11 potential coastal municipalities to be surveyed by the end of 2016. Training for Community Conservation Member on Dugong and Sea grass monitoring in Eastern coastal Municipality of Timor-Leste (Lautem) to carry out the monitoring for themselves Activity 3.1.5 Volunteers are trained in seagrass identification, boundary mapping for meadows and carry out ongoing survey's Training materials from Seagrass Watch, were translated into one of the national languages (Tetum) to use in the seagrass training carried out by CI staff. Training for the Project Partners and stakeholders on seagrass mapping and monitoring was completed with 15 attendees. Both classroom theory and onsite practical trainings were provided. Feedback from the participants was very positive and government has asked CI to provide future trainings for their staff. Mapping of the seagrass beds has begun with Atauro Island, the east end of the Timor island, and some of the surrounds of Dili Training for the Community Conservation members from Nino Konis Santana National Park on seagrass mapping and monitoring was completed with 20 attendees. Both classroom theory and onsite practical trainings were provided

  - Project implementation progress

| Outputs & Activities | Expected completion date | Implementation status as of end of reporting period expressed in % | Describe any problems in delivery and any changes/mitigation action required. |
| --- | --- | --- | --- |
| Output 1.2: Capacity developed for community-based stewardship (conservation and monitoring of dugongs & seagrass) | November 2017 | 20% | This Output will begin once Output 3.1 has achieved at least 50% |
| Activity 1.2.2 Community entry and socialisation of the dugong and seagrass project to aid selection of pilot community | June 2017 | 25% |  |
| Output 3.1: Critical knowledge gaps (dugongs and seagrass ecosystems) identified and surveys initiated/ completed | December 2017 | 20% |  |
| Activity 3.1.4: Community based dugong and seagrass survey implemented | January 2017 | 90% |  |
| Activity 3.1.5: Volunteers are trained in seagrass identification, boundary mapping for meadows and carry out ongoing survey's | November 2016 | 80% | Government have requested additional training events, so this activity will not be fully completed until 2017. Due to some tension between government and Blue Ventures, CI was forced to cancel one joint partner training event, and carry out 2 separate trainings instead. |

  - Risk and risk management

Please describe internal and external risks (examples included in brackets) that could affect successful implementation of project activities and the proposed risk mitigation measures.

| Risk group | Description | Risk level (Low/ Medium/ High) | Mitigation measures |
| --- | --- | --- | --- |
| Project Management (team capacity, internal communication, co-financing, budget, financial management, reporting, etc.) |  |  |  |
| Socio-cultural issues (external communications, capacity of and work with stakeholders, cultural aspects) | Communities are unwilling to carry out monitoring over the long term No community agrees to set aside a key dugong or seagrass area for protection | Low Low | Maintaining open and honest communication with communities, and working in partnership with government, will offset any perceived risk |
| Political risks (Political stability in country, political impacts on the project) |  |  |  |
| Environmental risks (severe weather events/ disasters, natural causes negatively affecting project areas, habitats and species) |  |  |  |
| Other (please specify) |  |  |  |

- MONITORING AND EVALUATION

  - Please describe activities for monitoring and evaluation carried out during the reporting period.

Examples include: baseline data collection, stakeholder surveys, field surveys, steering committee meetings to assess project progress, peer review of documentation to ensure quality, mid-term review, etc.

Do not include routine project reporting.

TL1 has carried informal Dugong surveys with communities and there is indication of a group of 5 Dugong on the south side of the island. No Dugong has ever been seen on the eastern tip of the island, with communities not recognising a picture of a Dugong. All communities state that Dugong are protected under traditional law and are not hunted by Timorese. This informal survey is being followed up by the formal Dugong and Seagrass questionnaire being implemented up to end of December 2016. CI has trained Blue Ventures, District Fisheries Officers, and Environment staff in seagrass mapping. Fisheries staff are currently undertaking a whole country seagrass mapping effort, which CI is supporting through the provision SCUBA equipment, boats, and staff time. Several “new” Dugong friendly seagrass beds have been identified and further investigation will be completed by CI and the government staff. CI has trained community Facilitator and Community Conservation members of Nino Konis Santana National Park of Lautem Municipality on Sea grass and the Dugong monitoring

- OTHER INFORMATION

  - Meetings

| Meeting type | Title | Venue | Dates | Convened by | Organised by | No. of participants | Report issued Y/N | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Stakeholder meeting (Atauro Isd.) | Project introduction meeting | Atauro community | 4th August 2016 | CI and Atauro Conservation Group and BV | CI and Atauro Conservation Group | 40+ | N |  |  |
| Partner | New project funding for cetacean survey (incl dugong) | Skype | 10 August | CI Hong Kong | CI Hong Kong | 6 | N | English |  |
| Training | WWF Marine turtle workshop | Darwin | 24 to 26 August | WWF Australia | WWF Australia | 30 | N | English |  |
| Stakeholder meeting (Oecuse) | Project introduction and Public awareness campaign | Oecuse community | 24-28th August 2016 | Ministry of Commerce, Industry, and Environment and CI | MCIE and Conservation International | 100+ | N |  |  |
| Training | CSIRO Marine planning workshop | Hotel Timor | 6 to 8 September | Ministry of Commerce, Industry, and Environment, & CSIRO | Ministry of Commerce, Industry, and Environment | 20+ | N | English |  |
| Partner | Cetacean Survey meeting | Skype | 16th September | CI Timor-Leste | Conservation International | 2 | N | English |  |
| Stakeholder meeting | Public awareness campaign | Timor Plaza and Atauro Island | 21 to 22 September | Conservation International | Conservation International | 100+ | N | Tetun-English |  |
| Stakeholder meeting and Training | Sea grass, Turtle and Cetacean monitoring training | Conservation International | 27-28th Sept-2016 | Conservation International | Conservation International | 15+ | N | Tetun-English |  |
| Survey’s Team meeting | Survey questionairre Discussion | Conservation International | 29th Sept-2016 | Conservation International | Conservation International | +15 | N | Tetun |  |
| Field staff and CCG member training | Sea grass, Turtle and Cetacean monitoring | Com (Nino Konis Santana NP | November 2016 | Conservation International | Conservation International | + 20 | N | Tetun |  |

  - List(s) of meeting participants

| No. | Name of participant | Nationality |
| --- | --- | --- |
|  | Attendance sheets can be provided for those meetings led by CI |  |

  - Documents, other printed materials, videos, and soft products (such as CDs or websites)

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication date |
| --- | --- | --- | --- | --- | --- | --- |

| Name of Project Manager: Anslemo Amaral | Name of Project Manager Supervisor: Trudiann Dale |
| --- | --- |
| Signature: | Date: 30/12/2016 | Signature: | Date: 30/12/2016 |

# Footnotes

Briefly describe progress made during the previous six months highlighting major outcomes/benchmarks achieved during the period.

Information provided in “Quarterly Expenditure Report” should be in line with output/activity progress reported in this table.

Outputs and activities as described in the project proposal or in any updated project revision. Expand table as necessary.

Expand table as necessary

Meeting types: e.g. expert group meeting, project inception workshop, training workshop/seminar, partners consultation workshop, project Steering Committee meeting etc.

Expand table as necessary

Documents and printed material types: e.g. technical publication, meeting report, technical/substantive report, brochures, media releases, etc.