The GEF Dugong and Seagrass Conservation Project

Project Progress Report

| Reporting Period | From: | July 2016 | To: | December 2016 |
| --- | --- | --- | --- | --- |

- PROJECT GENERAL INFORMATION

| National Project Code & Title: | TL3-2137 – Building national-level expertise in dugong and seagrass conservation and mainstreaming dugongs and their seagrass habitats into national coastal zone planning and decision making |
| --- | --- |

| Project Partner(s): | Ministry of Commerce Industry and Environment |
| --- | --- |

| Location (country, region/ district and commune/ city/ village/ region etc.) | Timor-Leste |
| --- | --- |
| Of which areas under protection (please indicate the name and size of protected areas or locally managed marine areas, if applicable) |  |

| Project start date | 1 July 2015 | Project intended completion date | 30 December 2018 |
| --- | --- | --- | --- |

- PROJECT PROGRESS

  - Narrative of project progress during the past semester by Project Activity

Output 3.2 Good practice guidelines for dugongs and seagrass ecosystems conservation developed from project experience Activity: 3.3.2 Build on networks from the workshop to develop/adapt current dugong & seagrass management guidelines in line with Timor-Leste data outcomes The team has reached out to some technical experts from the list of the D&S project to build on knowledge of dugong and seagrass needs. These communications are ongoing. Output 4.1 Policy, planning and regulatory gaps reviewed (conservation of dugongs and seagrass ecosystems) and recommendations developed Activity: 4.1.1 Desktop review and gap analysis of current policy & planning documents as they relate to seagrass and dugongs Based on the current research undertaken by the CI team, there is no existing legislation or planning guidelines for Dugong & Seagrass in place, for Timor-Leste. The CI team has reached out to neighbouring country contacts, and to date Australia is the only country in the region with this level of legislation. Some countries such as Indonesia has localised project based guidelines and planning requirements, but not at national level. Abu Dhabi appears to be the only other country with the same level of legislation in place as Australia. CI’s Marine team and the local authority from Varoana, Vila (Atauro Island) and Com have discussed and decided to put their sea grass area designated into their Suco Regulation (Local Regulation)

  - Project implementation progress

| Outputs & Activities | Expected completion date | Implementation status as of end of reporting period expressed in % | Describe any problems in delivery and any changes/mitigation action required. |
| --- | --- | --- | --- |
| Output 3.2 Good practice guidelines for dugongs and seagrass ecosystems conservation developed from project experience | September 2018 | 20% | The Baseline research identified that not regulations are in place for Timor-Leste. This has delayed the development of the Guidelines as it became evident that only Australia and Abu Dhabi had existing documents to use as a guide for the team. Developing the guidelines is the priority for 2017/2018 |
| Activity: 3.3.2 Build on networks from the workshop to develop/adapt current dugong & seagrass management guidelines in line with Timor-Leste data outcomes | June 2017 | 20% | Data from the questionnaire will not be available until Feb 2017 |
| Output 4.1 Policy, planning and regulatory gaps reviewed (conservation of dugongs and seagrass ecosystems) and recommendations developed | August 2018 | 20% |  |
| Activity: 4.1.1 Desktop review and gap analysis of current policy & planning documents as they relate to seagrass and dugongs | February 2017 | 80% | Delayed starting of the contract pushed this activity back while we identified a volunteer |

  - Risk and risk management

Please describe internal and external risks (examples included in brackets) that could affect successful implementation of project activities and the proposed risk mitigation measures.

| Risk group | Description | Risk level (Low/ Medium/ High) | Mitigation measures |
| --- | --- | --- | --- |
| Project Management (team capacity, internal communication, co-financing, budget, financial management, reporting, etc.) |  |  |  |
| Socio-cultural issues (external communications, capacity of and work with stakeholders, cultural aspects) | Cultural heritage and cultural land owner may not agree on management guidelines | Low | Rights-based approach may be appropriate to apply in this kind of situation |
| Political risks (Political stability in country, political impacts on the project) | Inter-ministerial and stakeholder groups do not agree on management guidelines | Low | The project team and government work in close coordination with stakeholders to avoid any miss-understandings of best practice |
| Environmental risks (severe weather events/ disasters, natural causes negatively affecting project areas, habitats and species) | ZEEZM Strategy Development Plan for Atauro Island | Low-Med | Visibility study and close coordination by project team and government with stakeholders may be appropriate to apply in such kind of situation |
| Other (please specify) |  |  |  |

- MONITORING AND EVALUATION

  - Please describe activities for monitoring and evaluation carried out during the reporting period.

Examples include: baseline data collection, stakeholder surveys, field surveys, steering committee meetings to assess project progress, peer review of documentation to ensure quality, mid-term review, etc.

Do not include routine project reporting.

Through the research behind the Guidelines and legislation analysis, it was identified that within the region of Timor-Leste only Australia has seagrass and dugong legislation and guidelines in place. The other country identified internationally with legislation in place is Abu Dhabi. This has allowed us to establish the baseline for Timor-Leste legislation and regulations

- OTHER INFORMATION

  - Meetings

| Meeting type | Title | Venue | Dates | Convened by | Organised by | No. of participants | Report issued Y/N | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Stakeholder meeting (Dili) | Public awareness campaign | Media (TVE) Office – Dili | 8th July, 2016 | CEO/Directorate of TVE TL, MCIE and CI | MCIE and Conservation International | 5+ | N | Tetun |  |
| Stakeholder meeting (Dili-Schools) | Public awareness campaign | Sao Miguel College (Dili) | July 2016 | MCIE and Conservation International | MCIE and Conservation International | 100+ | N | Tetun-English |  |
| Stakeholder meeting (Atauro Isd.) | Project introduction meeting | Atauro community | 4th August 2016 | CI and Atauro Conservation Group and BV | CI and Atauro Conservation Group | 40+ | N |  |  |
| Stakeholder meeting (Oecuse) | Project introduction and Public awareness campaign | Oecuse community | 24-28th August 2016 | Ministry of Commerce, Industry, and Environment and CI | MCIE and Conservation International | 100+ | N |  |  |
| Stakeholder meeting and Training | Sea grass, Turtle and Cetacean monitoring training | Conservation International | 27-28th Sept-2016 | Conservation International | Conservation International | 15+ | N | Tetun-English |  |
| Survey’s Team meeting | Survey questionnaire Discussion | Conservation International | 29th Sept-2016 | Conservation International | Conservation International | +15 | N | Tetun |  |
| Suco’s Council & Community meeting | Workshop & Participatory Planning for Sea grass Conservation | Vila & Varoana (Atauro Isd) | December-2016 | Fisheries & Conservation International | Conservation International | + 100 | N | Tetun |  |
| Suco’s Council & Community meeting | Workshop & Participatory Planning for Sea grass Conservation | Com (Lautem Municipality) | November-2016 | Fisheries & Conservation International | Conservation International | + 30 | N | Tetun |  |

  - List(s) of meeting participants

| No. | Name of participant | Nationality |
| --- | --- | --- |
|  | Attendance sheets can be provided for those meeting led by CI |  |

  - Documents, other printed materials, videos, and soft products (such as CDs or websites)

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication date |
| --- | --- | --- | --- | --- | --- | --- |

| Name of Project Manager: Anslemo Amaral | Name of Project Manager Supervisor: Trudiann Dale |
| --- | --- |
| Signature: | Date: 30/12/2016 | Signature: | Date: 30/12/2016 |

# Footnotes

Briefly describe progress made during the previous six months highlighting major outcomes/benchmarks achieved during the period.

Information provided in “Quarterly Expenditure Report” should be in line with output/activity progress reported in this table.

Outputs and activities as described in the project proposal or in any updated project revision. Expand table as necessary.

Expand table as necessary

Meeting types: e.g. expert group meeting, project inception workshop, training workshop/seminar, partners consultation workshop, project Steering Committee meeting etc.

Expand table as necessary

Documents and printed material types: e.g. technical publication, meeting report, technical/substantive report, brochures, media releases, etc.