The GEF Dugong and Seagrass Conservation Project

Project Progress Report

| Reporting Period | From: | July/ 2016 | To: | December / 2016 |
| --- | --- | --- | --- | --- |

- PROJECT GENERAL INFORMATION

| National Project Code & Title: | VU 1 – 2139 Project title: To develop recommendations for a National Plan for conservation of dugongs and their seagrass habitats, identify areas important for dugongs and seagrasses conservation in Vanuatu and to raise awareness about dugongs and seagrasses amongst the local communities in these areas. |
| --- | --- |

| Project Partner(s): | Implementing partner: Vanuatu Environmental Science Society (VESS) Supporting Partners: Department of Environmental Protection and Conservation (DEPC), Vanuatu and Vanuatu Fisheries Department (VFD) |
| --- | --- |

| Location (country, region/ district and commune/ city/ village/ region etc.) | Vanuatu |
| --- | --- |
| Of which areas under protection (please indicate the name and size of protected areas or locally managed marine areas, if applicable) | n/a |

| Project start date | 1st July 2015 | Project intended completion date | 30th September 2018 |
| --- | --- | --- | --- |

- PROJECT PROGRESS

  - Narrative of project progress during the past semester by Project Activity

1.2.1. Workshops for communities in hotspots to increase awareness about dugong and seagrass conservation This activity is not due to begin until 2017 and no workshops have begun. However at each of the sites where the questionnaire survey has been conducted booklets about dugongs and seagrass and posters, one on dugongs and one on seagrass, were given out. These books and posters were developed and printed by VESS with funding from a Critical Ecosystem Partnership Fund (CEPF) small grant. There are English and Bislama versions of these materials and the community members chose which they preferred. The materials are being handed out to begin the awareness activities and will be a precursor to the awareness workshops in the communities in 2017. To date 1,986 posters and 776 booklets have been distributed. These materials are also available on the VESS website to anyone to download. 1.2.2. Integration of dugong and seagrass conservation in the management plans of Community Conservation Areas. This activity is not due to begin until 2017. 3.1.1. Adaptation of survey to Vanuatu situation and to include eco-tourism practices and translation into Bishlama This activity was completed prior to this reporting period. 3.1.2. In country training for survey team by CMS-DTG This activity was completed prior to this reporting period. 3.1.3.Conduct the survey throughout Vanuatu and by utilising the existing meetings of networks in existence in Vanuatu Four hundred and fifty-five surveys have been conducted to the end of December 2016. The survey team has visited 25 islands within Vanuatu and visited each of the six provinces. The aim of the project is to complete a minimum of 250 questionnaires. Therefore this aim has been achieved. However there are still at least two places with know significant dugong populations that have not yet been visited. The majority of the data is yet to be entered onto the database. Therefore the survey is not yet complete however we are confident all the interviews will be conducted and all the data uploaded by the end of February 2017. 4.3.2. Attending NFC Christina Shaw (VESS) attended a meeting of the NFC on 28th October 2016. (Minutes of the meetings are enclosed). 4.3.3. Submitting findings and results to NFC Christina Shaw gave the committee an update on the progress of the VU1 project and presented the power point presentation that was to be presented at the EPSC meeting in Kuala Lumpur. NFC committee members gave feedback on both the power point presentation as well as the progress of the VU1 project. Minutes of the meeting are attached.

  - Project implementation progress

| Outputs & Activities | Expected completion date | Implementation status as of end of reporting period expressed in % | Describe any problems in delivery and any changes/mitigation action required. |
| --- | --- | --- | --- |
| Output 1: Output 1.2 Capacity developed for community-based stewardship (conservation and monitoring of dugongs & seagrass) |  |  |  |
| Activity 1: 1.2.1. Workshops for communities in hotspots to increase awareness about dugong and seagrass conservation | July 2018 | 0% | Activity has not started as yet |
| Activity 2: 1.2.2. Integration of dugong and seagrass conservation in the management plans of Community Conservation Areas. | July 2018 | 0% | Activity has not started as yet |
| Output 2: Output 3.1 Critical knowledge gaps (dugongs and seagrass ecosystems) identified and surveys initiated/ completed |  |  |  |
| Activity 3: 3.1.1. Adaptation of survey to Vanuatu situation and to include eco-tourism practices and translation into Bishlama. | October 2015 | 100% | No problems were encountered |
| Activity 4: 3.1.2. In country training for survey team by CMS-DTG | December 2015 | 100% | No problems were encountered |
| Activity 5: 3.1.3.Conduct the survey throughout Vanuatu and by utilising the existing meetings of networks in existence in Vanuatu | November 2016 | 90% | The survey is covering the whole of the Vanuatu islands archipelago. It is remote and some places are difficult to get to. There was a significant amount of travel conducted between July and December 2016 to conduct the questionnaire survey. Domestic air travel is not only expensive but is not completely reliable. The survey team suffered from cancelled and delayed flights. Interisland ferries are equally unreliable and travel less often and therefore end up just as expensive taking into account the addition accommodation. Delays and cancellations interfered with the planning of the travel as well as increasing the cost, as additional accommodation was required whilst the team were waiting for flights. Two members of the survey team are new graduates however 5 of the team are still studying and therefore the surveys they were involved with had to be conducted around their study commitments and exams. Some other people volunteered to conduct the questionnaires in their own areas or places they were visiting. They were given training on the questionnaire technique and questionnaire materials. However most of the volunteers only managed to conduct one of two surveys and therefore the data obtained was insufficient in their area. Subsequently the survey team had to or will have to visit these areas anyway to complete the survey. The original plan was to use the meetings of networks in Vanuatu to conduct some questionnaires where many people from areas were collected in one place. However this has proved difficult to arrange. We had planned to conduct interviews and the “Lukoatem Gud long Santo festival” in the island of Santo. We spoke to the organisers and agreed to be part of the festival and conducting awareness about dugongs and seagrass as part of the program. However the festival was postponed and then cancelled. We had also hoped to interview the fisheries extension officers when they came to Port Vila for training but the officer organising the training changed and we only found out about the timing of the training after the training had already occurred. These challenges have resulted in a small delay to the completion of the questionnaire survey. However as the bulk of the travel is now finished it is anticipated that the survey will be finished shortly. A student studying zoology in Australia is in Vanuatu for the summer holidays and has volunteered with VESS. She is assisting with the data entry for the survey. |
| Activity 6: 3.1.4. Results of survey analysed and map of hotspots for dugong and seagrass conservation complied | January 2017 | 0% | Activity has not started as yet. Once all the questionnaires have been conducted and the data has been uploaded to database the data will be analysed and the hotspots identified. The maps can then be produced. |
| Output 3: Output 4.3 Capacity for national and regional networking and contribution to global policy for effective dugong and seagrass conservation in Indian and Pacific Ocean basins |  |  |  |
| Activity 7: 4.3.1. Recommendations developed for the establishment of a National Plan for conservation of dugongs and their seagrass habitats. | January 2018 | 5% | It was decided at a previous NFC meeting to begin work on the Nation Plan once the survey results were available. |
| Activity 8: 4.3.2. Attending NFC | September 2018 | 57% | No problems were encountered |
| Activity 9 4.3.3. Submitting findings and results to NFC | September 2018 | 57% | No problems were encountered |

  - Risk and risk management

Please describe internal and external risks (examples included in brackets) that could affect successful implementation of project activities and the proposed risk mitigation measures.

| Risk group | Description | Risk level (Low/ Medium/ High) | Mitigation measures |
| --- | --- | --- | --- |
| Project Management (team capacity, internal communication, co-financing, budget, financial management, reporting, etc.) | The questionnaire survey team is, and the awareness workshop delivery team will be, compromised of volunteers. Some of these volunteers may not have the time to conduct the activities due to other commitments such as study or work. Co-financing commitment form the supporting partners are not easily fulfilled due to the limited capacity of the government departments. Staff time, equipment and premises may not be available due to other work commitments. | Low | Twenty-three people were trained for the questionnaire survey team therefore, there was enough reserve capacity to conduct the survey. In 2016 5 dedicated undergraduate students have been committed members of the survey team. This has proven to be the case. In Vanuatu there has been a significant increase in the number of projects in the aftermath of Cyclone Pam. Due to the lack of suitable other organisations to implement the projects the task has fallen on the Department of Environmental Protection and the Vanuatu Fisheries Department. These departments are already under-resourced and therefore there is little capacity for officers in the government departments to assist with the Dugong and Seagrass Conservation Project, although the departments are still supportive of the project. Other sources of co-funding from VESS, other NGOs and projects and the private sector can be sort to fulfil the over all project co-funding commitment |
| Socio-cultural issues (external communications, capacity of and work with stakeholders, cultural aspects) | Communities not willing to be interviewed for the questionnaire survey. Communities not willing to create CCAs or to incorporate dugong and seagrass conservation into their management plans. | Low | Training survey team members in good communication skills so they can fully explaining the aims and importance of the survey. So far the communities have been very willing to participate in the surveys and have expressed great interest in the team returning to conduct awareness training. Ensuring the awareness workshops are well delivered and ensuring the results of the survey are available to the communities will help them to understand the importance of dugong and seagrass conservation. |
| Political risks (Political stability in country, political impacts on the project) | Vanuatu has a history of instability within the government. However since the election earlier this year the government appears to have been relatively stable. It is not anticipated that the political situation will affect the project activities, however there may be changes to government departments that may alter the relationships with the project partners. | Low | Continuation of VESS’s good relationships with government departments and officers. |
| Environmental risks (severe weather events/ disasters, natural causes negatively affecting project areas, habitats and species) | Port Vila is reportedly the city most at risk of natural disasters. Vanuatu is within the cyclone belt and the pacific rim of fire and therefore susceptible to cyclones, flooding, volcanic eruption, earthquakes and tsunamis. However it is anticipated that although the project activities may be delayed by a natural disaster, they will still be able to be completed at a later date. | Medium | The majority of fieldwork that involves VESS teams members travelling to remote islands will be conducted outside of the main cyclone risk season. |
| Other (please specify) |  |  |  |

- MONITORING AND EVALUATION

  - Please describe activities for monitoring and evaluation carried out during the reporting period.

Examples include: baseline data collection, stakeholder surveys, field surveys, steering committee meetings to assess project progress, peer review of documentation to ensure quality, mid-term review, etc.

Do not include routine project reporting.

The booklets and posters being handed out to the communities at the time of the questionnaire surveys were written and printed with funding from a different project but were designed complement this project. Donna Kwan, Nicolas Pilcher and Len McKenzie from the Convention on the Conservation of Migratory Species of Wild Animal (CMS)- Dugong MOU Technical Team of Experts and Mike Donoghue, Threatened and Migratory Species Adviser at Secretariat of the Pacific Regional Environment Programme (SPREP) as well as officers from the Department of Environmental Protection Conservation (DEPC) and the Vanuatu Fisheries Department (VFD) reviewed the information in the booklets and posters to ensure they were technically correct prior to printing and distributing.

- OTHER INFORMATION

  - Meetings

| Meeting type | Title | Venue | Dates | Convened by | Organised by | No. of participants | Report issued Y/N | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Expert group meeting | Meeting of NFC | VESS Office | 28th October 2016 | Dugong Focal Point / DEPC | Trinison Tari / Christina Shaw | 7 | Y | English | 28th October 2016 |

  - List(s) of meeting participants

| No. | Name of participant | Nationality |
| --- | --- | --- |
| 1 | Names are listed in minutes of the NFC meeting |  |

  - Documents, other printed materials, videos, and soft products (such as CDs or websites)

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Posts on VESS Facebook Page | https://www.facebook.com/vanuatuconservation | Christina Shaw | VESS |  | July – December 2016 |
| 2 | Project Page on VESS website | Our current projects www.vanuatuconservation.org/our-projects/current-projects | Christina Shaw | VESS |  | 15 April 2016 |
| 3 | Poster | Koafis blong Vanuatu | Christina Shaw | VESS |  | Available on the VESS website |
| 4 | Poster | Dugongs of Vanautu | Christina Shaw | VESS |  | Available on the VESS website |
| 5 | Poster | Seagrass facts | Christina Shaw | VESS |  | Available on the VESS website |
| 6 | Poster | Gras Blong Solwata | Christina Shaw | VESS |  | Available on the VESS website |
| 7 | Book | Dugongs and their Seagrass habitat | Christina Shaw | VESS |  | Available on the VESS website |
| 8 | Book | Kaofis mo plis we oli kakae gras blong solwata | Christina Shaw | VESS |  | Available on the VESS website |
| 9 | Minutes | Minutes for Meeting of the National facilitating Committee (NFC) for the GEF Dugong and Seagrass Conservation Project on 28th October 2016 | Christina Shaw | VESS |  | 28th October 2016 |
| 9 | Photos of the survey team conducting surveys | Various photos | Christina Shaw, Douglas Koran and the survey team | VESS |  | July – December 2016 |

| Name of Project Manager: Christina Shaw | Name of Project Manager Supervisor: n/a |
| --- | --- |
| Signature: Christina Shaw | Date: 10th December 2016 | Signature: | Date: |

# Footnotes

Briefly describe progress made during the previous six months highlighting major outcomes/benchmarks achieved during the period.

Information provided in “Quarterly Expenditure Report” should be in line with output/activity progress reported in this table.

Outputs and activities as described in the project proposal or in any updated project revision. Expand table as necessary.

Expand table as necessary

Meeting types: e.g. expert group meeting, project inception workshop, training workshop/seminar, partners consultation workshop, project Steering Committee meeting etc.

Expand table as necessary

Documents and printed material types: e.g. technical publication, meeting report, technical/substantive report, brochures, media releases, etc.