The GEF Dugong and Seagrass Conservation Project

Project Progress Report

| Reporting Period | From: | July / 2016 | To: | December / 2016 |
| --- | --- | --- | --- | --- |

- PROJECT GENERAL INFORMATION

| National Project Code & Title: | VU 2 – 2140 VU2: National Facilitating Committee for the GEF Dugong and Seagrass Conservation Project |
| --- | --- |

| Project Partner(s): | Implementing partner: Vanuatu Environmental Science Society (VESS) Supporting Partners: Department of Environmental Protection and Conservation (DEPC), Vanuatu and Vanuatu Fisheries Department (VFD) |
| --- | --- |

| Location (country, region/ district and commune/ city/ village/ region etc.) | Vanuatu |
| --- | --- |
| Of which areas under protection (please indicate the name and size of protected areas or locally managed marine areas, if applicable) | n/a |

| Project start date | 1st July 2015 | Project intended completion date | 30th September 2018 |
| --- | --- | --- | --- |

- PROJECT PROGRESS

  - Narrative of project progress during the past semester by Project Activity

4.3.1. Formation of National Facilitating Committee (NFC) This activity was completed within a prior reporting period. 4.3.2. 6-monthly meeting of NFC A meeting of the NFC was convened on 28th October 2016. This was the 4th time the NFC has met. Christina Shaw (VESS) gave a report on the activities that had taken place for the VU1 project and presented the power point presentation to be presented at the EPSC II meeting in Kuala Lumpur. The NFC gave feedback and suggested some changes and further inclusions to the PPP. The minutes of the meeting are attached. 4.3.3. Press releases / communications activities / publications on internet sites The VESS Facebook page https://www.facebook.com/vanuatuconservation has carried posts of the dugong survey team at work during the questionnaire survey. The Dugong and Seagrass Conservation Project in Vanuatu was featured in a magazine article in Scuba Diver Australasia in August this year. The article is attached. The VESS website http://www.vanuatuconservation.org continues to features a page of current projects including the details of the Dugong and Seagrass Conservation Project. The educational materials which were produced with a small grant from the Critical Ecosystem Partnership Fund (CEPF) and are being given out during this project are also available to download from the VESS website.

  - Project implementation progress

| Outputs & Activities | Expected completion date | Implementation status as of end of reporting period expressed in % | Describe any problems in delivery and any changes/mitigation action required. |
| --- | --- | --- | --- |
| Output 1: Output 4.3 Capacity for national and regional networking and contribution to global policy for effective dugong and seagrass conservation in Indian and Pacific Ocean basins |  |  |  |
| Activity 1: 4.3.1. Formation of National Facilitating Committee (NFC) | September 2015 | 100% | No problems were encountered |
| Activity 2: 4.3.2. 6-monthly meeting of NFC | September 2018 | 57% | Whilst most of the members of the NFC attend the meetings, the representative of the Vanuatu Cultural Centre, Francis Hickey, is still yet to attend any of the meetings. It was decides the last NFC meeting to ask the cultural centre to send a different representative to the NFC meetings in the future. |
| Activity 3: 4.3.3. Press releases / communications activities / publications on internet sites | September 2018 | 45% | No problems were encountered. |

  - Risk and risk management

Please describe internal and external risks (examples included in brackets) that could affect successful implementation of project activities and the proposed risk mitigation measures.

| Risk group | Description | Risk level (Low/ Medium/ High) | Mitigation measures |
| --- | --- | --- | --- |
| Project Management (team capacity, internal communication, co-financing, budget, financial management, reporting, etc.) | Co-financing commitment form the supporting partners are not easily fulfilled due to the limited capacity of the government departments. Staff time, equipment and premises may not be available due to other work commitments. | Medium | Other sources of co-funding from VESS, other NGOs and projects and the private sector can be sort to fulfil the over all project co-funding commitment. |
| Socio-cultural issues (external communications, capacity of and work with stakeholders, cultural aspects) | The lack of priority placed on conservation in Vanuatu may result in a low level of commitment from the agencies invited to participate in the NFC. Many government departments, NGOs and civil society organisations are under-funded and under-staffed and therefore may not have the time or capacity to send a representative to the NFC. | Low | The representatives will be encouraged to participate. The dates of the meetings will be managed so they do not clash with other meetings that may be deemed of greater priority. So far the there has been a good commitment to the NFC by most of the government departments involved. For the next NFC meeting the Vanuatu cultural Centre will be asked to send a different representative. |
| Political risks (Political stability in country, political impacts on the project) | Vanuatu has a history of instability within the government. However since the election early in 2016 the government appears to have been relatively stable. It is not anticipated that the political situation will affect the project activities. However there may be changes to government departments that may alter the relationships with the project partners. | Low | Continuation of good relationships with government departments and officers. |
| Environmental risks (severe weather events/ disasters, natural causes negatively affecting project areas, habitats and species) | Port Vila is reportedly the city most at risk of natural disasters. Vanuatu is within the cyclone belt and the pacific rim of fire and therefore susceptible to cyclones, flooding, volcanic eruption, earthquakes and tsunamis. However it is anticipated that although the project activities may be delayed by a natural disaster, they will still be able to be completed at a later date. | Low | Meetings and activities may require rescheduling should a natural disaster occur. |
| Other (please specify) |  |  |  |

- MONITORING AND EVALUATION

  - Please describe activities for monitoring and evaluation carried out during the reporting period.

Examples include: baseline data collection, stakeholder surveys, field surveys, steering committee meetings to assess project progress, peer review of documentation to ensure quality, mid-term review, etc.

Do not include routine project reporting.

The NFC committee members were consulted on the presentation of Vanuatu’s project to the EPSC II meeting to ensure the presentation was an accurate depiction of the project’s progress.

- OTHER INFORMATION

  - Meetings

| Meeting type | Title | Venue | Dates | Convened by | Organised by | No. of participants | Report issued Y/N | Language | Dated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Expert group meeting | Meeting of NFC | VESS Office | 298h October 2016 | Dugong Focal Point / DEPC | Trinison Tari / Christina Shaw | 7 | Y | English | 28th March 2016 |

  - List(s) of meeting participants

| No. | Name of participant | Nationality |
| --- | --- | --- |
| 1 | Names are listed in minutes of the NFC meeting |  |

  - Documents, other printed materials, videos, and soft products (such as CDs or websites)

| No | Type | Title | Author(s) Editor(s) | Publisher | ISBN | Publication date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Posts on VESS Facebook Page | https://www.facebook.com/vanuatuconservation | Christina Shaw | VESS |  | July – December 2016 |
| 2 | Project Page on VESS website | Our current projects www.vanuatuconservation.org/our-projects/current-projects | Christina Shaw | VESS |  | 15 April 2016 |
| 3 | Minutes | Minutes for Meeting of the National facilitating Committee (NFC) for the GEF Dugong and Seagrass Conservation Project on 28th October 2016 | Christina Shaw | VESS |  | 28th March 2016 |
| 3 | Magazine article | Discovering Vanuatu’s Dugongs | Alice Grainger | Scuba Diver Australasia Magazine |  | 28th March 2016 |

| Name of Project Manager: Christina Shaw | Name of Project Manager Supervisor: n/a |
| --- | --- |
| Signature: Christina Shaw | Date: 9th January 2016 | Signature: | Date: |

# Footnotes

Briefly describe progress made during the previous six months highlighting major outcomes/benchmarks achieved during the period.

Information provided in “Quarterly Expenditure Report” should be in line with output/activity progress reported in this table.

Outputs and activities as described in the project proposal or in any updated project revision. Expand table as necessary.

Expand table as necessary

Meeting types: e.g. expert group meeting, project inception workshop, training workshop/seminar, partners consultation workshop, project Steering Committee meeting etc.

Expand table as necessary

Documents and printed material types: e.g. technical publication, meeting report, technical/substantive report, brochures, media releases, etc.